## Sheet1
Milestone ID | Milestone Name | WBS ID | Task Name | Start Date | End Date | Duration (Days) | Responsible Team | Status
M-001 | Project Kickoff | N/A | Project Initiation | 2024-01-01 | 2024-01-02 | 2 | Project Management | Completed
M-002 | Requirements Gathering Completed | WBS-000 | Requirements Documentation | 2024-01-05 | 2024-01-25 | 20 | Business Analysts | Completed
M-003 | Design Phase Completed | WBS-001 to WBS-005 | UI/UX Design and Prototyping | 2024-02-01 | 2024-02-28 | 28 | UI/UX Design Team | Completed
M-004 | User Registration System Deployment | WBS-001 | User Registration System | 2024-03-01 | 2024-03-15 | 15 | Development Team | Completed
M-005 | Inventory Management Deployment | WBS-002 | Admin Inventory Management | 2024-03-16 | 2024-04-05 | 20 | Development Team | Completed
M-006 | Parent Dashboard Deployment | WBS-003 | Parent Dashboard | 2024-03-16 | 2024-03-31 | 15 | Development Team | Completed
M-007 | Secure Payment System Deployment | WBS-004 | Secure Payment Integration | 2024-04-01 | 2024-04-15 | 15 | Development Team | Completed
M-008 | Order Tracking System Deployment | WBS-006 | Order Tracking System | 2024-03-17 | 2024-03-31 | 15 | Development Team | Completed
M-009 | AI-Powered Supply Prediction Deployed | WBS-007 | AI-Powered Supply Prediction | 2024-04-05 | 2024-05-05 | 30 | AI & Development Team | Completed
M-010 | Project Testing Phase Completed | WBS-000 | System Testing and Quality Assurance | 2024-05-01 | 2024-05-25 | 25 | QA & Testing Team | Completed
M-011 | User Training Completed | WBS-000 | Training and Support | 2024-05-20 | 2024-05-30 | 10 | Training Team | Completed
M-012 | Project Launch | N/A | Official Launch of the Application | 2024-06-01 | 2024-06-01 | 1 | Project Management | Completed
M-013 | Post-Launch Support | WBS-000 | Post-Launch Support and Maintenance | 2024-06-02 | 2024-06-30 | 28 | Support Team | Ongoing
M-014 | Final Review and Closure | N/A | Final Project Review and Documentation | 2024-06-25 | 2024-06-30 | 5 | Project Management | Planned