## Log
ID | User Story | Epic | Priority | Acceptance Criteria | Estimated Effort (Story Points) | Status
PB-001 | As a parent, I want to register and create an account so that I can access the app features. | User Registration | High | - User can successfully register with email. - Error message for invalid inputs. | 5 | Backlog
PB-002 | As an admin, I want to manage inventory levels so that I can keep track of stock availability. | Inventory Management | High | - Admin can add, update, and delete items in the inventory. - Low stock alerts are generated. | 8 | Backlog
PB-003 | As a parent, I want to view my order history so that I can track my past purchases. | Parent Dashboard | Medium | - Order history is displayed with details like date, items, and status. | 5 | Backlog
PB-004 | As an admin, I want to receive low-stock alerts so that I can reorder supplies on time. | Notifications & Alerts | High | - Alerts are triggered when stock falls below the threshold. - Email and in-app notifications are sent. | 3 | Backlog
PB-005 | As a supplier, I want to manage my product listings so that I can keep them up-to-date. | Supplier Product Management | Medium | - Supplier can add, update, and remove products. - Changes are reflected in real-time. | 8 | Backlog
PB-006 | As a parent, I want to add items to my wishlist so that I can purchase them later. | Wishlist | Low | - Items can be added and removed from the wishlist. - Wishlist items can be moved to the cart. | 3 | Backlog
PB-007 | As an admin, I want to generate reports on inventory usage so that I can optimize stock levels. | Reporting Dashboard | Medium | - Reports can be generated based on date range, product category, and supplier. | 5 | Backlog
PB-008 | As a parent, I want to make payments securely so that I can complete my purchase. | Secure Payment | High | - Multiple payment methods are supported. - Payment is processed securely and confirmed. | 8 | Backlog
PB-009 | As a parent, I want to search for specific school supplies so that I can find what I need quickly. | Product Search & Filter | High | - Search results are displayed based on keywords and filters. - Filtering options are available for category, price, and supplier. | 5 | Backlog
PB-010 | As a parent, I want to track my order status so that I know when to expect delivery. | Order Tracking | High | - Order status is displayed in real-time. - Notifications are sent for each status change. | 5 | Backlog
PB-011 | As a parent, I want to set up recurring orders for frequently used items so that I don't have to reorder manually. | Recurring Orders | Medium | - Parent can schedule recurring orders. - Recurring orders can be modified or canceled. | 8 | Backlog
PB-012 | As an admin, I want to assign roles and permissions to users so that I can control access to the system. | Role-Based Access Control | High | - Roles can be assigned and modified. - Permissions are enforced based on roles. | 5 | Backlog
PB-013 | As a parent, I want to receive notifications about promotions so that I can save money on purchases. | Notifications & Alerts | Low | - Notifications are sent for relevant promotions. - Notifications can be managed in user settings. | 3 | Backlog
PB-014 | As an admin, I want to evaluate supplier performance so that I can make informed purchasing decisions. | Supplier Evaluation | Medium | - Performance reports include metrics like delivery time and order accuracy. - Suppliers can be rated and reviewed. | 5 | Backlog
PB-015 | As a parent, I want to compare similar products so that I can make the best purchase decision. | Product Comparison Tool | Medium | - Product details are displayed side-by-side. - Comparison includes price, ratings, and availability. | 5 | Backlog
PB-016 | As a user, I want to reset my password so that I can regain access if I forget it. | User Account Management | High | - User receives a reset link via email. - Password is successfully updated. | 3 | Backlog
PB-017 | As a parent, I want to view supply suggestions based on my child's class schedule so that I can purchase relevant items. | Supply Suggestions | Medium | - Suggestions are displayed based on the current class schedule. - Suggestions can be added to the cart. | 8 | Backlog
PB-018 | As a supplier, I want to view my sales performance so that I can understand demand trends. | Supplier Dashboard | Medium | - Dashboard displays metrics like total sales, top-selling items, and revenue trends. | 5 | Backlog
PB-019 | As an admin, I want to access a multi-location dashboard so that I can manage supplies for multiple schools. | Multi-Location Management | Medium | - Admin can switch between locations. - Location-specific inventory and order data are displayed. | 8 | Backlog
PB-020 | As a user, I want the app to support multiple languages so that I can use it in my preferred language. | Multi-Language Support | Low | - User can select their preferred language. - All text in the app is translated accurately. | 8 | Backlog
PB-021 | As an admin, I want to see a visual representation of inventory trends so that I can plan future orders. | Reporting Dashboard | Medium | - Trends are displayed using graphs and charts. - Data can be filtered by time period and category. | 5 | Backlog
PB-022 | As a parent, I want to receive real-time updates on product availability so that I know when items are back in stock. | Notifications & Alerts | Medium | - Notifications are sent when out-of-stock items are back in inventory. - Users can opt-in to notifications for specific items. | 3 | Backlog
PB-023 | As an admin, I want to create custom reports so that I can analyze data in a way that suits my needs. | Custom Reporting Tool | Medium | - Admin can select data fields and criteria for custom reports. - Reports can be saved and exported. | 8 | Backlog
PB-024 | As a parent, I want to access chat support so that I can get help with order issues or questions. | In-App Chat Support | Medium | - Chat support is accessible from the app. - Users can rate the chat experience. | 5 | Backlog
PB-025 | As a parent, I want to participate in group purchases so that I can get bulk discounts on school supplies. | Group Purchasing | Low | - Users can join or create group purchases. - Discounts are applied based on group size. | 8 | Backlog
PB-026 | As a parent, I want to receive real-time notifications on order status so that I am informed about shipment and delivery updates. | Order Tracking | Medium | - Notifications are sent for each order status change. - Users can view shipment tracking information. | 4 | Backlog
PB-027 | As an admin, I want to monitor application performance metrics so that I can ensure smooth operations. | Performance Monitoring | High | - Real-time performance metrics are displayed. - Alerts are triggered for performance issues. | 6 | Backlog
PB-028 | As a user, I want to access FAQs and support articles so that I can resolve common issues on my own. | Support & Documentation | Low | - FAQs and support articles are easily accessible. - Users can search for specific topics. | 3 | Backlog
PB-029 | As a parent, I want to apply discount codes during checkout so that I can reduce my total purchase cost. | Secure Payment | Medium | - Discount codes can be entered during checkout. - Total cost is updated based on the applied code. | 3 | Backlog
PB-030 | As a supplier, I want to set up promotional offers so that I can attract more customers. | Supplier Product Management | Medium | - Suppliers can create, update, and remove promotional offers. - Offers are displayed on relevant product pages. | 5 | Backlog
PB-031 | As a parent, I want to save multiple shipping addresses so that I can choose the correct one during checkout. | User Account Management | Low | - Multiple addresses can be saved and selected during checkout. - Addresses can be edited or deleted. | 3 | Backlog
PB-032 | As an admin, I want to view historical data trends so that I can make data-driven decisions. | Reporting Dashboard | Medium | - Historical data is displayed in charts and tables. - Data can be filtered by date range and category | 3 | Backlog
PB-033 | As a parent, I want to receive recommendations for school supplies based on my previous purchases so that I can save time. | Supply Suggestions | Medium | - Recommendations are displayed on the dashboard. - Users can add recommended items to the cart. | 5 | Backlog
PB-034 | As an admin, I want to manage vendor contracts and agreements so that I can maintain compliance and terms. | Supplier Management | Medium | - Contracts and agreements can be uploaded, tracked, and managed. - Alerts are sent for expiring contracts. | 8 | Backlog
PB-035 | As a parent, I want to set notification preferences so that I only receive relevant updates. | Notifications & Alerts | Low | - Users can select which notifications to receive. - Preferences can be updated in settings. | 3 | Backlog
PB-036 | As a supplier, I want to view analytics on product performance so that I can optimize my offerings. | Supplier Dashboard | Medium | - Analytics include sales trends, top-performing products, and user feedback. | 5 | Backlog
PB-037 | As an admin, I want to set up approval workflows for large orders so that I can ensure they meet budget and policy requirements. | Order Management | Medium | - Approval workflows are configurable for different order sizes. - Notifications are sent for approvals. | 8 | Backlog
PB-038 | As a parent, I want to receive reminders for important school supply deadlines so that I don’t miss them. | Notifications & Alerts | Medium | - Reminders are sent based on the academic calendar. - Users can opt-in or out of reminders. | 3 | Backlog
PB-039 | As an admin, I want to compare supplier pricing so that I can choose the best option for school supplies. | Supplier Management | Medium | - Pricing comparison tool is available for all active suppliers. - Comparison includes total cost and delivery terms. | 5 | Backlog
PB-040 | As a parent, I want to be able to cancel my order within a specified time frame so that I have flexibility in purchasing. | Order Management | Medium | - Orders can be canceled within a defined time window. - Refunds or credits are applied upon cancellation. | 3 | Backlog
PB-041 | As an admin, I want to monitor the app's compliance with GDPR and FERPA regulations so that I can ensure data protection. | Compliance | High | - Compliance reports are available in the admin dashboard. - Alerts are triggered for non-compliance issues. | 6 | Backlog
PB-042 | As a parent, I want to pay in installments so that I can manage my expenses over time. | Secure Payment | Medium | - Installment plans are available at checkout. - Installment terms and conditions are displayed clearly. | 8 | Backlog
PB-043 | As a parent, I want to be able to reorder previous purchases easily so that I can save time. | Parent Dashboard | Medium | - Reorder button is available in order history. - Previous orders are added to the cart with one click. | 3 | Backlog
PB-044 | As a parent, I want to chat with support agents for quick assistance so that I can resolve issues promptly. | In-App Chat Support | Medium | - Chat is available 24/7. - Users can view chat history and transcripts. | 5 | Backlog
PB-045 | As a supplier, I want to receive feedback from parents and schools so that I can improve my products. | Supplier Management | Medium | - Feedback form is available on product pages. - Suppliers can respond to feedback. | 3 | Backlog
PB-046 | As an admin, I want to export data for external analysis so that I can use advanced tools for insights. | Custom Reporting Tool | Low | - Data can be exported in CSV, Excel, and PDF formats. - Export options are available for all report types. | 4 | Backlog
PB-047 | As a parent, I want to receive notifications when new items are added to the store so that I can stay updated on available supplies. | Notifications & Alerts | Low | - Notifications are sent for new product additions. - Users can opt-in or out of these notifications. | 3 | Backlog
PB-048 | As an admin, I want to track the performance of promotional campaigns so that I can assess their effectiveness. | Reporting Dashboard | Medium | - Campaign performance metrics include reach, engagement, and conversions. | 5 | Backlog
PB-049 | As a parent, I want to use voice commands to search for supplies so that I can use the app hands-free. | Product Search & Filter | Medium | - Voice search is supported for all product categories. - Search results are displayed based on spoken keywords. | 8 | Backlog
PB-050 | As an admin, I want to track spending by department or class so that I can manage budgets effectively. | Reporting Dashboard | High | - Spending reports are available for each department or class. - Data can be filtered by date range and category. | 6 | Backlog
PB-051 | As a parent, I want to use a loyalty program so that I can earn rewards on my purchases. | Loyalty Programs | Low | - Points are awarded for each purchase. - Points can be redeemed for discounts or gifts. | 5 | Backlog
PB-052 | As an admin, I want to track the overall app performance so that I can identify areas for improvement. | Performance Monitoring | Medium | - Performance metrics include load times, error rates, and user satisfaction. | 6 | Backlog
PB-053 | As a parent, I want to use a simplified checkout process so that I can complete my purchases quickly. | Secure Payment | High | - One-click checkout option is available. - Payment and address details are auto-filled. | 5 | Backlog
PB-054 | As a supplier, I want to upload bulk product information so that I can save time in managing my listings. | Supplier Product Management | Medium | - Bulk upload supports CSV and Excel formats. - Products are updated in real-time. | 5 | Backlog
PB-055 | As an admin, I want to see data visualizations for sales trends so that I can make informed decisions. | Reporting Dashboard | Medium | - Data visualizations include graphs, pie charts, and bar charts. - Visualizations can be customized based on criteria. | 5 | Backlog
PB-056 | As a parent, I want to apply multiple filters to search results so that I can find the exact items I need. | Product Search & Filter | High | - Filters include category, price, ratings, and supplier. - Results are updated dynamically based on selected filters. | 5 | Backlog
PB-057 | As an admin, I want to see a summary of all active orders so that I can monitor fulfillment status. | Order Management | High | - Active orders are displayed with details like status and delivery date. - Summary is updated in real-time. | 5 | Backlog
PB-058 | As a parent, I want to view my child’s school supply requirements for the entire year so that I can plan ahead. | Parent Dashboard | Medium | - Annual supply list is displayed based on the child’s grade and subjects. - Supplies can be added to the cart. | 5 | Backlog
PB-059 | As an admin, I want to set up user training sessions so that new users understand how to use the app. | User Training & Onboarding | Medium | - Training sessions can be scheduled and managed from the admin dashboard. - Training materials are available for download. | 5 | Backlog
PB-060 | As a parent, I want to access order invoices so that I can keep a record of my expenses. | Order Management | Low | - Invoices are available for download in PDF format. - Invoices include order details and tax information. | 3 | Backlog
PB-061 | As an admin, I want to receive alerts for critical issues so that I can respond promptly. | Notifications & Alerts | High | - Alerts are sent for system downtime, payment failures, and data breaches. - Alerts are visible in the admin dashboard and sent via email. | 5 | Backlog
PB-062 | As a supplier, I want to see a summary of my pending orders so that I can manage my shipments efficiently. | Supplier Dashboard | Medium | - Summary includes order ID, status, and expected shipment date. - Orders can be filtered by priority and date. | 4 | Backlog
PB-063 | As a parent, I want to track my child’s order status so that I can know when supplies will arrive. | Order Tracking | Medium | - Order status is updated in real-time. - Estimated delivery date is displayed. | 5 | Backlog
PB-064 | As an admin, I want to review and approve or reject vendor applications so that I can maintain quality. | Supplier Management | Medium | - Vendor applications are displayed with necessary details. - Admins can approve, reject, or request more information. | 6 | Backlog
PB-065 | As a parent, I want to see recommendations for sustainable and eco-friendly supplies so that I can make environmentally friendly choices. | Supply Suggestions | Low | - Recommendations are marked with eco-friendly labels. - Users can filter suggestions by sustainability. | 4 | Backlog
PB-066 | As a supplier, I want to receive notifications for low inventory so that I can restock products in time. | Inventory Management | Medium | - Low inventory alerts are sent via email and dashboard notifications. - Suppliers can set custom alert thresholds. | 4 | Backlog
PB-067 | As an admin, I want to generate custom financial reports so that I can analyze spending and budget allocation. | Custom Reporting Tool | High | - Financial reports can be customized by date, department, and spending category. - Reports are exportable in PDF and Excel formats. | 6 | Backlog
PB-068 | As a parent, I want to see a summary of all my purchases so that I can manage my budget better. | Parent Dashboard | Medium | - Summary includes total spent, items purchased, and remaining budget. - Users can filter by month and category. | 5 | Backlog
PB-069 | As a supplier, I want to update my product listings easily so that I can keep my offerings current. | Supplier Product Management | Medium | - Products can be updated individually or in bulk. - Updates are reflected in real-time. | 4 | Backlog
PB-070 | As an admin, I want to receive a daily report on order processing so that I can monitor performance. | Reporting Dashboard | High | - Daily report includes number of orders processed, pending, and delayed. - Report is sent via email and available in the dashboard. | 4 | Backlog
PB-071 | As a parent, I want to compare prices between multiple suppliers so that I can find the best deals. | Product Comparison Tool | High | - Price comparison includes all available suppliers. - Users can filter by rating, delivery time, and price. | 5 | Backlog
PB-072 | As an admin, I want to ensure that the app is ADA-compliant so that it is accessible to all users. | Compliance | High | - ADA compliance is verified through automated tests and manual reviews. - Reports are generated for compliance status. | 6 | Backlog
PB-073 | As a parent, I want to access a FAQ section so that I can find answers to common questions. | User Support | Low | - FAQ is available in the help section. - Users can search by category and keyword. | 2 | Backlog
PB-074 | As an admin, I want to see a dashboard of user engagement so that I can track active users and retention. | Reporting Dashboard | High | - Dashboard includes daily active users, new registrations, and user retention rates. - Data can be filtered by time period. | 6 | Backlog
PB-075 | As a parent, I want to view the school supply list by grade level so that I can purchase all needed items. | Parent Dashboard | Medium | - Supply lists are available for each grade level. - Items can be added to cart directly from the list. | 4 | Backlog
PB-076 | As an admin, I want to receive performance feedback from users so that I can make improvements. | User Feedback | Medium | - Feedback forms are available in the app. - Admins can view and respond to feedback. | 3 | Backlog
PB-077 | As a supplier, I want to receive alerts when products are out of stock so that I can restock quickly. | Inventory Management | Medium | - Out-of-stock alerts are sent via email and dashboard notifications. - Suppliers can view and update stock levels. | 4 | Backlog
PB-078 | As an admin, I want to manage user roles and permissions so that access is controlled appropriately. | User Management | High | - User roles can be added, updated, or removed. - Permissions are configured for each role. | 5 | Backlog
PB-079 | As a parent, I want to access my order history so that I can review past purchases. | Parent Dashboard | Low | - Order history includes item details, order dates, and costs. - Orders can be filtered by date and status. | 3 | Backlog
PB-080 | As an admin, I want to set up scheduled maintenance alerts so that users are informed about downtime. | Notifications & Alerts | Medium | - Maintenance alerts are scheduled and displayed in the app and sent via email. - Alerts include start and end times for maintenance. | 3 | Backlog
PB-081 | As a supplier, I want to track my fulfillment performance so that I can ensure timely deliveries. | Supplier Dashboard | Medium | - Fulfillment performance includes delivery times and order accuracy. - Performance data is displayed in the supplier dashboard. | 5 | Backlog
PB-082 | As an admin, I want to manage app settings and configurations so that I can customize the app experience. | Admin Dashboard | Medium | - Settings include theme, user preferences, and notification options. - Changes are applied immediately. | 4 | Backlog
PB-083 | As a parent, I want to create a wishlist of supplies so that I can track items for future purchases. | Wishlist/Favorites | Medium | - Wishlist items can be added to cart or removed. - Users receive notifications for wishlist items on sale. | 3 | Backlog
PB-084 | As an admin, I want to view data on app usage so that I can understand user behavior. | Reporting Dashboard | Medium | - App usage data includes session duration, most accessed pages, and drop-off points. - Data is updated in real-time. | 5 | Backlog
PB-085 | As a parent, I want to pay with multiple payment methods so that I have flexibility in how I pay. | Secure Payment | Medium | - Users can split payments between credit card, PayPal, and gift cards. - Payment options are displayed at checkout. | 4 | Backlog
PB-086 | As a supplier, I want to update my company profile so that I can provide accurate information to users. | Supplier Management | Low | - Profile updates include contact info, business hours, and product categories. - Updates are reflected in real-time. | 3 | Backlog
PB-087 | As an admin, I want to generate user activity reports so that I can track engagement trends. | Reporting Dashboard | Medium | - Reports include user logins, feature usage, and feedback trends. - Data can be filtered by user role and time period. | 4 | Backlog
PB-088 | As a parent, I want to track my reward points so that I can redeem them for discounts. | Loyalty Programs | Low | - Reward points are displayed in the user dashboard. - Points can be redeemed at checkout. | 4 | Backlog
PB-089 | As an admin, I want to track app uptime and performance metrics so that I can ensure a stable user experience. | Performance Monitoring | Medium | - Metrics include server uptime, response times, and error rates. - Alerts are sent for performance issues. | 6 | Backlog
PB-090 | As a parent, I want to receive discounts for bulk orders so that I can save on large purchases. | Bulk Ordering System | Medium | - Discounts are applied automatically for eligible bulk orders. - Discount tiers are displayed at checkout. | 5 | Backlog
PB-091 | As an admin, I want to schedule user onboarding sessions so that new users can learn how to use the app. | User Training & Onboarding | Medium | - Sessions can be scheduled in the admin dashboard. - Users receive notifications and reminders for sessions. | 4 | Backlog
PB-092 | As a supplier, I want to offer special promotions to schools so that I can increase sales. | Supplier Promotions | Medium | - Special promotions can be created and targeted to specific schools. - Promotions are displayed in the admin dashboard and emails. | 5 | Backlog
PB-093 | As an admin, I want to track data on user demographics so that I can understand user segments better. | Reporting Dashboard | Medium | - Demographics data includes age, location, and user role. - Data can be exported in various formats. | 4 | Backlog
PB-094 | As a parent, I want to receive recommendations for school supplies based on my child’s grade level so that I can buy the right items. | Supply Suggestions | Medium | - Recommendations are personalized based on grade level. - Users can add recommended items directly to their cart. | 4 | Backlog
PB-095 | As an admin, I want to monitor API performance so that I can ensure smooth data integration. | Performance Monitoring | Medium | - API performance metrics include response times and error rates. - Alerts are sent for API performance issues. | 5 | Backlog
PB-096 | As a parent, I want to participate in surveys about the app so that I can provide feedback on features. | User Feedback | Low | - Surveys are available in the user dashboard. - Users receive notifications when new surveys are available. | 3 | Backlog
PB-097 | As a supplier, I want to access training materials on how to use the supplier dashboard so that I can manage my listings effectively. | User Training & Onboarding | Low | - Training materials include video tutorials and FAQs. - Materials are accessible in the supplier dashboard. | 3 | Backlog
PB-098 | As an admin, I want to manage refund requests so that I can handle financial disputes efficiently. | Secure Payment | Medium | - Refund requests can be submitted and tracked in the admin dashboard. - Users receive updates on refund status. | 5 | Backlog
PB-099 | As a parent, I want to view payment history for each child so that I can track expenses separately. | Parent Dashboard | Medium | - Payment history is separated by child’s name and grade. - Users can filter by date and category. | 4 | Backlog
PB-100 | As a supplier, I want to view analytics on my product listings so that I can optimize my offerings. | Supplier Dashboard | Medium | - Analytics include product views, conversions, and ratings. - Data can be filtered by date range and product category. | 4 | Backlog
PB-101 | As an admin, I want to track system usage during peak times so that I can optimize resources. | Performance Monitoring | Medium | - System usage metrics include concurrent users and load times. - Recommendations are provided for resource optimization. | 5 | Backlog
PB-102 | As a parent, I want to receive reminders about upcoming school supply sales so that I can plan my purchases. | Notifications & Alerts | Low | - Sale reminders are sent via email and app notifications. - Users can customize reminder preferences. | 3 | Backlog
PB-103 | As a supplier, I want to access a support chat for technical issues so that I can get assistance quickly. | User Support | Low | - Support chat is available in the supplier dashboard. - Users receive a response within 24 hours. | 3 | Backlog
PB-104 | As an admin, I want to track data on customer satisfaction so that I can improve user experience. | User Feedback | Medium | - Satisfaction data is collected via surveys and feedback forms. - Reports are generated for trends and issues. | 4 | Backlog
PB-105 | As a parent, I want to rate and review suppliers so that I can share my experiences with other users. | Supplier Ratings & Reviews | Medium | - Ratings and reviews are visible on supplier profiles. - Users can edit or delete their reviews. | 4 | Backlog
PB-107 | As a supplier, I want to view detailed sales analytics so that I can understand my product performance. | Supplier Dashboard | Medium | - Sales analytics include product sales trends, best-selling items, and revenue breakdown. - Data can be filtered by date range and category. | 6 | Backlog
PB-108 | As an admin, I want to send targeted promotions to specific user groups so that I can increase engagement. | Marketing & Promotions | Medium | - Promotions can be targeted based on user role, purchase history, and location. - Campaign results are tracked and reported. | 5 | Backlog
PB-109 | As a parent, I want to access a help center so that I can find assistance with using the app. | User Support | Low | - Help center includes FAQs, tutorials, and contact support options. - Users can search by keyword or browse by topic. | 4 | Backlog
PB-110 | As an admin, I want to manage app update notifications so that users are informed about new features and improvements. | Notifications & Alerts | Medium | - Update notifications are displayed in the app and sent via email. - Notifications include release notes and links to new features. | 4 | Backlog
PB-111 | As a supplier, I want to manage my product reviews so that I can respond to customer feedback. | Supplier Dashboard | Medium | - Suppliers can view, respond to, and report inappropriate reviews. - Review summaries are displayed in the product management section. | 3 | Backlog
PB-112 | As a parent, I want to save my preferred payment methods so that I can check out quickly. | Secure Payment | Medium | - Users can add, edit, and remove payment methods in their profile. - Preferred methods are selected by default at checkout. | 4 | Backlog
PB-113 | As an admin, I want to set system maintenance schedules so that users are aware of planned downtimes. | Notifications & Alerts | Low | - Maintenance schedules are displayed in the app and sent via email. - Users are notified at least 24 hours in advance. | 3 | Backlog
PB-114 | As a supplier, I want to view my inventory levels so that I can manage stock efficiently. | Inventory Management | High | - Inventory dashboard displays current stock levels, reorder alerts, and sales velocity. - Suppliers can set low-stock thresholds for alerts. | 5 | Backlog
PB-115 | As a parent, I want to share my wishlist with others so that they can contribute to my school supply purchases. | Wishlist/Favorites | Low | - Users can share their wishlist via email or social media. - Wishlist items can be added to cart by other users. | 3 | Backlog
PB-116 | As an admin, I want to monitor supplier performance so that I can identify areas for improvement. | Supplier Management | Medium | - Performance metrics include order fulfillment rate, delivery times, and customer ratings. - Data can be filtered by supplier and time period. | 6 | Backlog
PB-117 | As a parent, I want to receive order status updates so that I can know when my supplies will arrive. | Order Tracking | Medium | - Status updates include order confirmation, shipping, and delivery. - Users can opt to receive updates via SMS, email, or app notifications. | 4 | Backlog
PB-118 | As an admin, I want to track project progress so that I can ensure milestones are met. | Project Management | High | - Progress is displayed as a Gantt chart with task status updates. - Alerts are sent for delayed tasks. | 5 | Backlog
PB-119 | As a supplier, I want to receive alerts for product returns so that I can address issues promptly. | Inventory Management | Medium | - Return alerts include order ID, product details, and reason for return. - Suppliers can view return statistics and trends. | 4 | Backlog
PB-120 | As an admin, I want to monitor compliance with security protocols so that user data is protected. | Compliance | High | - Security compliance dashboard includes status of data encryption, user authentication, and access controls. - Alerts are sent for any compliance issues. | 6 | Backlog
PB-121 | As a parent, I want to view my loyalty points history so that I can see how I've earned points. | Loyalty Programs | Low | - Loyalty points history includes date, action, and points earned. - Users can filter by date and action type. | 3 | Backlog
PB-122 | As a supplier, I want to view my delivery performance so that I can improve my logistics. | Supplier Dashboard | Medium | - Delivery performance includes on-time delivery rate, average delivery time, and delayed shipments. - Data can be filtered by time period and product category. | 4 | Backlog
PB-123 | As an admin, I want to view user satisfaction metrics so that I can improve app experience. | User Feedback | High | - Metrics include average ratings, NPS score, and satisfaction trends. - Feedback is categorized by app feature and user type. | 5 | Backlog
PB-124 | As a parent, I want to access a customer support chat so that I can get help with my orders. | User Support | Medium | - Chat support is available 24/7. - Users can view chat history and escalate issues. | 4 | Backlog
PB-125 | As a supplier, I want to update my shipping policies so that customers have accurate information. | Supplier Management | Low | - Shipping policies include delivery times, costs, and return conditions. - Changes are updated in real-time. | 3 | Backlog
PB-126 | As an admin, I want to track system performance during peak usage times so that I can ensure stability. | Performance Monitoring | Medium | - Performance metrics include response times, error rates, and server load. - Alerts are sent for performance issues. | 6 | Backlog
PB-127 | As a parent, I want to receive reminders for upcoming school events so that I can prepare in advance. | Notifications & Alerts | Low | - Event reminders are sent via email and app notifications. - Users can customize reminder settings. | 3 | Backlog
PB-128 | As a supplier, I want to view my overall sales performance so that I can plan for future orders. | Supplier Dashboard | Medium | - Sales performance includes total sales, best-selling products, and average order value. - Data is updated in real-time. | 4 | Backlog
PB-129 | As an admin, I want to schedule automatic backups so that data is not lost. | Data Management | High | - Automatic backups are scheduled daily, weekly, and monthly. - Backup status is displayed in the admin dashboard. | 5 | Backlog
PB-130 | As a parent, I want to see recommendations for best-selling supplies so that I can make informed purchases. | Supply Suggestions | Medium | - Recommendations are based on best-selling products in each category. - Users can view ratings and reviews. | 4 | Backlog
PB-131 | As a supplier, I want to set minimum order quantities so that I can manage my stock effectively. | Supplier Product Management | Low | - Minimum order quantities can be set per product. - Alerts are sent when orders do not meet the minimum. | 3 | Backlog
PB-132 | As an admin, I want to monitor app response times so that I can ensure a smooth user experience. | Performance Monitoring | Medium | - Response times are tracked by page and feature. - Alerts are sent for slow response times. | 5 | Backlog
PB-133 | As a parent, I want to access tips for purchasing school supplies so that I can make informed choices. | User Support | Low | - Tips are available in the help section and include buying guides and product reviews. - Users can search by keyword and category. | 2 | Backlog
PB-134 | As a supplier, I want to set up automated responses to common questions so that I can improve customer service. | Supplier Dashboard | Medium | - Automated responses can be set for common queries like shipping times and returns. - Responses are displayed in the chat and help sections. | 4 | Backlog
PB-135 | As an admin, I want to manage user roles and permissions so that access is controlled appropriately. | User Management | High | - User roles can be added, updated, or removed. - Permissions are configured for each role. | 5 | Backlog
PB-136 | As a parent, I want to view detailed product reviews so that I can make informed purchasing decisions. | Product Comparison Tool | Medium | - Reviews are displayed with ratings, pros/cons, and verified purchase badges. - Users can filter reviews by rating and date. | 4 | Backlog
PB-137 | As a supplier, I want to see my order fulfillment statistics so that I can improve my performance. | Supplier Dashboard | Medium | - Order fulfillment statistics include average fulfillment time, on-time delivery rate, and order accuracy. - Data is updated in real-time and displayed in the supplier dashboard. | 5 | Backlog
PB-138 | As an admin, I want to manage app security settings so that I can ensure data protection. | Compliance | High | - Security settings include user authentication, password policies, and access control. - Admins can configure and update settings in the security dashboard. | 6 | Backlog
PB-139 | As a parent, I want to receive personalized supply suggestions based on my child's grade and classes so that I can purchase relevant items. | Supply Suggestions | Medium | - Personalized suggestions are based on school grade, subjects, and curriculum. - Users can view and add suggested items to their cart. | 4 | Backlog
PB-140 | As a supplier, I want to receive weekly performance reports so that I can review my sales and operations. | Supplier Dashboard | Medium | - Weekly reports include sales data, product performance, and customer feedback. - Reports are sent via email and available in the dashboard. | 4 | Backlog
PB-141 | As an admin, I want to create user segments for targeted marketing campaigns so that I can increase engagement. | Marketing & Promotions | High | - User segments can be created based on role, purchase history, and location. - Campaign results are tracked and reported. | 5 | Backlog
PB-142 | As a parent, I want to see a history of my communication with customer support so that I can reference past interactions. | User Support | Medium | - Communication history includes chat transcripts, email exchanges, and support tickets. - Users can search and filter by date and issue. | 4 | Backlog
PB-143 | As an admin, I want to manage app themes and colors so that I can customize the app appearance. | Admin Dashboard | Low | - Admins can choose from pre-set themes or customize colors. - Changes are applied in real-time. | 3 | Backlog
PB-144 | As a supplier, I want to set custom shipping rates so that I can offer competitive pricing. | Supplier Management | Medium | - Shipping rates can be set based on weight, destination, and delivery speed. - Changes are updated in real-time. | 4 | Backlog
PB-145 | As a parent, I want to receive recommendations for popular supplies so that I can stay informed on trends. | Supply Suggestions | Low | - Recommendations are based on popular items within the community. - Users can view trending products by category. | 3 | Backlog
PB-146 | As an admin, I want to monitor system load during high traffic periods so that I can ensure stability. | Performance Monitoring | High | - System load is tracked and displayed in the admin dashboard. - Alerts are sent for high CPU, memory, and bandwidth usage. | 6 | Backlog
PB-147 | As a supplier, I want to access training materials on the platform so that I can maximize my use of the app. | Supplier Dashboard | Low | - Training materials include video tutorials, FAQs, and documentation. - Users can track their progress and receive completion badges. | 3 | Backlog
PB-148 | As an admin, I want to view and export audit logs so that I can review app activity and security. | Compliance | High | - Audit logs include user logins, data changes, and access attempts. - Logs can be exported in CSV and PDF formats. | 5 | Backlog
PB-149 | As a parent, I want to track my order returns so that I can know the status of my refunds. | Order Tracking | Medium | - Return tracking includes refund status, expected completion date, and return instructions. - Users can view and filter by return date and status. | 4 | Backlog
PB-150 | As a supplier, I want to receive alerts for potential stock shortages so that I can plan ahead. | Inventory Management | Medium | - Alerts include stock levels, estimated days until depletion, and recommended reorder quantities. - Alerts are sent via email and dashboard notifications. | 4 | Backlog
PB-151 | As an admin, I want to manage API keys and access so that I can control third-party integrations. | Data Management | High | - API keys can be created, updated, and revoked. - Access logs are displayed for each key. | 5 | Backlog
PB-152 | As a parent, I want to view recommendations for back-to-school supplies so that I can prepare for the new school year. | Supply Suggestions | Medium | - Recommendations are tailored based on grade level and previous purchases. - Users can add items directly to their cart. | 4 | Backlog
PB-153 | As a supplier, I want to view customer feedback trends so that I can improve my products. | Supplier Dashboard | Medium | - Feedback trends include average ratings, common complaints, and product-specific feedback. - Data is displayed in a graphical format with filters for date and product. | 5 | Backlog
PB-154 | As an admin, I want to manage multi-factor authentication settings so that I can ensure user security. | Compliance | High | - MFA settings include activation for specific roles, timeout durations, and recovery options. - Admins can enable or disable MFA per user role. | 6 | Backlog
PB-155 | As a parent, I want to see recommendations for budget-friendly supplies so that I can manage my expenses. | Supply Suggestions | Medium | - Recommendations are based on lowest price and highest ratings. - Users can view discounts and promotions for budget-friendly items. | 4 | Backlog
PB-156 | As a supplier, I want to set shipping time estimates so that customers know when to expect deliveries. | Supplier Product Management | Medium | - Shipping time estimates can be set for each product. - Estimates are displayed on the product page and at checkout. | 4 | Backlog
PB-157 | As an admin, I want to view app crash reports so that I can address stability issues. | Performance Monitoring | High | - Crash reports include error messages, affected users, and impacted features. - Reports are updated in real-time and displayed in the admin dashboard. | 6 | Backlog
PB-158 | As a parent, I want to receive reminders for supply reordering so that I never run out of essential items. | Notifications & Alerts | Medium | - Reorder reminders are based on past purchase history and expected usage. - Users can set their preferred reminder intervals. | 4 | Backlog
PB-159 | As a supplier, I want to view analytics on seasonal trends so that I can plan my inventory. | Supplier Dashboard | Medium | - Seasonal trends include sales data by month, top-selling products, and category demand. - Data is displayed in a graphical format with comparison to previous years. | 5 | Backlog
PB-160 | As an admin, I want to track user engagement so that I can identify high-performing features. | Reporting Dashboard | High | - Engagement metrics include feature usage, session duration, and drop-off rates. - Data can be filtered by user role and time period. | 5 | Backlog

## Epics
User Registration & Authentication
PB-001: User Registration System
PB-002: Login Screen UI
PB-004: Password Recovery System
PB-138: Manage App Security Settings
Parent Dashboard & User Experience
PB-003: Parent Dashboard Overview
PB-006: Order History Feature
PB-139: Personalized Supply Suggestions
PB-142: Communication History Access
PB-152: Back-to-School Supply Recommendations
PB-155: Budget-Friendly Supply Recommendations
Admin Dashboard & Management
PB-010: Admin Dashboard Overview
PB-020: User Management System
PB-040: Manage School Inventory
PB-048: Compliance Management
PB-141: Targeted Marketing Campaigns
PB-151: Manage API Keys and Access
PB-160: User Engagement Tracking
Supplier Dashboard & Management
PB-030: Supplier Product Management
PB-031: Supplier Dashboard Overview
PB-053: Supplier Feedback System
PB-065: Performance Evaluation
PB-137: Order Fulfillment Statistics
PB-140: Weekly Performance Reports
PB-144: Custom Shipping Rates
PB-150: Stock Shortage Alerts
PB-156: Shipping Time Estimates
PB-159: Seasonal Trend Analytics
Order Management & Tracking
PB-005: Shopping Cart System
PB-011: Order Tracking System
PB-018: Bulk Ordering System
PB-022: Order Grouping Feature
PB-039: Group Purchasing Options
PB-149: Order Returns Tracking
Notifications & Alerts
PB-013: Notifications System
PB-016: Stock Alert Notifications
PB-018: Low Stock Alerts
PB-033: Delivery Status Notifications
PB-150: Stock Shortage Alerts
PB-158: Supply Reordering Reminders
Product Search & Comparison
PB-021: Product Search Functionality
PB-036: Product Comparison Tool
PB-145: Trending Product Recommendations
PB-153: Customer Feedback Trends
Reporting & Analytics
PB-026: Reporting Dashboard
PB-028: Custom Reporting Tool
PB-046: Supplier Reports
PB-053: Supplier Feedback Reports
PB-140: Supplier Performance Reports
PB-157: App Crash Reports
PB-160: User Engagement Reports
AI & Prediction Systems
PB-007: AI-Powered Supply Prediction
PB-024: AI Model for Inventory Management
PB-029: Supply Prediction Tool
PB-062: AI-Powered Forecasting
Compliance & Security
PB-006: FERPA and GDPR Compliance
PB-038: Data Encryption
PB-048: Compliance Monitoring
PB-154: Multi-Factor Authentication Settings
PB-151: Manage API Keys and Access
PB-157: App Crash Reports
User Experience & Support
PB-015: Multi-Language Support
PB-017: In-App Chat Support
PB-064: Voice-Assisted Search
PB-147: Supplier Training Materials
PB-158: Reordering Reminders
Performance Monitoring & Optimization
PB-019: Performance Optimization
PB-046: Server Load Monitoring
PB-061: System Load Management
PB-146: High Traffic Monitoring
PB-157: Crash Report Monitoring
Payment & Financial Management
PB-008: Payment Gateway Integration
PB-034: Transaction History
PB-070: Discounts and Promotions Management
Training & Documentation
PB-032: Supplier Documentation
PB-055: User Onboarding Materials
PB-147: Supplier Training Materials
PB-054: User Training Documentation