## Sheet1
Sprint | Sprint Goal | PBI ID | User Story/Feature | Tasks | Assignee | Status | Estimated Effort (Story Points) | Notes
Sprint 1 | Implement User Registration | PB-001 | Implement User Registration | Design UI, Backend Integration | Dev Team A | In Progress | 8 | Priority Feature
|  | PB-002 | Build Admin Inventory Management | Create UI, Build DB, Implement Alerts | Dev Team B | Not Started | 13 | Complex
|  | PB-003 | Parent Dashboard | UI Design, Backend Integration | Dev Team C | Not Started | 8 | -
|  | PB-004 | Payment Integration | Payment Gateway, Data Encryption | Dev Team A | Not Started | 5 | -
|  | PB-005 | Order Tracking System | UI Design, Build Tracking Logic | Dev Team B | Not Started | 8 | -
|  | PB-006 | Bulk Ordering System | UI Design, Backend Integration | Dev Team C | Not Started | 8 | -
Sprint 2 | Role-Based Access Control | PB-007 | Role-Based Access Control | Define Roles, Build System, Test | Dev Team A | Not Started | 8 | Priority
|  | PB-008 | In-App Chat Support | UI Design, Build Backend, Integration | Dev Team B | Not Started | 5 | -
|  | PB-009 | AI-Powered Supply Prediction | Data Collection, Model Training | AI Team | Not Started | 13 | AI Integration Required
|  | PB-010 | Custom Reporting Tool | Report UI, Data Integration | Dev Team C | Not Started | 8 | -
Sprint 3 | Product Comparison Tool | PB-011 | Product Comparison Tool | UI Design, Build Engine | Dev Team A | Not Started | 5 | -
|  | PB-012 | Notifications and Alerts | UI Design, Implement Alerts | Dev Team B | Not Started | 5 | -
|  | PB-013 | Product Wishlist/Favorites | UI Design, Backend Integration | Dev Team C | Not Started | 8 | -
|  | PB-014 | Recurring Orders Setup | UI Design, Backend Integration | Dev Team A | Not Started | 5 | -
Sprint 4 | Multi-Language Support | PB-015 | Multi-Language Support | UI, Localization, Integration | Dev Team B | Not Started | 8 | -
|  | PB-016 | Voice-Assisted Search | UI Design, Build Engine | Dev Team A | Not Started | 8 | Voice Recognition
|  | PB-017 | Admin Multi-Location Dashboard | UI Design, Data Tracking | Dev Team C | Not Started | 5 | -
Sprint 5 | Secure API Integration | PB-018 | Secure API Integration | Design Protocols, Implement APIs | Dev Team A | Not Started | 8 | Security Critical
|  | PB-019 | Mobile App Responsiveness | Responsive UI Design, Testing | Dev Team B | Not Started | 8 | Mobile Optimization
|  | PB-020 | ADA Compliance for Accessibility | Audit, Implement Compliance Features | Accessibility Team | Not Started | 13 | Accessibility Standards
Sprint 6 | Optimize and secure API integrations | PB-021 | Implement Payment Gateway API | Design API, Implement, Test | Dev Team A | Not Started | 8 | Security required
|  | PB-022 | Implement Backup and Recovery | Design backup strategy, Implement | IT Team | Not Started | 5 | -
|  | PB-023 | Implement Load Balancing | Design and setup load balancing | IT Team | Not Started | 8 | High traffic handling
|  | PB-024 | Implement Multi-Factor Auth | Design MFA UI, Backend | Dev Team B | Not Started | 5 | Security feature
|  | PB-025 | Implement Secure API Endpoints | Design endpoints, Implement security | Dev Team A | Not Started | 8 | Security critical
|  | PB-026 | Implement Vendor Feedback System | UI Design, Implement backend | Dev Team C | Not Started | 5 | -
Sprint 7 | Finalize key reporting features | PB-027 | Implement Supplier Evaluation Tool | Design UI, Build evaluation metrics | Dev Team A | Not Started | 8 | Supplier performance
|  | PB-028 | Implement Custom Reporting Tool | UI Design, Backend | Dev Team B | Not Started | 8 | -
|  | PB-029 | Implement ADA Compliance | Design, Implement compliance features | Accessibility Team | Not Started | 5 | ADA standards
|  | PB-030 | Implement Performance Optimization | Analyze, Implement optimization | IT Team | Not Started | 8 | System optimization
|  | PB-031 | Implement Mobile Responsiveness | Design responsive layout, Test | Dev Team A | Not Started | 8 | Mobile optimization
|  | PB-032 | Implement AI Supply Prediction Tool | Data Collection, Model training | AI Team | Not Started | 8 | AI integration required
Sprint 8 | Enhance User Experience | PB-033 | Implement Product Wishlist | Design UI, Backend | Dev Team B | Not Started | 8 | UX enhancement
|  | PB-034 | Implement Group Purchasing Tool | Design UI, Backend | Dev Team A | Not Started | 5 | Bulk orders
|  | PB-035 | Implement AI-Powered Recommendations | Data Collection, AI model training | AI Team | Not Started | 8 | AI-driven recommendations
|  | PB-036 | Implement Loyalty Program | UI Design, Backend | Dev Team C | Not Started | 5 | User retention
|  | PB-037 | Implement Custom Report Generation | Design, Build report engine | Dev Team A | Not Started | 8 | Reporting tools
|  | PB-038 | Implement Recurring Orders System | Design UI, Build backend | Dev Team B | Not Started | 8 | Repeat orders
Sprint 9 | Finalize and Test Core Features | PB-039 | Implement Secure Checkout | Design checkout UI, Build backend | Dev Team A | Not Started | 8 | Secure transactions
|  | PB-040 | Implement Vendor Rating System | UI Design, Backend integration | Dev Team B | Not Started | 8 | Vendor management
|  | PB-041 | Implement Payment Gateway API | Design API, Backend integration | Dev Team A | Not Started | 5 | Payment systems
|  | PB-042 | Implement Voice-Assisted Search | Design UI, Build backend | Dev Team C | Not Started | 5 | Voice recognition
|  | PB-043 | Implement Data Encryption | Encrypt data at rest and in transit | Security Team | Not Started | 8 | Security feature
|  | PB-044 | Implement Cloud Auto-Scaling | Set up cloud infrastructure, Auto-scaling rules | IT Team | Not Started | 8 | Cloud optimization
Sprint 10 | Final Testing and UAT | PB-045 | Perform Final System Testing | Prepare test cases, Execute tests | QA Team | Not Started | 8 | System-wide testing
|  | PB-046 | Conduct User Acceptance Testing | Prepare UAT scenarios, Execute tests | QA & Users | Not Started | 8 | User feedback
|  | PB-047 | Perform Security Audits | Prepare security tests, Execute audits | Security Team | Not Started | 8 | Security compliance
|  | PB-048 | Finalize Documentation | Prepare all user guides, technical docs | Documentation Team | Not Started | 5 | Documentation review
|  | PB-049 | Perform Load Testing | Prepare scenarios, Execute load tests | QA & IT Teams | Not Started | 5 | Performance testing
|  | PB-050 | Final Product Handover | Prepare handover docs, Handover to client | Project Manager | Not Started | 5 | Project completion
Sprint 11 | Post-Deployment Support | PB-051 | Implement Support Ticket System | Design UI, Backend | Dev Team A | Not Started | 8 | Support management
|  | PB-052 | Prepare Knowledge Base | Prepare articles, Upload | Documentation Team | Not Started | 5 | User support
|  | PB-053 | Monitor System Performance | Set up monitoring tools, Monitor | IT Team | Not Started | 5 | Performance monitoring
|  | PB-054 | Address Post-Launch Bugs | Identify, Fix bugs | Dev Team B | Not Started | 8 | Issue resolution
|  | PB-055 | Collect User Feedback | Prepare surveys, Collect feedback | UX Team | Not Started | 5 | User experience
|  | PB-056 | Conduct Post-Mortem Review | Prepare report, Conduct review | Project Manager | Not Started | 5 | Lessons learned