## Sheet1
Sprint | Day | Planned Work (Story Points) | Completed Work (Story Points) | Cumulative Work Completed (Story Points) | Remaining Work (Story Points) | Target Line | Notes
Sprint 1 | Day 1 | 50 | 0 | 0 | 50 | 7.14 | Sprint planning
| Day 2 | 50 | 5 | 5 | 45 | 14.28 | Initial tasks completed
| Day 3 | 50 | 5 | 10 | 40 | 21.42 | Steady progress
| Day 4 | 50 | 10 | 20 | 30 | 28.56 | Ahead of schedule
| Day 5 | 50 | 10 | 30 | 20 | 35.7 | Good progress
| Day 6 | 50 | 10 | 40 | 10 | 42.84 | Minor delays
| Day 7 | 50 | 10 | 50 | 0 | 50 | Sprint completed
Sprint 2 | Day 1 | 60 | 0 | 0 | 60 | 8.57 | Sprint planning
| Day 2 | 60 | 5 | 5 | 55 | 17.14 | Initial progress
| Day 3 | 60 | 10 | 15 | 45 | 25.71 | Steady progress
| Day 4 | 60 | 10 | 25 | 35 | 34.28 | On track
| Day 5 | 60 | 10 | 35 | 25 | 42.85 | Slight delays
| Day 6 | 60 | 10 | 45 | 15 | 51.42 | Catching up
| Day 7 | 60 | 15 | 60 | 0 | 60 | Sprint completed
Sprint 3 | Day 1 | 55 | 0 | 0 | 55 | 7.86 | Sprint planning
| Day 2 | 55 | 5 | 5 | 50 | 15.72 | Initial tasks completed
| Day 3 | 55 | 10 | 15 | 40 | 23.58 | Good progress
| Day 4 | 55 | 10 | 25 | 30 | 31.44 | On track
| Day 5 | 55 | 10 | 35 | 20 | 39.3 | Minor delays
| Day 6 | 55 | 10 | 45 | 10 | 47.16 | Final push
| Day 7 | 55 | 10 | 55 | 0 | 55 | Sprint completed
Sprint 4 | Day 1 | 70 | 0 | 0 | 70 | 10 | Sprint planning
| Day 2 | 70 | 5 | 5 | 65 | 20 | Initial work completed
| Day 3 | 70 | 10 | 15 | 55 | 30 | Steady progress
| Day 4 | 70 | 15 | 30 | 40 | 40 | Ahead of schedule
| Day 5 | 70 | 15 | 45 | 25 | 50 | On track
| Day 6 | 70 | 15 | 60 | 10 | 60 | Catching up
| Day 7 | 70 | 10 | 70 | 0 | 70 | Sprint completed
Sprint 5 | Day 1 | 65 | 0 | 0 | 65 | 9.29 | Sprint planning
| Day 2 | 65 | 5 | 5 | 60 | 18.58 | Initial tasks completed
| Day 3 | 65 | 10 | 15 | 50 | 27.87 | Good progress
| Day 4 | 65 | 10 | 25 | 40 | 37.16 | On track
| Day 5 | 65 | 10 | 35 | 30 | 46.45 | Minor delays
| Day 6 | 65 | 15 | 50 | 15 | 55.74 | Final push
| Day 7 | 65 | 15 | 65 | 0 | 65 | Sprint completed
Sprint 6 | Day 1 | 75 | 0 | 0 | 75 | 10.71 | Sprint planning
| Day 2 | 75 | 5 | 5 | 70 | 21.42 | Initial progress
| Day 3 | 75 | 10 | 15 | 60 | 32.13 | Moving along
| Day 4 | 75 | 15 | 30 | 45 | 42.84 | On track
| Day 5 | 75 | 15 | 45 | 30 | 53.55 | Slight delays
| Day 6 | 75 | 15 | 60 | 15 | 64.26 | Final push
| Day 7 | 75 | 15 | 75 | 0 | 75 | Sprint completed