## Feed
Metric | Description | Formula/Calculation | Purpose | Frequency | Responsibility | Target Value
Velocity | Amount of work completed in a sprint measured in story points or tasks. | Sum of Story Points Completed per Sprint | To measure team's work capacity and forecast future sprints. | End of Each Sprint | Scrum Master/Team | Varies per team capacity
Sprint Burndown | A chart that shows the amount of work remaining in the sprint. | Work Remaining (Story Points) | To track sprint progress and identify issues early. | Daily During Sprint | Scrum Master | Target: 0 Remaining Points
Burnup Chart | A chart that shows the work completed over time in the sprint. | Cumulative Work Completed (Story Points) | To show progress toward the sprint goal. | Daily During Sprint | Scrum Master | 100% Completion
Cycle Time | The time taken to complete a user story or task from start to finish. | Completion Date - Start Date | To evaluate process efficiency and identify bottlenecks. | Continuous | Scrum Master/Team | Varies by Task Complexity
Lead Time | The time taken from the moment a request is made until it is delivered. | Delivery Date - Request Date | To measure overall process efficiency. | Continuous | Product Owner/Team | Shorter Lead Time
Work In Progress (WIP) | Number of user stories or tasks that are currently being worked on. | Count of Active Tasks | To monitor work capacity and limit overloading. | Daily | Scrum Master | Maintain WIP Limit
Cumulative Flow Diagram | A chart showing the status of work items in different stages (e.g., To Do, In Progress, Done) over time. | Visual Representation | To identify process stability and bottlenecks. | Weekly | Scrum Master/Team | Consistent Flow
Defect Density | Number of defects identified per user story or feature. | Total Defects / Total User Stories | To assess product quality and reduce defects. | Per Release | QA Team | Below Industry Average
Defect Leakage | Percentage of defects found after release. | (Defects Found Post-Release / Total Defects) * 100 | To evaluate testing effectiveness. | Per Release | QA Team | Below 5%
Escaped Defects | Number of defects that were not identified during the sprint and were found later. | Count of Escaped Defects | To measure the quality of sprint deliverables. | Per Sprint | QA Team/Scrum Master | 0 Escaped Defects
Team Happiness | Measurement of the team's morale and satisfaction. | Survey Scores | To monitor team well-being and address issues proactively. | Sprint Retrospective | Scrum Master | Above 8/10
Sprint Goal Success Rate | Percentage of sprint goals achieved. | (Sprint Goals Achieved / Total Sprint Goals) * 100 | To measure the team's ability to meet commitments. | End of Each Sprint | Scrum Master | 100% Goal Achievement
Release Burnup | Tracks progress toward completing the work planned for a release. | Cumulative Work Completed / Total Work Planned | To visualize progress toward release goals. | Weekly | Scrum Master/Team | 100% Release Completion
Blocked Time | Amount of time a user story or task is blocked and cannot progress. | Cumulative Time Blocked | To identify blockers and improve flow efficiency. | Weekly | Scrum Master | 0 Blocked Time
Technical Debt | Measure of the effort required to fix code quality issues, such as bugs and refactoring. | Count of Technical Debt Items | To track code quality and prioritize technical debt. | Per Release | Development Team | Below Acceptable Level
Code Coverage | Percentage of code covered by automated tests. | (Covered Lines / Total Lines) * 100 | To measure test coverage and identify gaps. | Per Sprint/Release | QA Team/Development Team | Above 80%
Customer Satisfaction (CSAT) | Measures end-user satisfaction with the product delivered. | Survey Scores | To ensure the product meets customer needs. | Per Release | Product Owner | Above 8/10
Product Backlog Health | Measure of the readiness of the product backlog items for upcoming sprints. | Count of Groomed Items | To ensure the team has sufficient and well-defined work. | Weekly | Product Owner | 1-2 Sprints Worth of Work
Deployment Frequency | How often the team deploys code to production. | Count of Deployments per Time Period | To assess the agility and delivery speed of the team. | Weekly/Monthly | DevOps Team | High Frequency
Mean Time to Recovery (MTTR) | Average time to recover from a production failure. | Total Downtime / Number of Incidents | To improve system reliability and minimize downtime. | Per Incident | DevOps Team | Below Industry Average
Sprint Carryover Rate | Percentage of work carried over to the next sprint. | (Story Points Carried Over / Total Story Points) * 100 | To monitor planning accuracy and team capacity. | End of Each Sprint | Scrum Master | Below 10%

## Sprint Carryover Rate
Sprint Number | Start Date | End Date | Total Planned Story Points | Completed Story Points | Carried Over Story Points | Carryover Rate (%) | Comments
Sprint 1 | 2024-01-04 | 14/04/2024 | 50 | 40 | 10 | 20% | Initial sprint, underestimation of complexity
Sprint 2 | 15/04/2024 | 28/04/2024 | 60 | 55 | 5 | 8% | Minor carryover due to a critical bug fix
Sprint 3 | 29/04/2024 | 2024-12-05 | 55 | 45 | 10 | 18% | Issues with payment gateway integration
Sprint 4 | 13/05/2024 | 26/05/2024 | 65 | 50 | 15 | 23% | High-priority bugs caused task delays
Sprint 5 | 27/05/2024 | 2024-09-06 | 70 | 60 | 10 | 14% | Better estimation but some tasks still pending
Sprint 6 | 2024-10-06 | 23/06/2024 | 60 | 48 | 12 | 20% | Delays due to external dependencies
Sprint 7 | 24/06/2024 | 2024-07-07 | 55 | 50 | 5 | 9% | Focused on finishing carried-over tasks
Sprint 8 | 2024-08-07 | 21/07/2024 | 65 | 55 | 10 | 15% | New features took longer than expected
Sprint 9 | 22/07/2024 | 2024-04-08 | 70 | 65 | 5 | 7% | Improved planning and execution
Sprint 10 | 2024-05-08 | 18/08/2024 | 75 | 70 | 5 | 7% | Only minor carryover, mostly completed sprint

## Mean Time to Recovery
Incident ID | Incident Date | Affected Module | Incident Description | Start Time | End Time | Recovery Time (Hours) | Severity (Low/Medium/High) | Root Cause | Resolution Summary
INC-001 | 2024-01-04 | Payment Gateway | Payment gateway not processing orders | 10:00 | 11:30 | 1.5 | High | API credential issue | Updated API credentials
INC-002 | 2024-05-04 | User Interface | UI freezing on product catalog page | 14:00 | 15:00 | 1 | Medium | JavaScript memory leak | Refactored JS code
INC-003 | 2024-10-04 | Notifications | Delayed push notifications | 9:00 | 12:00 | 3 | Medium | Server overload | Increased server capacity
INC-004 | 15/04/2024 | Database | Slow database queries affecting app performance | 8:30 | 10:00 | 1.5 | High | Missing indexes | Added required indexes
INC-005 | 18/04/2024 | Authentication | Users unable to log in | 11:00 | 12:15 | 1.25 | High | Authentication service crash | Restarted service and applied hotfix
INC-006 | 20/04/2024 | Search Functionality | Search returning incomplete results | 15:00 | 17:00 | 2 | Medium | Indexing issue | Re-indexed the database
INC-007 | 22/04/2024 | Mobile App | Mobile app crashing on launch | 9:00 | 10:30 | 1.5 | High | SDK compatibility issue | Updated SDK version
INC-008 | 25/04/2024 | Teacher Dashboard | Report generation timing out | 13:00 | 14:45 | 1.75 | Medium | Query optimization required | Refactored query logic
INC-009 | 28/04/2024 | Notifications | Email notifications not sent | 16:00 | 18:30 | 2.5 | High | SMTP server misconfiguration | Corrected SMTP settings
INC-010 | 30/04/2024 | Shopping Cart | Items disappearing from cart | 7:30 | 8:30 | 1 | High | Session timeout issue | Fixed session handling logic

## Deployment Frequency
Deployment ID | Environment | Deployment Date | Version | Features/Changes Deployed | Deployment Type (Major/Minor/Patch) | Downtime (Hours) | Deployment Status (Success/Failure) | Comments
DEP-001 | Production | 2024-01-04 | v1.0.0 | Initial release of the School Supplies App | Major | 1 | Success | Initial launch
DEP-002 | Staging | 2024-05-04 | v1.0.1 | UI fixes, shopping cart enhancements | Patch | 0 | Success | Prepared for production release
DEP-003 | Production | 2024-07-04 | v1.0.1 | UI fixes, shopping cart enhancements | Patch | 0.5 | Success | Smooth deployment
DEP-004 | Development | 2024-10-04 | v1.1.0-beta | Payment gateway integration, teacher dashboard updates | Minor | 0 | Success | Testing new features
DEP-005 | Production | 15/04/2024 | v1.1.0 | Payment gateway integration, teacher dashboard updates | Minor | 0.5 | Success | Stable release after testing
DEP-006 | Staging | 20/04/2024 | v1.1.1 | Bug fixes, performance improvements | Patch | 0 | Success | Pre-release for testing
DEP-007 | Production | 22/04/2024 | v1.1.1 | Bug fixes, performance improvements | Patch | 0 | Success | No issues reported
DEP-008 | Development | 25/04/2024 | v1.2.0-beta | New notification system, enhanced search functionality | Minor | 0 | Success | Beta testing new features
DEP-009 | Staging | 28/04/2024 | v1.2.0 | New notification system, enhanced search functionality | Minor | 0 | Success | Ready for production
DEP-010 | Production | 30/04/2024 | v1.2.0 | New notification system, enhanced search functionality | Minor | 0.5 | Success | Deployed with minimal downtime
DEP-011 | Development | 2024-05-05 | v1.2.1-beta | Content management updates, UI tweaks | Patch | 0 | Success | Testing small updates
DEP-012 | Production | 2024-10-05 | v1.2.1 | Content management updates, UI tweaks | Patch | 0 | Success | No issues reported

## Product Backlog Health
Backlog ID | User Story/Task | Priority (Low/Medium/High) | Status | Story Points | Estimated Effort (Hours) | Ready for Sprint (Yes/No) | Comments
PBL-001 | Implement Shopping Cart Feature | High | To Do | 8 | 16 | Yes | Critical for MVP launch
PBL-002 | Create Teacher Dashboard Reports | Medium | In Progress | 5 | 12 | Yes | Key reports in development
PBL-003 | Integrate Payment Gateway | High | To Do | 8 | 20 | No | Waiting for API credentials
PBL-004 | Optimize Search Functionality | Medium | To Do | 3 | 8 | Yes | Enhancement for faster search
PBL-005 | Design Product Catalog UI | High | In Progress | 5 | 10 | Yes | UI/UX design in final stages
PBL-006 | Implement User Authentication | High | Completed | 8 | 15 | Yes | Implemented with new security features
PBL-007 | Set Up Notifications for Orders | Medium | To Do | 5 | 12 | No | Needs dependencies on messaging system
PBL-008 | Add Filters to Product Catalog | Medium | In Progress | 4 | 8 | Yes | Filter options under development
PBL-009 | Mobile App Feature - Teacher Resources | Low | To Do | 3 | 6 | No | Scheduled for future release
PBL-010 | Improve Error Handling for API | High | To Do | 6 | 10 | Yes | Important for robust system
PBL-011 | Create Admin Panel | High | To Do | 10 | 20 | No | Complex functionality, needs more refinement
PBL-012 | Conduct Usability Testing | Medium | To Do | 4 | 8 | Yes | Needed before final release

## Customer Satisfaction
Survey ID | Customer ID | Date | Feature/Module | Satisfaction Rating (1-5) | Feedback Comments | Issue Reported (Yes/No) | Action Taken
CSAT-001 | CUST-1001 | 2024-05-04 | User Interface | 4 | Easy to navigate, but color scheme could be better | No | N/A
CSAT-002 | CUST-1002 | 2024-06-04 | Shopping Cart | 3 | Sometimes cart items disappear | Yes | Bug identified, fix deployed
CSAT-003 | CUST-1003 | 2024-07-04 | Payment Gateway | 5 | Smooth transaction process | No | N/A
CSAT-004 | CUST-1004 | 2024-08-04 | Notifications | 2 | Notification delays for new offers | Yes | Server issue resolved, performance improved
CSAT-005 | CUST-1005 | 2024-09-04 | Teacher Dashboard | 4 | Useful features, add more report options | No | New report options added
CSAT-006 | CUST-1006 | 2024-10-04 | Search Functionality | 3 | Search results not relevant enough | Yes | Search algorithm optimized
CSAT-007 | CUST-1007 | 2024-11-04 | Mobile App | 5 | Great experience, easy to use | No | N/A
CSAT-008 | CUST-1008 | 2024-12-04 | Content Management | 4 | Good content variety, need more filters | No | Filter options enhanced
CSAT-009 | CUST-1009 | 13/04/2024 | User Authentication | 2 | Password reset emails not received | Yes | Email service issue resolved
CSAT-010 | CUST-1010 | 14/04/2024 | Product Catalog | 5 | Excellent product descriptions and images | No | N/A

## Code Coverage
Module/Component | Total Lines of Code (LOC) | Lines Covered by Tests | Code Coverage (%) | Test Coverage Status (Low/Medium/High) | Comments
User Interface | 4000 | 2800 | 70% | Medium | Needs more unit tests for edge cases
Authentication | 2500 | 2250 | 90% | High | Well covered, only a few edge cases left
Database | 3000 | 1800 | 60% | Low | More tests needed for complex queries
Payment Gateway | 1500 | 1200 | 80% | High | Focus on error handling scenarios
Shopping Cart | 2200 | 1540 | 70% | Medium | Improve test coverage for discounts
Notifications | 1000 | 400 | 40% | Low | Add tests for various notification types
Teacher Dashboard | 3200 | 2400 | 75% | Medium | Good coverage, optimize test scenarios
Content Management | 2000 | 1000 | 50% | Low | Add tests for file upload functionality
Search Functionality | 1800 | 1440 | 80% | High | Improve test coverage for complex queries
User Profile Management | 1700 | 1190 | 70% | Medium | Enhance validation tests
Total | 22900 | 15020 | 66% | Medium | Overall coverage is satisfactory, but can be improved

## Technical Debt
Debt ID | Component/Module | Description of Debt | Priority (Low/Medium/High) | Impact | Estimated Effort (Hours) | Created Date | Assigned To | Planned Resolution Date | Comments
TD-001 | User Interface | Hard-coded strings in UI elements | Medium | Difficult to localize | 10 | 2024-05-04 | John Doe | 30/04/2024 | Need to use string resources for localization
TD-002 | Payment Gateway Integration | Deprecated API usage | High | Risk of payment failure | 12 | 2024-07-04 | Sara Davis | 20/04/2024 | Update to the latest API version required
TD-003 | Database | Missing indexes on frequently queried tables | High | Performance issues | 15 | 2024-08-04 | Mike Johnson | 25/04/2024 | Add appropriate indexes to improve performance
TD-004 | Authentication Module | Legacy authentication library in use | High | Security vulnerabilities | 20 | 2024-10-04 | Jane Smith | 28/04/2024 | Upgrade to new authentication method
TD-005 | Mobile App | Outdated dependencies | Medium | Compatibility issues | 8 | 2024-12-04 | Linda Green | 30/04/2024 | Update to latest SDK versions
TD-006 | Teacher Dashboard Reports | Complex queries without optimization | High | Slow response times | 18 | 14/04/2024 | Emma Brown | 2024-05-05 | Refactor queries for optimization
TD-007 | Content Management | Inline CSS in HTML templates | Low | Difficult to maintain | 5 | 16/04/2024 | Chris White | 25/04/2024 | Move CSS to external stylesheet
TD-008 | Notifications | No retry mechanism for failed notifications | Medium | Lost notifications | 10 | 18/04/2024 | David Black | 2024-02-05 | Implement retry logic for failed notifications
TD-009 | Search Functionality | Inefficient search algorithm | High | Poor user experience | 15 | 20/04/2024 | Jane Smith | 2024-10-05 | Optimize search algorithm
TD-010 | User Profile Management | No validation for user input fields | High | Data integrity issues | 8 | 22/04/2024 | Mike Johnson | 2024-01-05 | Add input validation checks

## Blocked Time
Task ID | Task Name | Assigned To | Blocked Start Date | Blocked End Date | Total Blocked Time (Days) | Reason for Blockage | Resolution/Comments
1 | UI Design for Shopping Cart | John Doe | 2024-05-04 | 2024-08-04 | 3 | Awaiting feedback from stakeholders | Feedback received, design updated
2 | API Integration with Payment Gateway | Sara Davis | 2024-10-04 | 15/04/2024 | 5 | Delay in receiving API credentials | API keys received, integration ongoing
3 | Database Schema Update | Mike Johnson | 2024-12-04 | 13/04/2024 | 1 | Dependency on finalizing product catalog | Product catalog finalized, schema updated
4 | User Authentication Module | Jane Smith | 14/04/2024 | 18/04/2024 | 4 | Conflict in third-party library versions | Library updated, issue resolved
5 | Mobile App Notifications | Linda Green | 15/04/2024 | 20/04/2024 | 5 | Server issues affecting push notifications | Server issue fixed, testing resumed
6 | Teacher Dashboard Reports | Emma Brown | 17/04/2024 | 18/04/2024 | 1 | Data inconsistency in reporting API | Data source corrected, report updated
7 | Content Upload for Supplies Catalog | Chris White | 20/04/2024 | 23/04/2024 | 3 | Delay in receiving content from vendors | Content received, uploaded successfully
8 | User Profile Management | David Black | 22/04/2024 | 24/04/2024 | 2 | Awaiting UI design approval | Design approved, development resumed
9 | Search Functionality | Jane Smith | 25/04/2024 | 27/04/2024 | 2 | Issue with indexing service | Indexing service updated, issue resolved
10 | Teacher Resource Integration | Mike Johnson | 28/04/2024 | 30/04/2024 | 2 | API rate limiting causing delays | Rate limits adjusted, integration completed

## Release Burnup
Sprint Number | Start Date | End Date | Total Scope (Story Points) | Work Completed (Story Points) | Cumulative Work Completed (Story Points)
Sprint 1 | 2024-01-04 | 14/04/2024 | 150 | 20 | 20
Sprint 2 | 15/04/2024 | 28/04/2024 | 150 | 30 | 50
Sprint 3 | 29/04/2024 | 2024-12-05 | 160 | 25 | 75
Sprint 4 | 13/05/2024 | 26/05/2024 | 160 | 35 | 110
Sprint 5 | 27/05/2024 | 2024-09-06 | 160 | 30 | 140
Sprint 6 | 2024-10-06 | 23/06/2024 | 170 | 20 | 160
Sprint 7 | 24/06/2024 | 2024-07-07 | 170 | 35 | 195
Sprint 8 | 2024-08-07 | 21/07/2024 | 180 | 25 | 220
Sprint 9 | 22/07/2024 | 2024-04-08 | 180 | 30 | 250
Sprint 10 | 2024-05-08 | 18/08/2024 | 180 | 20 | 270

## Sprint Goal Success Rate
Sprint Number | Start Date | End Date | Sprint Goal | Goal Achieved (Yes/No) | Success Rate (%)
Sprint 1 | 2024-01-04 | 14/04/2024 | Implement Login Module | Yes | 100
Sprint 2 | 15/04/2024 | 28/04/2024 | Complete UI Design | No | 60
Sprint 3 | 29/04/2024 | 2024-12-05 | Integrate Payment Gateway | Yes | 100
Sprint 4 | 13/05/2024 | 26/05/2024 | Develop Notification System | No | 70
Sprint 5 | 27/05/2024 | 2024-09-06 | Finalize User Reports | Yes | 100
Sprint 6 | 2024-10-06 | 23/06/2024 | Complete API Integration | No | 80
Sprint 7 | 24/06/2024 | 2024-07-07 | Conduct Full System Testing | Yes | 100
Sprint 8 | 2024-08-07 | 21/07/2024 | Fix Critical Bugs | Yes | 100
Sprint 9 | 22/07/2024 | 2024-04-08 | Optimize Database Performance | No | 75
Sprint 10 | 2024-05-08 | 18/08/2024 | Prepare for Launch | Yes | 100

## Team Happiness
Team Member | Role | Survey Date | Happiness Rating (1-5) | Stress Level (1-5) | Comments
John Doe | UI/UX Designer | 2024-01-04 | 4 | 3 | Feeling good, workload manageable.
Jane Smith | Backend Developer | 2024-01-04 | 3 | 4 | Slightly overwhelmed with deadlines.
Mike Johnson | Database Administrator | 2024-01-04 | 5 | 2 | Enjoying the project, no major concerns.
Sara Davis | API Integration Lead | 2024-01-04 | 3 | 4 | Finding it hard to manage time.
Emma Brown | QA Tester | 2024-01-04 | 4 | 3 | Comfortable with tasks, but testing load is rising.
Chris White | Content Specialist | 2024-01-04 | 5 | 2 | Very satisfied with workload and team communication.
Linda Green | Mobile App Developer | 2024-01-04 | 2 | 5 | Struggling with project scope and expectations.
Alex Blue | Project Manager | 2024-01-04 | 4 | 3 | Happy with progress but concerned about deadlines.
David Black | Frontend Developer | 2024-01-04 | 3 | 4 | Feels slightly under pressure with multiple tasks.
Rebecca Gray | Product Owner | 2024-01-04 | 5 | 2 | Satisfied with team progress, no issues.

## Escaped Defects
Module Name | Total Defects | Escaped to Testing | Escaped to UAT | Escaped to Production | Total Escaped Defects | Escape Rate (Total Escaped/Total Defects)
User Interface | 30 | 5 | 3 | 2 | 10 | 33.3%
Backend API | 40 | 8 | 5 | 3 | 16 | 40%
Database | 20 | 4 | 3 | 1 | 8 | 40%
Authentication | 25 | 3 | 4 | 2 | 9 | 36%
Payment Gateway | 18 | 2 | 3 | 1 | 6 | 33.3%
Notifications | 15 | 2 | 2 | 1 | 5 | 33.3%
Reporting | 22 | 4 | 4 | 2 | 10 | 45.5%
Mobile App Module | 35 | 6 | 5 | 3 | 14 | 40%
Total | 205 | 34 | 29 | 15 | 78 | 38%

## Defect Leakage
Module Name | Total Defects | Defects Found in Development | Defects Found in Testing | Defects Found in Production | Leakage Rate (Production/Total)
User Interface | 20 | 10 | 7 | 3 | 15%
Backend API | 25 | 15 | 8 | 2 | 8%
Database | 12 | 7 | 4 | 1 | 8%
Authentication | 15 | 8 | 5 | 2 | 13%
Payment Gateway | 18 | 12 | 5 | 1 | 6%
Notifications | 10 | 4 | 5 | 1 | 10%
Reporting | 16 | 10 | 4 | 2 | 12%
Mobile App Module | 22 | 12 | 8 | 2 | 9%
Total | 138 | 78 | 46 | 14 | 10%

## Velocity
Sprint | Planned Story Points | Completed Story Points | Velocity | Notes
Sprint 1 | 50 | 45 | 45 | Initial sprint, minor scope changes.
Sprint 2 | 55 | 50 | 50 | Team adapting to new processes.
Sprint 3 | 60 | 55 | 55 | Good sprint, team at full capacity.
Sprint 4 | 65 | 60 | 60 | No blockers, smooth execution.
Sprint 5 | 60 | 52 | 52 | Unplanned leave impacted capacity.
Sprint 6 | 70 | 68 | 68 | High performance, no impediments.
Sprint 7 | 75 | 72 | 72 | Focused sprint, major deliverables.
Sprint 8 | 70 | 65 | 65 | Minor delays due to integration issues.
Sprint 9 | 80 | 75 | 75 | Team performing consistently.
Sprint 10 | 85 | 80 | 80 | High velocity, on track for goals.
Sprint 11 | 80 | 78 | 78 | Slight deviation from plan.
Sprint 12 | 90 | 85 | 85 | Smooth sprint, minor adjustments.
Sprint 13 | 95 | 90 | 90 | Continuous improvement observed.
Sprint 14 | 100 | 95 | 95 | Team at optimal performance level.
Sprint 15 | 90 | 88 | 88 | Consistent velocity maintained.
Sprint 16 | 85 | 83 | 83 | Minor disruptions handled well.
Sprint 17 | 95 | 90 | 90 | Strong performance across team.
Sprint 18 | 100 | 98 | 98 | Close to perfect execution.
Sprint 19 | 105 | 100 | 100 | High engagement, excellent results.
Sprint 20 | 110 | 108 | 108 | Top velocity achieved.

## Cycle Time
Task ID | Task Description | Assigned To | Start Date | End Date | Cycle Time (Days) | Task Type | Priority | Comments
T-001 | User Registration Module | Developer A | 2024-03-01 | 2024-03-06 | 5 | Development | High | Initial setup for user login.
T-002 | Create Admin Dashboard UI | Developer B | 2024-03-07 | 2024-03-12 | 5 | UI/UX | Medium | UI design iterations included.
T-003 | Inventory Management Back-End | Developer C | 2024-03-13 | 2024-03-20 | 7 | Back-End | High | Database setup for inventory.
T-004 | Payment Gateway Integration | Developer D | 2024-03-10 | 2024-03-17 | 7 | Integration | High | Integrated with multiple providers.
T-005 | Order History Feature for Parents | Developer E | 2024-03-15 | 2024-03-18 | 3 | Development | Medium | Simple feature, quick completion.
T-006 | Bulk Ordering System | Developer F | 2024-03-19 | 2024-03-26 | 7 | Development | High | Required extensive back-end work.
T-007 | Implement Low Stock Alerts | Developer G | 2024-03-21 | 2024-03-25 | 4 | Development | Medium | Notifications setup for inventory.
T-008 | Role-Based Access Control Setup | Developer H | 2024-03-22 | 2024-03-28 | 6 | Development | High | Complex access management logic.
T-009 | In-App Chat Support | Developer I | 2024-03-23 | 2024-03-29 | 6 | Development | Medium | Implemented real-time messaging.
T-010 | AI Model Training for Supply Prediction | Data Scientist 1 | 2024-03-24 | 2024-04-07 | 14 | AI/ML | High | Extensive training cycles.
T-011 | Product Comparison Tool UI | Developer J | 2024-03-26 | 2024-03-30 | 4 | UI/UX | Medium | UI created for comparison feature.
T-012 | Implement Search Engine for Products | Developer K | 2024-03-27 | 2024-04-02 | 6 | Development | High | Search and filtering integrated.
T-013 | Vendor Feedback and Rating System | Developer L | 2024-03-28 | 2024-04-05 | 8 | Development | Medium | Vendor feedback loop created.
T-014 | Multi-Language Support Integration | Developer M | 2024-03-29 | 2024-04-04 | 6 | Integration | Medium | Added support for three languages.
T-015 | ADA Compliance Implementation | Developer N | 2024-04-01 | 2024-04-08 | 7 | Accessibility | High | Ensured compliance standards met.
T-016 | Order Grouping Feature | Developer O | 2024-04-02 | 2024-04-09 | 7 | Development | Medium | Grouping logic for multiple orders.
T-017 | Secure API Integration | Developer P | 2024-04-03 | 2024-04-11 | 8 | Integration | High | API secured with OAuth.
T-018 | Push Notifications Setup | Developer Q | 2024-04-04 | 2024-04-10 | 6 | Development | Medium | Notifications for mobile devices.
T-019 | Backup and Recovery System | Developer R | 2024-04-05 | 2024-04-12 | 7 | IT Infrastructure | High | Setup for critical data.
T-020 | Product Wishlist/Favorites Feature | Developer S | 2024-04-06 | 2024-04-13 | 7 | Development | Medium | Wishlist functionality added.
T-021 | Discount and Promotions Feature | Developer T | 2024-04-07 | 2024-04-15 | 8 | Development | Medium | Promotions logic implemented.
T-022 | Mobile Responsiveness Optimization | Developer U | 2024-04-08 | 2024-04-16 | 8 | UI/UX | High | Optimized for various devices.
T-023 | User Guide Documentation | Technical Writer | 2024-04-09 | 2024-04-12 | 3 | Documentation | Low | User manuals created.

## Lead Time
Task ID | Task Description | Assigned To | Start Date | End Date | Cycle Time (Days) | Task Type | Priority | Comments
T-001 | User Registration Module | Developer A | 2024-03-01 | 2024-03-06 | 5 | Development | High | Initial setup for user login.
T-002 | Create Admin Dashboard UI | Developer B | 2024-03-07 | 2024-03-12 | 5 | UI/UX | Medium | UI design iterations included.
T-003 | Inventory Management Back-End | Developer C | 2024-03-13 | 2024-03-20 | 7 | Back-End | High | Database setup for inventory.
T-004 | Payment Gateway Integration | Developer D | 2024-03-10 | 2024-03-17 | 7 | Integration | High | Integrated with multiple providers.
T-005 | Order History Feature for Parents | Developer E | 2024-03-15 | 2024-03-18 | 3 | Development | Medium | Simple feature, quick completion.
T-006 | Bulk Ordering System | Developer F | 2024-03-19 | 2024-03-26 | 7 | Development | High | Required extensive back-end work.
T-007 | Implement Low Stock Alerts | Developer G | 2024-03-21 | 2024-03-25 | 4 | Development | Medium | Notifications setup for inventory.
T-008 | Role-Based Access Control Setup | Developer H | 2024-03-22 | 2024-03-28 | 6 | Development | High | Complex access management logic.
T-009 | In-App Chat Support | Developer I | 2024-03-23 | 2024-03-29 | 6 | Development | Medium | Implemented real-time messaging.
T-010 | AI Model Training for Supply Prediction | Data Scientist 1 | 2024-03-24 | 2024-04-07 | 14 | AI/ML | High | Extensive training cycles.
T-011 | Product Comparison Tool UI | Developer J | 2024-03-26 | 2024-03-30 | 4 | UI/UX | Medium | UI created for comparison feature.
T-012 | Implement Search Engine for Products | Developer K | 2024-03-27 | 2024-04-02 | 6 | Development | High | Search and filtering integrated.
T-013 | Vendor Feedback and Rating System | Developer L | 2024-03-28 | 2024-04-05 | 8 | Development | Medium | Vendor feedback loop created.
T-014 | Multi-Language Support Integration | Developer M | 2024-03-29 | 2024-04-04 | 6 | Integration | Medium | Added support for three languages.
T-015 | ADA Compliance Implementation | Developer N | 2024-04-01 | 2024-04-08 | 7 | Accessibility | High | Ensured compliance standards met.
T-016 | Order Grouping Feature | Developer O | 2024-04-02 | 2024-04-09 | 7 | Development | Medium | Grouping logic for multiple orders.
T-017 | Secure API Integration | Developer P | 2024-04-03 | 2024-04-11 | 8 | Integration | High | API secured with OAuth.
T-018 | Push Notifications Setup | Developer Q | 2024-04-04 | 2024-04-10 | 6 | Development | Medium | Notifications for mobile devices.
T-019 | Backup and Recovery System | Developer R | 2024-04-05 | 2024-04-12 | 7 | IT Infrastructure | High | Setup for critical data.
T-020 | Product Wishlist/Favorites Feature | Developer S | 2024-04-06 | 2024-04-13 | 7 | Development | Medium | Wishlist functionality added.
T-021 | Discount and Promotions Feature | Developer T | 2024-04-07 | 2024-04-15 | 8 | Development | Medium | Promotions logic implemented.
T-022 | Mobile Responsiveness Optimization | Developer U | 2024-04-08 | 2024-04-16 | 8 | UI/UX | High | Optimized for various devices.
T-023 | User Guide Documentation | Technical Writer | 2024-04-09 | 2024-04-12 | 3 | Documentation | Low | User manuals created.

## Work In Progress
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Comments
1 | User Interface Design | John Doe | 2024-01-03 | 15/03/2024 | In Progress | Initial drafts completed
2 | Backend Development | Jane Smith | 2024-05-04 | 20/04/2024 | Not Started | Awaiting final designs
3 | Database Setup | Mike Johnson | 2024-10-03 | 20/03/2024 | Completed | Database ready for testing
4 | API Integration | Sara Davis | 15/04/2024 | 30/04/2024 | Not Started | Dependencies pending
5 | Testing Phase 1 | Emma Brown | 2024-01-05 | 2024-10-05 | Not Started | Scheduled for next month
6 | Content Creation | Chris White | 2024-01-04 | 2024-10-04 | In Progress | Drafts under review
7 | Mobile App Prototype | Linda Green | 15/03/2024 | 31/03/2024 | Completed | Approved by stakeholders
8 | Final Review | Project Team | 25/05/2024 | 30/05/2024 | Not Started | Final checks before launch

## Cumulative Flow Diagram
Date | Backlog | In Progress | Review | Completed
2024-01-04 | 20 | 0 | 0 | 0
2024-02-04 | 18 | 2 | 0 | 0
2024-03-04 | 15 | 5 | 0 | 0
2024-04-04 | 13 | 6 | 1 | 0
2024-05-04 | 10 | 7 | 2 | 1
2024-06-04 | 8 | 6 | 3 | 3
2024-07-04 | 6 | 5 | 4 | 5
2024-08-04 | 4 | 4 | 5 | 7
2024-09-04 | 3 | 3 | 6 | 8
2024-10-04 | 2 | 3 | 6 | 9
2024-11-04 | 1 | 2 | 6 | 11
2024-12-04 | 0 | 1 | 6 | 12

## Defect Density
Module Name | Lines of Code (LOC) | Number of Defects | Defect Density (Defects/LOC)
User Interface | 5000 | 12 | 0.0024
Backend API | 10000 | 20 | 0.002
Database | 3000 | 8 | 0.0027
Authentication | 2500 | 6 | 0.0024
Payment Gateway | 4500 | 10 | 0.0022
Notifications | 1200 | 4 | 0.0033
Reporting | 3500 | 9 | 0.0026
Mobile App Module | 7000 | 15 | 0.0021
Total | 36700 | 84 | 0.0023