## Sheet1
Requirement ID | Requirement Description | Category | Source | Design Specification ID | Development Task ID | Test Case ID | Status | Notes
BR-001 | Centralized platform for school supply procurement | Business Requirement | Stakeholder Interviews | DS-001 | DEV-001 | TC-001 | Approved
BR-002 | Reduction in procurement time by 25% | Business Requirement | Project Charter | DS-002 | DEV-002 | TC-002 | In Progress
BR-003 | Real-time integration with suppliers | Business Requirement | Workshops | DS-003 | DEV-003 | TC-003 | Approved
BR-004 | Multi-user role access system (parents, admins, suppliers) | Business Requirement | Stakeholder Interviews | DS-023 | DEV-023 | TC-023 | In Progress
BR-005 | Increase transparency and communication between suppliers and schools | Business Requirement | Stakeholder Interviews | DS-033 | DEV-033 | TC-033 | Pending Approval
BR-006 | Ensure compliance with FERPA and GDPR regulations | Business Requirement | Regulatory Compliance | DS-034 | DEV-034 | TC-034 | Approved
BR-007 | Vendor performance evaluation metrics | Business Requirement | Survey Results | DS-024 | DEV-068 | TC-068 | Pending Approval
BR-008 | Reduce supply procurement costs by 10% within the first year | Business Requirement | Project Charter | DS-037 | DEV-008 | TC-008 | In Progress | Added to cost optimization dashboard
BR-009 | Integration with existing school systems (ERP, financial systems) | Business Requirement | Stakeholder Interviews | DS-029 | DEV-009 | TC-009 | Pending Approval
BR-010 | Improve supplier relationships by 20% through direct communication | Business Requirement | Stakeholder Interviews | DS-036 | DEV-010 | TC-010 | Pending Approval
BR-011 | Increase app user retention by 15% through loyalty programs | Business Requirement | Stakeholder Interviews | DS-035 | DEV-053 | TC-053 | Pending Approval
BR-012 | Vendor feedback and rating system | Business Requirement | Survey Results | DS-054 | DEV-054 | TC-054 | Pending Approval
FR-001 | User Authentication and Authorization | Functional Requirement | RSD | DS-001 | DEV-004 | TC-004 | Approved
FR-002 | Inventory Management | Functional Requirement | Workshops | DS-005 | DEV-005 | TC-005 | In Progress
FR-003 | Order Tracking | Functional Requirement | Stakeholder Interviews | DS-006 | DEV-006 | TC-006 | Approved
FR-004 | Low Stock Alerts | Functional Requirement | Stakeholder Interviews | DS-025 | DEV-025 | TC-025 | Pending Approval
FR-005 | Payment Gateway Integration | Functional Requirement | Stakeholder Interviews | DS-007 | DEV-007 | TC-007 | In Progress
FR-006 | Supplier Performance Reporting | Functional Requirement | Survey Results | DS-024 | DEV-024 | TC-024 | Pending Approval
FR-007 | Bulk Ordering | Functional Requirement | Stakeholder Interviews | DS-014 | DEV-014 | TC-014 | Pending Approval
FR-008 | Shopping Cart Functionality | Functional Requirement | Survey Results | DS-013 | DEV-013 | TC-013 | In Progress
FR-009 | Automated recurring orders for frequently ordered supplies | Functional Requirement | Stakeholder Interviews | DS-066 | DEV-066 | TC-066 | Approved
FR-010 | Order History | Functional Requirement | Stakeholder Interviews | DS-021 | DEV-021 | TC-021 | In Progress
FR-011 | Reporting Dashboard for Admins | Functional Requirement | Workshops | DS-030 | DEV-030 | TC-030 | In Progress
FR-012 | Custom Reporting Tool | Functional Requirement | Stakeholder Interviews | DS-032 | DEV-032 | TC-032 | Pending Approval
FR-013 | Real-time product availability for parents | Functional Requirement | Survey Results | DS-019 | DEV-019 | TC-019 | In Progress
FR-014 | Discount and promotions feature for suppliers | Functional Requirement | Survey Results | DS-036 | DEV-069 | TC-069 | Pending Approval
FR-015 | Order grouping feature for parents with multiple children | Functional Requirement | Survey Results | DS-037 | DEV-070 | TC-070 | Pending Approval
FR-016 | Bulk and individual ordering options | Functional Requirement | Stakeholder Interviews | DS-014 | DEV-038 | TC-038 | In Progress
FR-017 | Supplier onboarding process | Functional Requirement | Stakeholder Interviews | DS-039 | DEV-039 | TC-039 | Pending Approval
FR-018 | Multi-user collaboration for admins | Functional Requirement | Workshops | DS-040 | DEV-040 | TC-040 | Pending Approval
FR-019 | User tutorial and onboarding flow | Functional Requirement | RSD | DS-055 | DEV-055 | TC-055 | Pending Approval
FR-020 | Notification preferences management | Functional Requirement | Workshops | DS-018 | DEV-056 | TC-056 | Pending Approval
FR-021 | Product comparison tool | Functional Requirement | Stakeholder Interviews | DS-057 | DEV-057 | TC-057 | Pending Approval
FR-022 | Order splitting feature for multiple suppliers | Functional Requirement | Stakeholder Interviews | DS-038 | DEV-058 | TC-058 | Pending Approval
NFR-001 | Performance - App load time within 3 seconds | Non-Functional Requirement | Project Charter | DS-008 | DEV-008 | TC-008 | In Progress
NFR-002 | Scalability for increased user traffic | Non-Functional Requirement | RSD | DS-026 | DEV-026 | TC-026 | Pending Approval
NFR-003 | Data Encryption for sensitive information | Non-Functional Requirement | RSD | DS-009 | DEV-009 | TC-009 | Approved
NFR-004 | Multi-Language Support (English, French, Spanish) | Non-Functional Requirement | Workshops | DS-015 | DEV-015 | TC-015 | Pending Approval
NFR-005 | Availability (99.9% uptime) | Non-Functional Requirement | RSD | DS-027 | DEV-027 | TC-027 | In Progress
NFR-007 | Backup and Recovery | Non-Functional Requirement | RSD | DS-016 | DEV-016 | TC-016 | Approved
NFR-012 | ADA compliance with accessibility standards | Non-Functional Requirement | Regulatory Compliance | DS-071 | DEV-071 | TC-071 | Pending Approval
NFR-016 | GDPR-compliant data portability | Non-Functional Requirement | Regulatory Compliance | DS-059 | DEV-059 | TC-059 | Approved
NFR-017 | Offline access for order history | Non-Functional Requirement | RSD | DS-060 | DEV-060 | TC-060 | Pending Approval
NFR-018 | Push notifications for mobile users | Non-Functional Requirement | Survey Results | DS-061 | DEV-061 | TC-061 | Approved
TR-010 | Load balancing for high availability | Technical Requirement | Infrastructure Planning | DS-072 | DEV-072 | TC-072 | In Progress
TR-011 | Database partitioning for optimized performance | Technical Requirement | RSD | DS-073 | DEV-073 | TC-073 | Pending Approval
TR-013 | Encryption for sensitive fields in the database | Technical Requirement | Regulatory Compliance | DS-048 | DEV-048 | TC-048 | Approved
TR-015 | AI-powered supply prediction tool | Technical Requirement | Workshops | DS-062 | DEV-062 | TC-062 | Pending Approval
TR-016 | Automatic server scaling | Technical Requirement | Infrastructure Planning | DS-063 | DEV-063 | TC-063 | Approved
UR-001 | Parent User Registration | User Requirement | Survey Results | DS-011 | DEV-011 | TC-011 | Approved
UR-003 | Admin User Role Assignment | User Requirement | Workshops | DS-012 | DEV-012 | TC-012 | In Progress
UR-005 | Admin Report Generation | User Requirement | Stakeholder Interviews | DS-029 | DEV-029 | TC-029 | Pending Approval
UR-007 | Parent Order Notifications | User Requirement | Survey Results | DS-018 | DEV-018 | TC-018 | Approved
UR-009 | Parent payment history | User Requirement | Survey Results | DS-049 | DEV-049 | TC-049 | In Progress
UR-010 | Admin role delegation | User Requirement | Workshops | DS-075 | DEV-075 | TC-075 | Pending Approval
UR-011 | Parent supply suggestions based on class schedule | User Requirement | Survey Results | DS-020 | DEV-020 | TC-020 | Pending Approval
UR-012 | Supplier product management | User Requirement | Workshops | DS-031 | DEV-031 | TC-031 | In Progress
UR-015 | Voice-assisted search (voice commands for searching supplies) | User Requirement | Survey Results | DS-064 | DEV-064 | TC-064 | Pending Approval
UR-016 | In-app chat support | User Requirement | Stakeholder Interviews | DS-065 | DEV-065 | TC-065 | Pending Approval
UR-017 | Quick reorder option for frequently purchased items | User Requirement | Workshops | DS-066 | DEV-066 | TC-066 | Approved
UR-018 | Group purchasing options for bulk discounts | User Requirement | Stakeholder Interviews | DS-067 | DEV-067 | TC-067 | Pending Approval
TR-002 | API Integration with Suppliers | Technical Requirement | Stakeholder Interviews | DS-010 | DEV-010 | TC-010 | Approved
TR-003 | Cloud Hosting and Infrastructure | Technical Requirement | RSD | DS-028 | DEV-028 | TC-028 | In Progress
TR-004 | Multi-Factor Authentication (MFA) | Technical Requirement | Regulatory Compliance | DS-044 | DEV-044 | TC-044 | Approved
TR-009 | API Endpoint Security | Technical Requirement | Workshops | DS-017 | DEV-017 | TC-017 | Approved
TR-010 | Load balancing for high availability | Technical Requirement | Infrastructure Planning | DS-072 | DEV-072 | TC-072 | In Progress
TR-011 | Database partitioning for optimized performance | Technical Requirement | RSD | DS-073 | DEV-073 | TC-073 | Pending Approval
TR-013 | Encryption for sensitive fields in the database | Technical Requirement | Regulatory Compliance | DS-048 | DEV-048 | TC-048 | Approved
TR-015 | AI-powered supply prediction tool | Technical Requirement | Workshops | DS-062 | DEV-062 | TC-062 | Pending Approval
TR-016 | Automatic server scaling | Technical Requirement | Infrastructure Planning | DS-063 | DEV-063 | TC-063 | Approved
UR-001 | Parent User Registration | User Requirement | Survey Results | DS-011 | DEV-011 | TC-011 | Approved
UR-003 | Admin User Role Assignment | User Requirement | Workshops | DS-012 | DEV-012 | TC-012 | In Progress
UR-005 | Admin Report Generation | User Requirement | Stakeholder Interviews | DS-029 | DEV-029 | TC-029 | Pending Approval
UR-007 | Parent Order Notifications | User Requirement | Survey Results | DS-018 | DEV-018 | TC-018 | Approved
UR-009 | Parent payment history | User Requirement | Survey Results | DS-049 | DEV-049 | TC-049 | In Progress
UR-010 | Admin role delegation | User Requirement | Workshops | DS-075 | DEV-075 | TC-075 | Pending Approval
UR-011 | Parent supply suggestions based on class schedule | User Requirement | Survey Results | DS-020 | DEV-020 | TC-020 | Pending Approval
UR-012 | Supplier product management | User Requirement | Workshops | DS-031 | DEV-031 | TC-031 | In Progress
UR-015 | Voice-assisted search (voice commands for searching supplies) | User Requirement | Survey Results | DS-064 | DEV-064 | TC-064 | Pending Approval
UR-016 | In-app chat support | User Requirement | Stakeholder Interviews | DS-065 | DEV-065 | TC-065 | Pending Approval
UR-017 | Quick reorder option for frequently purchased items | User Requirement | Workshops | DS-066 | DEV-066 | TC-066 | Approved
UR-018 | Group purchasing options for bulk discounts | User Requirement | Stakeholder Interviews | DS-067 | DEV-067 | TC-067 | Pending Approval