## Level-1
WBS ID | Task Name | Description | Phase | Linked Requirement ID | Scope | Cost | Deliverables | Duration (days) | Start Date | End Date | Acceptance Criteria | Budget | Milestones | Team / Person Responsible
WBS-001 | User Registration System | Create a system for parent, admin, and supplier registration | Development | UR-001, FR-001 | User account creation and management | 50000 | Registration interface | 14 | 2024-03-01 | 2024-03-15 | User can register successfully and access their dashboard | 50000 | Registration system completed | Development Team
WBS-002 | Admin Inventory Management | Develop inventory management system for admins | Development | FR-002, FR-005 | Inventory updates, stock alerts | 80000 | Inventory management dashboard | 20 | 2024-03-16 | 2024-04-05 | Admin can update stock levels and receive low-stock alerts | 80000 | Inventory system deployment | Development Team
WBS-003 | Parent Dashboard | Create a dashboard for parents showing order history and supply suggestions | Development | UR-007, FR-003 | Display of parent order information | 40000 | Parent dashboard | 15 | 2024-03-16 | 2024-03-31 | Parent can view order history and receive supply suggestions based on the schedule | 40000 | Dashboard completion | Development Team
WBS-004 | Secure Payment Integration | Integrate payment gateway for secure checkout | Development | FR-005, NFR-003 | Payment processing | 60000 | Payment gateway and encryption | 12 | 2024-04-01 | 2024-04-13 | Secure payment is processed, and data is encrypted in transit and at rest | 60000 | Payment integration completed | Development Team
WBS-005 | Product Comparison Tool | Develop a tool to allow users to compare products before purchase | Development | FR-021, FR-014 | Product comparison | 35000 | Comparison interface | 10 | 2024-04-06 | 2024-04-16 | Users can compare products based on price, supplier, and reviews | 35000 | Product comparison feature completed | Development Team
WBS-006 | Order Tracking System | Implement order tracking system for parents | Development | UR-006, FR-003 | Real-time order status | 45000 | Order tracking page | 14 | 2024-03-17 | 2024-03-31 | Parents can track their orders in real-time | 45000 | Order tracking feature deployment | Development Team
WBS-007 | AI-Powered Supply Prediction | Implement AI tool to predict future supply needs based on historical data | Development | TR-015 | AI-powered predictions | 100000 | AI-powered prediction tool | 30 | 2024-04-05 | 2024-05-05 | Admins receive accurate predictions based on past data | 100000 | AI prediction system deployment | AI & Development Team
WBS-008 | Role-Based Access Control | Implement a multi-user role system for different users | Development | BR-004, UR-003 | Role-based access | 55000 | Multi-user role access system | 14 | 2024-03-25 | 2024-04-08 | Admins can assign roles with specific permissions | 55000 | Role-based access control completed | Development Team
WBS-009 | In-App Chat Support | Implement real-time chat support for users | Development | UR-016 | Real-time chat interface | 25000 | Chat support interface | 8 | 2024-03-29 | 2024-04-06 | Users can communicate with support in real-time for order-related issues | 25000 | In-app chat feature completed | Development Team
WBS-010 | Bulk Ordering System | Enable bulk ordering functionality for admins | Development | FR-007 | Bulk ordering for schools | 50000 | Bulk ordering system | 12 | 2024-04-02 | 2024-04-14 | Admins can place bulk orders for multiple supplies | 50000 | Bulk ordering system deployment | Development Team
WBS-011 | Product Search and Filter | Create a product search system with filters | Development | FR-008, FR-014 | Product search and filtering | 35000 | Product search system | 12 | 2024-04-10 | 2024-04-22 | Users can search and filter products based on category, price, and supplier | 35000 | Product search system completed | Development Team
WBS-012 | Reports Dashboard (Admin) | Develop reporting tools for admins to view supplier performance and spending | Development | FR-011, BR-008 | Reporting tools for admins | 70000 | Admin reports dashboard | 20 | 2024-04-15 | 2024-05-05 | Admins can view reports on supplier performance and inventory spending | 70000 | Reporting tools completed | Development Team
WBS-013 | Notifications and Alerts | Implement a notification system for order updates and inventory alerts | Development | UR-007, FR-004 | Notifications and alerts | 30000 | Real-time notifications | 10 | 2024-03-21 | 2024-03-31 | Users receive notifications on order updates and low-stock inventory alerts | 30000 | Notification system deployment | Development Team
WBS-014 | Supplier Product Management | Develop a system for suppliers to manage their products | Development | UR-012 | Supplier product management | 40000 | Product management system | 15 | 2024-04-15 | 2024-04-30 | Suppliers can add, edit, and delete products and manage stock availability | 40000 | Supplier product management completed | Development Team
WBS-015 | Multi-Language Support | Implement support for multiple languages (English, French, Spanish) | Development | NFR-004 | Language options | 20000 | Multi-language support | 8 | 2024-04-20 | 2024-04-28 | Users can switch the app to their preferred language | 20000 | Multi-language support completed | Development Team
WBS-016 | Product Wishlist/Favorites | Enable parents to save items to a wishlist for future purchases | Development | UR-012 | Wishlist functionality | 25000 | Wishlist feature | 10 | 2024-04-22 | 2024-05-02 | Parents can save items to a wishlist and move them to the cart later | 25000 | Wishlist system deployment | Development Team
WBS-017 | Data Encryption for Security | Implement encryption for sensitive data such as payment and personal info | Development | NFR-003, TR-013 | Data encryption | 50000 | Data encryption system | 14 | 2024-04-25 | 2024-05-09 | Sensitive data is encrypted in transit and at rest | 50000 | Encryption system completed | Development Team
WBS-018 | Recurring Orders Setup (Parent) | Enable parents to set up recurring orders for frequently used supplies | Development | UR-014 | Recurring order setup | 30000 | Recurring order system | 12 | 2024-05-01 | 2024-05-13 | Parents can set up and manage recurring orders for selected products | 30000 | Recurring order system completed | Development Team
WBS-019 | Load Balancing for High Traffic | Implement load balancing to ensure system handles high traffic | Development | TR-010 | Traffic management and load balancing | 60000 | Load balancing system | 15 | 2024-04-25 | 2024-05-10 | System automatically distributes traffic to prevent failures during high load | 60000 | Load balancing system completed | IT Team
WBS-020 | Server Scalability (Auto-Scaling) | Implement automatic server scaling based on traffic patterns | Development | TR-016 | Server scaling | 70000 | Auto-scaling system | 20 | 2024-05-01 | 2024-05-21 | System scales automatically to accommodate increased traffic | 70000 | Auto-scaling system completed | IT Team
WBS-021 | Database Partitioning | Partition the database to improve performance and scalability | Development | TR-011 | Database optimization | 50000 | Partitioned database | 18 | 2024-05-02 | 2024-05-20 | Database performance is improved with optimized query times | 50000 | Database partitioning completed | Database Team
WBS-022 | Multi-Factor Authentication (MFA) | Implement MFA for secure access to admin and supplier accounts | Development | TR-004 | Secure access for admin and suppliers | 40000 | MFA system | 10 | 2024-05-05 | 2024-05-15 | Admins and suppliers can log in securely using MFA | 40000 | MFA system completed | IT & Security Team
WBS-023 | Low Stock Alerts | Implement a system to notify admins when stock is low | Development | FR-004 | Low stock notification | 35000 | Low stock alert system | 12 | 2024-05-06 | 2024-05-18 | Admins receive real-time alerts when stock falls below the set threshold | 35000 | Low stock alert system completed | Development Team
WBS-024 | Custom Reporting Tool | Create a custom reporting tool for admins to generate detailed reports | Development | FR-012 | Custom reports generation | 55000 | Custom reporting tool | 15 | 2024-05-10 | 2024-05-25 | Admins can generate and download custom reports based on selected criteria | 55000 | Custom reporting tool completed | Development Team
WBS-025 | Push Notifications for Mobile | Enable push notifications for mobile users | Development | NFR-018 | Push notifications for mobile users | 30000 | Push notification system | 10 | 2024-05-15 | 2024-05-25 | Mobile users receive push notifications for important updates | 30000 | Push notifications completed | Mobile Development Team
WBS-026 | Multi-Language Support | Enable support for multiple languages in the app | Development | NFR-004 | Multi-language options | 25000 | Language support feature | 12 | 2024-05-20 | 2024-06-01 | Users can switch between multiple languages (English, French, Spanish) | 25000 | Multi-language support completed | Development Team
WBS-027 | Data Portability (GDPR Compliance) | Implement GDPR-compliant data export functionality for user accounts | Development | NFR-016 | Data export and GDPR compliance | 40000 | Data export functionality | 10 | 2024-05-22 | 2024-06-01 | Users can export their data in a machine-readable format in compliance with GDPR | 40000 | Data portability system completed | Compliance & IT Team
WBS-028 | Supplier Performance Dashboard | Implement a dashboard to track supplier performance metrics | Development | BR-007 | Supplier performance tracking | 45000 | Supplier performance dashboard | 14 | 2024-05-25 | 2024-06-08 | Admins can view and track supplier performance based on delivery times, accuracy | 45000 | Supplier performance system completed | Development Team
WBS-029 | Recurring Orders for Parents | Enable parents to set up recurring orders for frequently purchased items | Development | UR-014 | Recurring order setup | 40000 | Recurring order functionality | 12 | 2024-05-26 | 2024-06-07 | Parents can manage recurring orders for frequently purchased supplies | 40000 | Recurring orders system completed | Development Team
WBS-030 | Voice-Assisted Search | Implement voice search functionality for finding school supplies | Development | UR-015 | Voice-enabled search functionality | 35000 | Voice search interface | 14 | 2024-05-27 | 2024-06-10 | Users can search for school supplies using voice commands | 35000 | Voice search system completed | Development Team
WBS-031 | Supplier Product Management | Develop a tool for suppliers to manage their product catalogs | Development | UR-012 | Product management for suppliers | 40000 | Supplier product management system | 15 | 2024-05-28 | 2024-06-12 | Suppliers can upload, edit, and manage their product offerings | 40000 | Supplier product management completed | Development Team
WBS-032 | Forgot Password System | Implement a system for users to reset their passwords | Development | UR-001 | Password recovery system | 25000 | Password recovery functionality | 8 | 2024-05-30 | 2024-06-07 | Users can reset their passwords using a registered email | 25000 | Forgot password system completed | Development Team
WBS-033 | Product Details Page | Create a detailed product information page for parents and admins | Development | FR-013 | Product details for selected items | 30000 | Product details page | 10 | 2024-06-01 | 2024-06-11 | Users can view product details, prices, availability, and supplier info | 30000 | Product details page completed | Development Team
WBS-034 | Reports Dashboard (Admin) | Provide administrators with a reports dashboard for viewing key metrics | Development | FR-011, BR-008 | Reports dashboard for admins | 50000 | Admin reports dashboard | 18 | 2024-06-05 | 2024-06-23 | Admins can view reports on inventory, spending, and supplier performance | 50000 | Admin reports dashboard completed | Development Team
WBS-035 | Multi-Location Admin Dashboard | Develop a dashboard for administrators managing multiple schools/locations | Development | UR-013 | Multi-location management | 50000 | Multi-location admin dashboard | 14 | 2024-06-10 | 2024-06-24 | Admins can toggle between different locations and view specific metrics | 50000 | Multi-location dashboard completed | Development Team
WBS-036 | AI Supply Prediction Tool | AI-powered predictions for supply needs based on past data | Development | TR-015 | AI-driven supply predictions | 80000 | AI-powered supply prediction tool | 18 | 2024-06-15 | 2024-07-03 | Accurate supply predictions provided based on historical data | 80000 | AI prediction tool deployed | AI & Development Team
WBS-037 | ADA Compliance | Ensure the app is ADA-compliant and accessible for all users | Development | NFR-012 | ADA-compliance features | 40000 | ADA compliance across the app | 12 | 2024-06-20 | 2024-07-02 | The app meets all ADA standards for accessibility | 40000 | ADA compliance completed | Compliance & Development Team
WBS-038 | Discount and Promotion Feature | Allow suppliers to offer discounts and promotions to users | Development | FR-014 | Discounts and promotions feature | 35000 | Discounts and promotions functionality | 10 | 2024-06-22 | 2024-07-02 | Suppliers can create and offer promotions/discounts to parents and admins | 35000 | Discounts feature deployed | Development Team
WBS-039 | Order Grouping for Parents | Enable parents to group their orders for multiple children for easier management | Development | FR-015 | Grouping orders by children | 30000 | Group ordering functionality | 10 | 2024-06-24 | 2024-07-04 | Parents can group orders for multiple children and manage them in one place | 30000 | Order grouping completed | Development Team
WBS-040 | Group Purchasing for Bulk Orders | Enable group purchasing for bulk discounts for parents | Development | UR-018 | Group purchasing | 50000 | Group purchasing feature | 12 | 2024-06-26 | 2024-07-08 | Parents can group purchases for discounts from suppliers | 50000 | Group purchasing feature completed | Development Team
WBS-041 | Secure API Integration | Ensure secure API integration with third-party suppliers for real-time updates | Development | TR-002, TR-009 | Secure API integration | 70000 | Secure API integration | 14 | 2024-07-01 | 2024-07-15 | Real-time integration with suppliers is secure and compliant | 70000 | API integration completed | IT & Security Team
WBS-042 | Performance Optimization | Optimize app performance for quick load times and responsive design | Development | NFR-001 | Performance optimization | 60000 | Optimized performance | 10 | 2024-07-05 | 2024-07-15 | The app loads in under 3 seconds and functions smoothly across all devices | 60000 | Performance optimization completed | IT & Development Team
WBS-043 | Data Backup and Recovery | Implement a robust backup and recovery system to ensure data integrity | Development | NFR-007 | Data backup and recovery | 50000 | Backup and recovery system | 12 | 2024-07-08 | 2024-07-20 | The system performs regular backups and can restore data within 24 hours | 50000 | Backup and recovery system deployed | IT Team
WBS-044 | Mobile App Responsiveness | Ensure mobile responsiveness for the app across all devices | Development | NFR-009 | Mobile responsiveness | 30000 | Fully responsive mobile app | 10 | 2024-07-12 | 2024-07-22 | The app works seamlessly on mobile, tablet, and desktop platforms | 30000 | Mobile responsiveness completed | Mobile Development Team

## Level-n
WBS ID | Task Name | Description | Phase | Linked Requirement ID | Scope | Cost | Deliverables | Duration (days) | Start Date | End Date | Acceptance Criteria | Budget | Milestones | Team / Person Responsible
WBS-001 | User Registration System | Create a system for parent, admin, and supplier registration | Development | UR-001, FR-001 | User account creation and management | 50000 | Registration interface | 14 | 2024-03-01 | 2024-03-15 | Users can register successfully and access their dashboard | 50000 | Registration system completed | Development Team
WBS-001.1 | Create Registration UI | Design the UI for registration interface for users | Development | UR-001 | Interface design | 10000 | UI design for registration | 5 | 2024-03-01 | 2024-03-06 | The UI follows user-friendly principles | 10000 | UI design completed | UI/UX Team
WBS-001.2 | Build Back-End for Registration | Create a back-end system for handling registration data | Development | UR-001 | Back-end system | 15000 | Secure back-end for data management | 6 | 2024-03-07 | 2024-03-13 | Back-end successfully processes registrations and stores user data | 15000 | Back-end system completed | Back-End Development Team
WBS-001.3 | Integrate Social Media Logins | Integrate Google/Facebook login options | Development | UR-001 | Social media integration | 10000 | Google and Facebook login options | 3 | 2024-03-14 | 2024-03-16 | Users can log in using social media accounts | 10000 | Social media login integrated | Development Team
WBS-001.4 | Test and Deploy Registration | Conduct end-to-end testing and deploy the registration system | Testing | UR-001 | Testing and deployment | 15000 | Registration system tested and deployed | 3 | 2024-03-17 | 2024-03-20 | No critical issues during testing, system is live | 15000 | Registration system live | QA & Development Teams
WBS-002 | Admin Inventory Management | Develop inventory management system for admins | Development | FR-002, FR-005 | Inventory updates, stock alerts | 80000 | Inventory management dashboard | 20 | 2024-03-16 | 2024-04-05 | Admin can update stock levels and receive low-stock alerts | 80000 | Inventory system deployment | Development Team
WBS-002.1 | Create Inventory Dashboard UI | Design the admin dashboard for inventory management | Development | FR-002 | UI design for dashboard | 20000 | Admin inventory dashboard design | 5 | 2024-03-16 | 2024-03-21 | Dashboard designed and ready for implementation | 20000 | Dashboard UI completed | UI/UX Team
WBS-002.2 | Build Inventory Database | Set up the database structure for managing inventory | Development | FR-002 | Inventory database | 30000 | Inventory database ready | 8 | 2024-03-22 | 2024-03-30 | Inventory data stored, organized, and accessible | 30000 | Inventory database completed | Database Team
WBS-002.3 | Implement Low Stock Alerts | Develop alert system to notify admins of low stock | Development | FR-004 | Low-stock alerts | 20000 | Low-stock alerts system | 5 | 2024-03-31 | 2024-04-05 | Admins receive real-time notifications when stock levels are low | 20000 | Low-stock alert system completed | Development Team
WBS-002.4 | Test and Deploy Inventory System | Conduct end-to-end testing and deploy the inventory management system | Testing | FR-002 | Testing and deployment | 10000 | Inventory system tested and deployed | 2 | 2024-04-06 | 2024-04-07 | Inventory system works without issues, deployed to live system | 10000 | Inventory system live | QA & Development Teams
WBS-003 | Parent Dashboard | Create a dashboard for parents showing order history and supply suggestions | Development | UR-007, FR-003 | Display of parent order information | 40000 | Parent dashboard | 15 | 2024-03-16 | 2024-03-31 | Parent can view order history and receive supply suggestions based on the schedule | 40000 | Dashboard completion | Development Team
WBS-003.1 | Design Parent Dashboard UI | Create a user-friendly interface for the parent dashboard | Development | UR-007 | UI design for parent dashboard | 12000 | Parent dashboard UI | 5 | 2024-03-16 | 2024-03-21 | Dashboard is designed with user-friendly navigation | 12000 | UI design completed | UI/UX Team
WBS-003.2 | Build Order History Display | Create a module to display past and current orders for parents | Development | FR-003 | Order history module | 15000 | Order history feature | 5 | 2024-03-22 | 2024-03-27 | Parents can see their complete order history | 15000 | Order history feature completed | Development Team
WBS-003.3 | Build Supply Suggestions System | Develop a suggestion system based on the parent’s child schedule | Development | UR-007 | Supply suggestions | 13000 | Supply suggestion module | 5 | 2024-03-28 | 2024-04-02 | Parents receive useful supply suggestions based on their child’s needs | 13000 | Supply suggestion feature completed | Development Team
WBS-003.4 | Test and Deploy Parent Dashboard | Test the functionality of the parent dashboard and deploy to production | Testing | UR-007 | Testing and deployment | 10000 | Parent dashboard tested and deployed | 3 | 2024-04-03 | 2024-04-06 | All features function correctly, dashboard is live | 10000 | Parent dashboard live | QA & Development Teams
WBS-004 | Secure Payment Integration | Integrate payment gateway for secure checkout | Development | FR-005, NFR-003 | Payment processing | 60000 | Payment gateway and encryption | 12 | 2024-04-01 | 2024-04-13 | Secure payment is processed, and data is encrypted in transit and at rest | 60000 | Payment integration completed | Development Team
WBS-004.1 | Design Checkout UI | Create a checkout interface for parents | Development | FR-005 | Checkout UI design | 15000 | User-friendly checkout interface | 4 | 2024-04-01 | 2024-04-05 | Checkout UI is intuitive and easy to use | 15000 | Checkout UI completed | UI/UX Team
WBS-004.2 | Integrate Payment Gateway | Set up and integrate multiple payment options | Development | FR-005 | Payment gateway integration | $
WBS-004 | Secure Payment Integration | Integrate payment gateway for secure checkout | Development | FR-005, NFR-003 | Payment processing | 60000 | Payment gateway and encryption | 12 | 2024-04-01 | 2024-04-13 | Secure payment is processed, and data is encrypted in transit and at rest | 60000 | Payment integration completed | Development Team
WBS-004.1 | Design Checkout UI | Create a checkout interface for parents | Development | FR-005 | Checkout UI design | 15000 | User-friendly checkout interface | 4 | 2024-04-01 | 2024-04-05 | Checkout UI is intuitive and easy to use | 15000 | Checkout UI completed | UI/UX Team
WBS-004.2 | Integrate Payment Gateway | Set up and integrate multiple payment options | Development | FR-005 | Payment gateway integration | 20000 | Payment gateway (PayPal, credit cards) | 5 | 2024-04-06 | 2024-04-10 | Payments can be processed securely with multiple methods | 20000 | Payment gateway integrated | Development Team
WBS-004.3 | Implement Data Encryption | Encrypt payment details and sensitive information during checkout | Development | NFR-003 | Data encryption | 15000 | Encrypted payment data | 3 | 2024-04-11 | 2024-04-13 | All sensitive payment data is encrypted in transit and at rest | 15000 | Data encryption completed | Security Team
WBS-004.4 | Test and Deploy Payment System | Test the payment system and ensure compliance with PCI DSS | Testing | NFR-003 | Payment system testing | 10000 | Payment system tested and deployed | 2 | 2024-04-14 | 2024-04-15 | No critical issues found during testing, payment system is live | 10000 | Payment system deployed | QA & Development Teams
WBS-005 | Product Comparison Tool | Develop a tool to allow users to compare products before purchase | Development | FR-021, FR-014 | Product comparison | 35000 | Comparison interface | 10 | 2024-04-06 | 2024-04-16 | Users can compare products based on price, supplier, and reviews | 35000 | Product comparison feature completed | Development Team
WBS-005.1 | Design Comparison Tool UI | Design the user interface for comparing products side-by-side | Development | FR-021 | UI design for product comparison | 10000 | Comparison tool UI design | 4 | 2024-04-06 | 2024-04-09 | Users can intuitively compare products via a well-designed interface | 10000 | UI design completed | UI/UX Team
WBS-005.2 | Build Comparison Engine | Develop the back-end system for comparing product features, pricing, and ratings | Development | FR-021 | Comparison engine | 15000 | Product comparison logic implemented | 4 | 2024-04-10 | 2024-04-13 | Product data is retrieved accurately and comparisons are processed correctly | 15000 | Comparison engine built | Back-End Development Team
WBS-005.3 | Implement Sorting and Filters | Add sorting and filtering functionality to allow users to refine their comparisons | Development | FR-014 | Sorting and filtering tools | 5000 | Sorting and filtering functionality | 2 | 2024-04-14 | 2024-04-15 | Users can sort and filter products based on criteria such as price, rating, etc. | 5000 | Sorting and filtering tools completed | Development Team
WBS-005.4 | Test and Deploy Comparison Tool | Perform functionality and usability testing, then deploy the comparison tool | Testing | FR-021 | Testing and deployment | 5000 | Comparison tool tested and deployed | 2 | 2024-04-16 | 2024-04-17 | Comparison tool works correctly without any critical bugs | 5000 | Comparison tool deployed | QA & Development Teams
WBS-006 | Order Tracking System | Implement order tracking system for parents | Development | UR-006, FR-003 | Real-time order status | 45000 | Order tracking page | 14 | 2024-03-17 | 2024-03-31 | Parents can track their orders in real-time | 45000 | Order tracking feature deployment | Development Team
WBS-006.1 | Design Order Tracking UI | Design the interface for tracking orders | Development | UR-006 | UI design for order tracking | 12000 | Order tracking UI | 5 | 2024-03-17 | 2024-03-21 | UI design allows parents to track their orders easily | 12000 | Order tracking UI completed | UI/UX Team
WBS-006.2 | Build Order Tracking Engine | Build the back-end logic to fetch and display real-time order status | Development | FR-003 | Order tracking logic | 20000 | Real-time order tracking functionality | 6 | 2024-03-22 | 2024-03-28 | Real-time order statuses are fetched accurately and displayed to the user | 20000 | Order tracking logic completed | Back-End Development Team
WBS-006.3 | Test and Deploy Order Tracking | Test the real-time functionality and deploy | Testing | UR-006 | Testing and deployment | 13000 | Order tracking system tested and deployed | 3 | 2024-03-29 | 2024-03-31 | No issues found during testing, and the system is deployed to production | 13000 | Order tracking system deployed | QA & Development Teams
WBS-007 | AI-Powered Supply Prediction | Implement AI tool to predict future supply needs based on historical data | Development | TR-015 | AI-powered predictions | 100000 | AI-powered prediction tool | 30 | 2024-04-05 | 2024-05-05 | Admins receive accurate predictions based on past data | 100000 | AI prediction system deployment | AI & Development Team
WBS-007.1 | Data Collection and Analysis | Collect historical supply data and analyze trends for AI training | Development | TR-015 | Data collection and analysis | 30000 | Historical data ready for AI training | 10 | 2024-04-05 | 2024-04-15 | Sufficient historical data is collected and analyzed | 30000 | Data collection completed | Data Science Team
WBS-007.2 | AI Model Training | Train AI model using the historical data to predict future supply needs | Development | TR-015 | AI model training | 40000 | Trained AI model | 15 | 2024-04-16 | 2024-05-01 | AI model predicts future supply needs accurately | 40000 | AI model trained | AI Team
WBS-007.3 | Integrate AI Model with Platform | Integrate the AI model with the main platform to display predictions | Development | TR-015 | AI platform integration | 20000 | AI model integrated into the platform | 5 | 2024-05-02 | 2024-05-07 | Predictions are displayed in the admin dashboard | 20000 | AI model integration completed | AI & Development Teams
WBS-007.4 | Test and Optimize AI Predictions | Test the accuracy of AI predictions and optimize the model as needed | Testing | TR-015 | AI testing and optimization | 10000 | AI predictions tested and optimized | 5 | 2024-05-08 | 2024-05-12 | Predictions are accurate, and the system is optimized | 10000 | AI testing completed | AI & QA Teams
WBS-008 | Role-Based Access Control | Implement a multi-user role system for different users | Development | BR-004, UR-003 | Role-based access | 55000 | Multi-user role access system | 14 | 2024-03-25 | 2024-04-08 | Admins can assign roles with specific permissions | 55000 | Role-based access control completed | Development Team
WBS-008.1 | Define User Roles and Permissions | Define roles and access levels for different types of users (admin, parent, etc.) | Planning | BR-004 | User roles and permissions | 10000 | Role definitions and access rules | 4 | 2024-03-25 | 2024-03-28 | Clear roles and permissions are defined for all user types | 10000 | Roles and permissions defined | Project Management Team
WBS-008.2 | Build Access Control System | Implement the back-end system to manage role-based access | Development | UR-003 | Access control back-end | 30000 | Role-based access system | 8 | 2024-03-29 | 2024-04-06 | Roles and permissions are enforced correctly across the system | 30000 | Access control system completed | Back-End Development Team
WBS-008.3 | Integrate with Front-End | Integrate role-based access control with the front-end interface | Development | UR-003 | Front-end access control | 10000 | Role-based access on the UI | 4 | 2024-04-02 | 2024-04-07 | The front-end correctly reflects role-based access restrictions | 10000 | UI integration completed | Front-End Development Team
WBS-008.4 | Test and Deploy Access Control | Test role-based access functionality and deploy to the live system | Testing | UR-003 | Testing and deployment | 5000 | Role-based access control tested and deployed | 3 | 2024-04-08 | 2024-04-10 | No critical issues found, and access control is working properly | 5000 | Access control system deployed | QA & Development Teams
WBS-009 | In-App Chat Support | Implement real-time chat support for users | Development | UR-016 | Real-time chat interface | 25000 | Chat support interface | 8 | 2024-03-29 | 2024-04-06 | Users can communicate with support in real-time for order-related issues | 25000 | In-app chat feature completed | Development Team
WBS-009.1 | Design Chat UI | Design the user interface for the in-app chat system | Development | UR-016 | Chat UI design | 10000 | Chat UI ready | 3 | 2024-03-29 | 2024-04-01 | UI is intuitive and user-friendly for real-time chat | 10000 | Chat UI design completed | UI/UX Team
WBS-009.2 | Implement Chat Back-End | Build the back-end infrastructure for handling chat messages and support tickets | Development | UR-016 | Chat back-end | 10000 | Chat back-end system | 4 | 2024-04-02 | 2024-04-05 | Messages are delivered in real-time, and support agents can respond | 10000 | Chat back-end completed | Back-End Development Team
WBS-009.3 | Test and Deploy Chat System | Test the in-app chat system and deploy to production | Testing | UR-016 | Chat testing and deployment | 5000 | Chat system tested and deployed | 1 | 2024-04-06 | 2024-04-06 | No issues during testing, chat system is live | 5000 | Chat system deployed | QA & Development Teams
WBS-010 | Bulk Ordering System | Enable bulk ordering functionality for admins | Development | FR-007 | Bulk ordering for schools | 50000 | Bulk ordering system | 12 | 2024-04-02 | 2024-04-14 | Admins can place bulk orders for multiple supplies | 50000 | Bulk ordering system deployment | Development Team
WBS-010.1 | Design Bulk Ordering UI | Design user interface for bulk order placement | Development | FR-007 | UI for bulk orders | 10000 | UI design for bulk orders | 4 | 2024-04-02 | 2024-04-06 | Bulk order UI is user-friendly and intuitive | 10000 | Bulk ordering UI completed | UI/UX Team
WBS-010.2 | Build Bulk Ordering Back-End | Develop the back-end system for managing bulk orders | Development | FR-007 | Bulk ordering back-end | 20000 | Bulk ordering back-end system | 6 | 2024-04-07 | 2024-04-12 | The back-end system processes and manages bulk orders efficiently | 20000 | Back-end system completed | Back-End Development Team
WBS-010.3 | Test and Deploy Bulk Ordering | Test the bulk ordering functionality and deploy | Testing | FR-007 | Bulk ordering testing | 10000 | Bulk ordering system tested and deployed | 2 | 2024-04-13 | 2024-04-14 | No issues during testing, and system is deployed to production | 10000 | Bulk ordering system deployed | QA & Development Teams
WBS-010.4 | Add Bulk Discounts Integration | Integrate bulk discounts for certain order quantities | Development | FR-007 | Bulk discount management | 10000 | Bulk discounts feature | 4 | 2024-04-13 | 2024-04-17 | Discounts are automatically applied to bulk orders based on quantity | 10000 | Bulk discount feature completed | Development Team
WBS-011 | Product Search and Filter | Create a product search system with filters | Development | FR-008, FR-014 | Product search and filtering | 35000 | Product search system | 12 | 2024-04-10 | 2024-04-22 | Users can search and filter products based on category, price, and supplier | 35000 | Product search system completed | Development Team
WBS-011.1 | Design Product Search UI | Create an intuitive interface for product search and filters | Development | FR-008 | UI for search and filters | 10000 | Search and filter UI | 4 | 2024-04-10 | 2024-04-14 | Users can easily navigate the search and apply filters | 10000 | Product search UI completed | UI/UX Team
WBS-011.2 | Implement Search Engine | Build the search engine that fetches products based on queries | Development | FR-008 | Search engine implementation | 15000 | Functional search engine | 6 | 2024-04-15 | 2024-04-21 | The search engine accurately retrieves products from the database | 15000 | Search engine completed | Back-End Development Team
WBS-011.3 | Add Filtering Options | Add various filter options like price, supplier, and category | Development | FR-014 | Filters for search | 10000 | Filter system | 2 | 2024-04-22 | 2024-04-23 | Filters work seamlessly and narrow down search results | 10000 | Filter system completed | Development Team
WBS-011.4 | Test and Deploy Search System | Test the search and filter functionality and deploy to production | Testing | FR-008 | Testing and deployment | 5000 | Search system tested and deployed | 2 | 2024-04-24 | 2024-04-25 | Search and filter functionality works as intended | 5000 | Product search system deployed | QA & Development Teams
WBS-012 | Reports Dashboard (Admin) | Develop reporting tools for admins to view supplier performance and spending | Development | FR-011, BR-008 | Reporting tools for admins | 70000 | Admin reports dashboard | 20 | 2024-04-15 | 2024-05-05 | Admins can view reports on supplier performance and inventory spending | 70000 | Reporting tools completed | Development Team
WBS-012.1 | Design Reports Dashboard UI | Design a user-friendly interface for the admin reports dashboard | Development | FR-011 | UI design for reports | 20000 | Admin reports UI | 6 | 2024-04-15 | 2024-04-21 | Admins can easily navigate the reports dashboard and generate reports | 20000 | Reports dashboard UI completed | UI/UX Team
WBS-012.2 | Implement Report Generation | Develop the back-end system for generating and downloading reports | Development | FR-011 | Report generation logic | 30000 | Report generation functionality | 10 | 2024-04-22 | 2024-05-01 | Reports are generated based on selected criteria, and they are downloadable | 30000 | Report generation system completed | Back-End Development Team
WBS-012.3 | Integrate with Supplier Data | Integrate supplier performance metrics into the report generation system | Development | BR-008 | Supplier data integration | 10000 | Supplier data integrated into reports | 4 | 2024-05-02 | 2024-05-05 | Supplier performance metrics are correctly reflected in the generated reports | 10000 | Supplier data integration completed | Development Team
WBS-012.4 | Test and Deploy Reports Dashboard | Test the reporting functionality and deploy the dashboard | Testing | FR-011 | Testing and deployment | 10000 | Reports dashboard tested and deployed | 4 | 2024-05-06 | 2024-05-09 | No critical issues found, reports are accurate and downloadable | 10000 | Reports dashboard deployed | QA & Development Teams
WBS-013 | Notifications and Alerts | Implement a notification system for order updates and inventory alerts | Development | UR-007, FR-004 | Notifications and alerts | 30000 | Real-time notifications | 10 | 2024-03-21 | 2024-03-31 | Users receive notifications on order updates and low-stock inventory alerts | 30000 | Notification system deployment | Development Team
WBS-013.1 | Design Notification UI | Design the user interface for displaying notifications and alerts | Development | UR-007 | Notification UI | 10000 | Notification UI | 3 | 2024-03-21 | 2024-03-24 | The UI is clear and shows notifications for orders, inventory, and offers | 10000 | Notification UI design completed | UI/UX Team
WBS-013.2 | Implement Notification Logic | Develop the back-end logic for sending real-time notifications | Development | FR-004 | Notification logic | 10000 | Notification logic implemented | 5 | 2024-03-25 | 2024-03-29 | The system sends real-time notifications to users when order status or stock changes | 10000 | Notification system implemented | Back-End Development Team
WBS-013.3 | Set Up Push Notifications | Enable push notifications for mobile users | Development | NFR-018 | Mobile push notifications | 5000 | Push notification system | 2 | 2024-03-30 | 2024-03-31 | Mobile users receive push notifications for order updates, low stock alerts, and offers | 5000 | Push notification system completed | Mobile Development Team
WBS-013.4 | Test and Deploy Notification System | Test the notification system and deploy it | Testing | FR-004 | Testing and deployment | 5000 | Notification system tested and deployed | 2 | 2024-04-01 | 2024-04-02 | All notifications work properly across platforms, and users receive updates | 5000 | Notification system deployed | QA & Development Teams
WBS-014 | Supplier Product Management | Develop a system for suppliers to manage their products | Development | UR-012 | Supplier product management | 40000 | Product management system | 15 | 2024-04-15 | 2024-04-30 | Suppliers can add, edit, and delete products and manage stock availability | 40000 | Supplier product management completed | Development Team
WBS-014.1 | Design Supplier Product UI | Design the interface for suppliers to manage their products | Development | UR-012 | Supplier product management UI | 12000 | Supplier product UI | 5 | 2024-04-15 | 2024-04-20 | Suppliers can easily navigate the interface to manage their products | 12000 | Supplier product UI completed | UI/UX Team
WBS-014.2 | Build Product Management Back-End | Develop the back-end system for product upload, editing, and deletion | Development | UR-012 | Product management back-end | 20000 | Back-end product management system | 7 | 2024-04-21 | 2024-04-28 | Suppliers can add, update, and delete products in the system | 20000 | Product management back-end completed | Back-End Development Team
WBS-014.3 | Implement Stock Level Management | Integrate stock level monitoring to allow suppliers to manage availability | Development | UR-012 | Stock level monitoring | 8000 | Stock level management feature | 3 | 2024-04-29 | 2024-04-30 | Suppliers can monitor and manage stock levels and adjust availability | 8000 | Stock level management completed | Development Team
WBS-014.4 | Test and Deploy Product Management | Test the product management system and deploy | Testing | UR-012 | Testing and deployment | 5000 | Product management system tested and deployed | 3 | 2024-05-01 | 2024-05-03 | The product management system is fully functional and deployed to production | 5000 | Product management system deployed | QA & Development Teams
WBS-015 | Multi-Language Support | Implement support for multiple languages (English, French, Spanish) | Development | NFR-004 | Multi-language options | 20000 | Multi-language support | 8 | 2024-04-20 | 2024-04-28 | Users can switch the app to their preferred language | 20000 | Multi-language support completed | Development Team
WBS-015.1 | Language Selection UI | Design the UI for language selection | Development | NFR-004 | UI for language options | 5000 | Language selection UI | 2 | 2024-04-20 | 2024-04-22 | Users can select their preferred language through a simple, intuitive interface | 5000 | Language selection UI completed | UI/UX Team
WBS-015.2 | Translation and Localization | Translate and localize the app content for English, French, and Spanish | Development | NFR-004 | Localization and translation | 10000 | Translated content for all languages | 4 | 2024-04-23 | 2024-04-26 | All content is accurately translated and localized for the respective languages | 10000 | Content localization completed | Localization Team
WBS-015.3 | Integrate Multi-Language Back-End | Implement the logic to switch languages dynamically in the back-end | Development | NFR-004 | Multi-language back-end integration | 5000 | Multi-language back-end functionality | 2 | 2024-04-27 | 2024-04-28 | Users can switch between languages seamlessly without any issues | 5000 | Multi-language integration completed | Development Team
WBS-015.4 | Test and Deploy Multi-Language | Test the multi-language functionality and deploy | Testing | NFR-004 | Testing and deployment | 5000 | Multi-language support tested and deployed | 2 | 2024-04-29 | 2024-04-30 | All language options are functional, and the app operates smoothly in all languages | 5000 | Multi-language support deployed | QA & Development Teams
WBS-016 | Product Wishlist/Favorites | Enable parents to save items to a wishlist for future purchases | Development | UR-012 | Wishlist functionality | 25000 | Wishlist feature | 10 | 2024-04-22 | 2024-05-02 | Parents can save items to a wishlist and move them to the cart later | 25000 | Wishlist system deployment | Development Team
WBS-016.1 | Design Wishlist UI | Create an intuitive interface for adding items to the wishlist | Development | UR-012 | Wishlist UI | 8000 | Wishlist UI | 3 | 2024-04-22 | 2024-04-25 | The UI is user-friendly and allows parents to add items to the wishlist easily | 8000 | Wishlist UI completed | UI/UX Team
WBS-016.2 | Build Wishlist Back-End | Develop the back-end system for storing and retrieving wishlist items | Development | UR-012 | Wishlist back-end | 12000 | Wishlist back-end | 5 | 2024-04-26 | 2024-05-01 | Parents' wishlist items are stored and retrieved correctly from the database | 12000 | Wishlist back-end completed | Back-End Development Team
WBS-016.3 | Integrate with Cart System | Integrate wishlist functionality with the cart to allow easy item movement | Development | UR-012 | Wishlist and cart integration | 5000 | Wishlist-to-cart integration | 2 | 2024-05-01 | 2024-05-02 | Items can be moved from wishlist to cart with a single click | 5000 | Wishlist-cart integration completed | Development Team
WBS-016.4 | Test and Deploy Wishlist Feature | Test wishlist functionality and deploy | Testing | UR-012 | Testing and deployment | 5000 | Wishlist system tested and deployed | 2 | 2024-05-03 | 2024-05-05 | Wishlist feature is fully functional, and items are correctly stored and retrieved | 5000 | Wishlist system deployed | QA & Development Teams
WBS-017 | Data Encryption for Security | Implement encryption for sensitive data such as payment and personal info | Development | NFR-003, TR-013 | Data encryption | 50000 | Data encryption system | 14 | 2024-04-25 | 2024-05-09 | Sensitive data is encrypted in transit and at rest | 50000 | Encryption system completed | Development Team
WBS-017.1 | Encrypt Payment Data | Implement encryption for payment data in transit and at rest | Development | NFR-003 | Payment data encryption | 20000 | Encrypted payment data | 6 | 2024-04-25 | 2024-05-01 | All payment data is encrypted end-to-end | 20000 | Payment data encryption completed | Security & Development Team
WBS-017.2 | Encrypt Personal Information | Encrypt personal information such as names, addresses, and payment details | Development | TR-013 | Personal info encryption | 20000 | Encrypted personal data | 6 | 2024-05-02 | 2024-05-08 | Personal data is encrypted in the database and while in transit | 20000 | Personal data encryption completed | Security Team
WBS-017.3 | Test and Deploy Encryption System | Test the encryption system for security vulnerabilities and deploy | Testing | NFR-003 | Encryption system testing | 10000 | Encryption system tested and deployed | 2 | 2024-05-09 | 2024-05-10 | No vulnerabilities found, encryption system deployed to production | 10000 | Encryption system deployed | QA & Security Teams
WBS-018 | Recurring Orders Setup (Parent) | Enable parents to set up recurring orders for frequently used supplies | Development | UR-014 | Recurring order setup | 30000 | Recurring order system | 12 | 2024-05-01 | 2024-05-13 | Parents can set up and manage recurring orders for selected products | 30000 | Recurring order system completed | Development Team
WBS-018.1 | Design Recurring Order UI | Design the interface for parents to set up recurring orders | Development | UR-014 | Recurring order UI | 10000 | UI for recurring order setup | 4 | 2024-05-01 | 2024-05-05 | The UI allows users to set frequency, start dates, and edit recurring orders | 10000 | Recurring order UI completed | UI/UX Team
WBS-018.2 | Build Recurring Order Back-End | Develop the back-end logic to handle recurring order scheduling and processing | Development | UR-014 | Back-end for recurring orders | 15000 | Recurring order back-end | 6 | 2024-05-06 | 2024-05-11 | The system processes recurring orders automatically based on user preferences | 15000 | Recurring order back-end completed | Back-End Development Team
WBS-018.3 | Test and Deploy Recurring Order | Test the recurring order system and deploy | Testing | UR-014 | Recurring order testing | 5000 | Recurring order system tested and deployed | 2 | 2024-05-12 | 2024-05-13 | Recurring order functionality works without issues and is deployed to production | 5000 | Recurring order system deployed | QA & Development Teams
WBS-019 | Admin Multi-Location Dashboard | Develop a dashboard for administrators managing multiple schools/locations | Development | UR-013 | Multi-location management | 50000 | Multi-location admin dashboard | 14 | 2024-06-10 | 2024-06-24 | Admins can toggle between different locations and view specific metrics | 50000 | Multi-location dashboard completed | Development Team
WBS-019.1 | Design Location Selection UI | Design the user interface for admins to select and toggle between multiple locations | Development | UR-013 | UI for location selection | 15000 | Location selection UI | 5 | 2024-06-10 | 2024-06-15 | Admins can easily toggle between different schools or locations | 15000 | Location selection UI completed | UI/UX Team
WBS-019.2 | Implement Location Data Tracking | Develop the back-end system to track and report on data from different locations | Development | UR-013 | Location data tracking | 20000 | Location-based tracking and reports | 6 | 2024-06-16 | 2024-06-21 | Location data is correctly tracked and reflected in the dashboard | 20000 | Location data tracking completed | Back-End Development Team
WBS-019.3 | Test and Deploy Multi-Location Dashboard | Test the dashboard functionality and deploy | Testing | UR-013 | Testing and deployment | 15000 | Multi-location dashboard tested and deployed | 3 | 2024-06-22 | 2024-06-24 | Admins can successfully manage multiple locations from the dashboard | 15000 | Multi-location dashboard deployed | QA & Development Teams
WBS-020 | Voice-Assisted Search | Implement voice command functionality for searching supplies | Development | UR-015 | Voice-enabled search | 35000 | Voice search feature | 14 | 2024-06-25 | 2024-07-09 | Users can search for supplies using voice commands | 35000 | Voice search feature completed | Development Team
WBS-020.1 | Design Voice Search UI | Create the user interface for voice-enabled search | Development | UR-015 | UI for voice search | 10000 | Voice search UI | 5 | 2024-06-25 | 2024-06-30 | The UI includes a microphone icon and voice command instructions | 10000 | Voice search UI completed | UI/UX Team
WBS-020.2 | Build Voice Recognition Back-End | Implement the back-end system to process voice commands | Development | UR-015 | Voice recognition system | 15000 | Back-end system for voice commands | 7 | 2024-07-01 | 2024-07-08 | Voice commands are processed correctly, and search results are returned | 15000 | Voice recognition back-end completed | Back-End Development Team
WBS-020.3 | Test and Deploy Voice Search | Test the voice search feature and deploy | Testing | UR-015 | Testing and deployment | 10000 | Voice search system tested and deployed | 3 | 2024-07-09 | 2024-07-11 | Voice search is functional without issues, and the feature is deployed | 10000 | Voice search system deployed | QA & Development Teams
WBS-021 | Automatic Server Scaling | Implement automatic scaling for cloud infrastructure to handle traffic spikes | Development | TR-016 | Server scaling for traffic spikes | 70000 | Auto-scaling infrastructure | 18 | 2024-07-10 | 2024-07-28 | Servers automatically scale based on traffic load | 70000 | Auto-scaling system completed | IT & Cloud Infrastructure Team
WBS-021.1 | Set Up Cloud Infrastructure | Set up the scalable cloud infrastructure (AWS, Azure, etc.) | Development | TR-016 | Cloud infrastructure setup | 30000 | Cloud servers ready | 8 | 2024-07-10 | 2024-07-18 | The cloud servers are set up and configured to handle traffic spikes | 30000 | Cloud infrastructure set up | IT Team
WBS-021.2 | Implement Auto-Scaling Rules | Create the rules and logic for automatic server scaling based on usage patterns | Development | TR-016 | Auto-scaling rules implemented | 30000 | Auto-scaling rules | 8 | 2024-07-19 | 2024-07-27 | Servers scale automatically based on predefined thresholds | 30000 | Auto-scaling logic completed | IT & Development Teams
WBS-021.3 | Test and Monitor Auto-Scaling | Test auto-scaling under high traffic scenarios and monitor performance | Testing | TR-016 | Testing and monitoring | 10000 | Auto-scaling system tested and monitored | 3 | 2024-07-28 | 2024-07-30 | Auto-scaling works as expected without disruptions | 10000 | Auto-scaling system deployed | QA & IT Teams
WBS-022 | Supplier Performance Evaluation | Create a system for schools to evaluate and rate supplier performance | Development | BR-007, FR-006 | Supplier performance metrics | 45000 | Supplier evaluation tool | 14 | 2024-07-15 | 2024-07-29 | Schools can evaluate suppliers based on delivery time, product quality, etc. | 45000 | Supplier evaluation tool completed | Development Team
WBS-022.1 | Design Supplier Evaluation UI | Create the interface for rating and reviewing suppliers | Development | BR-007 | Supplier evaluation UI | 10000 | Evaluation interface for suppliers | 5 | 2024-07-15 | 2024-07-20 | The interface allows users to submit ratings and reviews for suppliers | 10000 | Supplier evaluation UI completed | UI/UX Team
WBS-022.2 | Build Evaluation Metrics System | Implement the back-end logic for collecting and processing evaluation data | Development | FR-006 | Evaluation back-end | 20000 | Supplier evaluation system | 7 | 2024-07-21 | 2024-07-27 | Evaluation data is stored securely and accessible for reporting | 20000 | Evaluation metrics system completed | Back-End Development Team
WBS-022.3 | Test and Deploy Supplier Evaluation System | Test the evaluation system and deploy | Testing | BR-007 | Testing and deployment | 15000 | Evaluation system tested and deployed | 3 | 2024-07-28 | 2024-07-30 | No critical issues found, and the system is fully functional | 15000 | Evaluation system deployed | QA & Development Teams
WBS-023 | Vendor Feedback and Rating System | Allow parents and schools to provide feedback and rate vendors | Development | BR-012 | Feedback and rating system | 35000 | Vendor feedback tool | 10 | 2024-07-30 | 2024-08-10 | Parents and schools can leave feedback and rate vendors | 35000 | Vendor feedback tool completed | Development Team
WBS-023.1 | Design Feedback and Rating UI | Design the user interface for leaving feedback and rating vendors | Development | BR-012 | Feedback and rating UI | 10000 | UI for vendor feedback | 4 | 2024-07-30 | 2024-08-03 | The UI allows users to rate vendors and leave detailed feedback | 10000 | Feedback UI completed | UI/UX Team
WBS-023.2 | Implement Rating System Logic | Build the logic for capturing and calculating vendor ratings | Development | BR-012 | Rating system logic | 15000 | Vendor rating system | 5 | 2024-08-04 | 2024-08-09 | Ratings are processed and displayed correctly on vendor profiles | 15000 | Rating system completed | Back-End Development Team
WBS-023.3 | Test and Deploy Feedback System | Test the vendor feedback system and deploy | Testing | BR-012 | Testing and deployment | 10000 | Vendor feedback system tested and deployed | 2 | 2024-08-10 | 2024-08-11 | Feedback system works as expected, and all ratings are visible | 10000 | Vendor feedback system deployed | QA & Development Teams
WBS-024 | Custom Reporting Tool | Create a reporting tool for admins to generate custom reports based on criteria | Development | FR-012 | Custom report generation | 45000 | Custom reporting tool | 12 | 2024-08-01 | 2024-08-13 | Admins can create custom reports based on date, supplier, category, etc. | 45000 | Custom reporting tool completed | Development Team
WBS-024.1 | Design Custom Report UI | Design the interface for custom report generation | Development | FR-012 | Custom report UI | 15000 | Custom report UI | 5 | 2024-08-01 | 2024-08-06 | The UI allows admins to select report criteria and generate reports | 15000 | Custom report UI completed | UI/UX Team
WBS-024.2 | Implement Report Generation Logic | Build the logic for generating reports based on selected criteria | Development | FR-012 | Report generation logic | 20000 | Custom report generation system | 5 | 2024-08-07 | 2024-08-12 | Reports are generated based on criteria like date, department, and suppliers | 20000 | Report generation system completed | Back-End Development Team
WBS-024.3 | Test and Deploy Custom Report Tool | Test the custom reporting tool and deploy | Testing | FR-012 | Testing and deployment | 10000 | Custom reporting tool tested and deployed | 2 | 2024-08-13 | 2024-08-15 | Custom reports are generated without issues, and the tool is deployed | 10000 | Custom reporting tool deployed | QA & Development Teams
WBS-025 | Loyalty Programs for User Retention | Implement a loyalty program to increase user retention | Development | BR-011 | Loyalty programs | 50000 | Loyalty program feature | 14 | 2024-08-10 | 2024-08-24 | Parents and admins earn loyalty points for frequent purchases | 50000 | Loyalty program deployed | Development Team
WBS-025.1 | Design Loyalty Program UI | Design the interface for users to view and redeem loyalty points | Development | BR-011 | Loyalty program UI | 15000 | Loyalty program UI | 5 | 2024-08-10 | 2024-08-15 | The UI allows users to track points, view offers, and redeem rewards | 15000 | Loyalty program UI completed | UI/UX Team
WBS-025.2 | Build Loyalty Points System | Implement the back-end system to track and accumulate loyalty points | Development | BR-011 | Loyalty points tracking system | 20000 | Loyalty points system | 7 | 2024-08-16 | 2024-08-22 | Loyalty points are tracked, and users can redeem points | 20000 | Loyalty points system completed | Back-End Development Team
WBS-025.3 | Integrate Loyalty Offers and Rewards | Implement the logic for redeeming loyalty points for offers and rewards | Development | BR-011 | Offer and reward integration | 10000 | Offers and rewards feature | 5 | 2024-08-16 | 2024-08-21 | Users can redeem loyalty points for discounts, offers, or rewards | 10000 | Offers and rewards feature completed | Development Team
WBS-025.4 | Test and Deploy Loyalty Program | Test the loyalty program system and deploy | Testing | BR-011 | Testing and deployment | 5000 | Loyalty program tested and deployed | 2 | 2024-08-23 | 2024-08-24 | Loyalty program functions correctly, and users can redeem points without issues | 5000 | Loyalty program deployed | QA & Development Teams
WBS-026 | Order Splitting Across Suppliers | Implement the ability to split orders across multiple suppliers based on availability and pricing | Development | FR-022 | Order splitting across suppliers | 40000 | Order splitting feature | 10 | 2024-08-20 | 2024-08-30 | Orders are automatically split across suppliers based on availability and best pricing | 40000 | Order splitting system completed | Development Team
WBS-026.1 | Design Order Splitting UI | Create the interface to show split orders across suppliers | Development | FR-022 | Order splitting UI | 12000 | Order splitting UI | 4 | 2024-08-20 | 2024-08-24 | Users can view how orders are split across multiple suppliers | 12000 | Order splitting UI completed | UI/UX Team
WBS-026.2 | Implement Splitting Logic | Build the back-end logic for splitting orders based on supplier availability and pricing | Development | FR-022 | Order splitting logic | 20000 | Order splitting functionality | 6 | 2024-08-25 | 2024-08-30 | Orders are split correctly and processed by different suppliers | 20000 | Order splitting logic completed | Back-End Development Team
WBS-026.3 | Test and Deploy Order Splitting System | Test the order splitting system and deploy | Testing | FR-022 | Testing and deployment | 8000 | Order splitting system tested and deployed | 2 | 2024-09-01 | 2024-09-02 | The order splitting system works as expected and is deployed to production | 8000 | Order splitting system deployed | QA & Development Teams
WBS-027 | Discount and Promotions Feature | Implement a feature allowing suppliers to offer discounts and promotions | Development | FR-014 | Discounts and promotions for suppliers | 35000 | Discount and promotion feature | 12 | 2024-08-28 | 2024-09-09 | Suppliers can create discounts and promotions that are visible to parents and admins | 35000 | Discounts and promotions feature deployed | Development Team
WBS-027.1 | Design Discounts UI | Create the interface for displaying and managing discounts and promotions | Development | FR-014 | Discounts and promotions UI | 10000 | Discounts and promotions UI | 4 | 2024-08-28 | 2024-09-01 | The UI displays supplier discounts and promotions clearly | 10000 | Discounts UI completed | UI/UX Team
WBS-027.2 | Build Discount Logic | Develop the logic to create, manage, and apply discounts and promotions | Development | FR-014 | Discounts logic | 15000 | Discount and promotion management system | 6 | 2024-09-02 | 2024-09-08 | Discounts and promotions can be created and managed by suppliers | 15000 | Discount logic completed | Back-End Development Team
WBS-027.3 | Test and Deploy Discounts Feature | Test the discount and promotion feature and deploy | Testing | FR-014 | Testing and deployment | 10000 | Discount system tested and deployed | 2 | 2024-09-09 | 2024-09-11 | Discounts and promotions work as expected, and the feature is deployed | 10000 | Discount system deployed | QA & Development Teams
WBS-028 | Shopping Cart and Checkout System | Implement the shopping cart and secure checkout system | Development | FR-008, FR-016 | Shopping cart and checkout | 60000 | Shopping cart and checkout feature | 20 | 2024-09-10 | 2024-09-30 | Parents can add items to the cart and proceed through a secure checkout process | 60000 | Shopping cart and checkout deployed | Development Team
WBS-028.1 | Design Shopping Cart UI | Create the interface for the shopping cart, including item details, quantity selection, and cart total | Development | FR-008 | Shopping cart UI | 15000 | Shopping cart UI | 6 | 2024-09-10 | 2024-09-16 | The UI allows users to view cart items, edit quantities, and see the total amount | 15000 | Shopping cart UI completed | UI/UX Team
WBS-028.2 | Build Secure Checkout Logic | Implement the back-end logic for processing orders through secure checkout | Development | FR-016 | Secure checkout logic | 30000 | Secure checkout system | 10 | 2024-09-17 | 2024-09-27 | Orders are processed securely, and payment methods are handled safely | 30000 | Secure checkout logic completed | Back-End Development Team
WBS-028.3 | Test and Deploy Shopping Cart | Test the shopping cart and secure checkout process | Testing | FR-008, FR-016 | Testing and deployment | 15000 | Shopping cart and checkout system tested and deployed | 3 | 2024-09-28 | 2024-09-30 | No issues found during testing, and the shopping cart and checkout system are live | 15000 | Shopping cart and checkout system deployed | QA & Development Teams
WBS-029 | AI-Powered Supply Prediction Tool | Develop an AI-based tool to predict future supply needs based on historical usage | Development | TR-015 | AI-driven supply prediction | 55000 | AI-powered supply prediction system | 18 | 2024-10-01 | 2024-10-18 | Schools and parents receive accurate supply predictions based on historical trends | 55000 | AI prediction system completed | AI & Development Teams
WBS-029.1 | Data Collection and Model Training | Collect historical data and train the AI model for accurate supply predictions | Development | TR-015 | Data collection and AI training | 20000 | Trained AI model | 7 | 2024-10-01 | 2024-10-08 | AI model is trained with sufficient data to generate accurate predictions | 20000 | AI model training completed | Data Science & AI Teams
WBS-029.2 | Build Prediction Engine | Build the back-end system to generate supply predictions using AI | Development | TR-015 | Prediction engine | 20000 | Supply prediction engine | 7 | 2024-10-09 | 2024-10-16 | Predictions are generated based on historical usage and are accurate | 20000 | Prediction engine completed | Back-End Development Team
WBS-029.3 | Test and Deploy Prediction Tool | Test the AI prediction tool and deploy it to production | Testing | TR-015 | Testing and deployment | 15000 | Prediction tool tested and deployed | 2 | 2024-10-17 | 2024-10-18 | The AI-powered supply prediction tool functions as expected | 15000 | Prediction tool deployed | QA & Development Teams
WBS-030 | ADA Compliance for Accessibility | Ensure the app meets ADA compliance requirements for accessibility | Development | NFR-012 | ADA compliance | 45000 | ADA-compliant system | 14 | 2024-10-20 | 2024-11-03 | The app is accessible for users with disabilities, including screen reader support | 45000 | ADA-compliant system completed | Development & Accessibility Teams
WBS-030.1 | Conduct Accessibility Audit | Audit the app to identify areas that need to be improved for ADA compliance | Planning | NFR-012 | Accessibility audit | 10000 | Accessibility audit report | 4 | 2024-10-20 | 2024-10-24 | A comprehensive report identifies all areas that need improvement for compliance | 10000 | Accessibility audit completed | Accessibility Team
WBS-030.2 | Implement ADA Compliance Features | Implement features such as screen reader compatibility, high contrast, and text resizing | Development | NFR-012 | ADA-compliant features | 25000 | ADA-compliant features | 8 | 2024-10-25 | 2024-11-02 | Features such as screen reader support and text resizing are implemented | 25000 | ADA compliance features completed | Development Team
WBS-030.3 | Test and Deploy ADA-Compliant Features | Test the features for accessibility compliance and deploy | Testing | NFR-012 | Testing and deployment | 10000 | ADA-compliant system tested and deployed | 2 | 2024-11-03 | 2024-11-04 | All features pass accessibility tests, and the system is fully compliant | 10000 | ADA-compliant system deployed | QA & Accessibility Teams
WBS-031 | Load Balancing for High Traffic | Implement load balancing to handle large numbers of users | Development | TR-010 | Load balancing for high traffic | 40000 | Load balancing system | 12 | 2024-04-01 | 2024-04-13 | The system automatically distributes traffic to avoid slowdowns | 40000 | Load balancing system deployed | IT & Cloud Infrastructure Team
WBS-031.1 | Design Load Balancing Logic | Design the logic for load balancing across servers | Development | TR-010 | Load balancing design | 15000 | Load balancing design | 5 | 2024-04-01 | 2024-04-06 | Load balancing rules distribute user requests evenly across servers | 15000 | Load balancing logic completed | IT Team
WBS-031.2 | Implement Load Balancing | Configure load balancers to distribute traffic | Development | TR-010 | Load balancing configuration | 15000 | Load balancers set up | 5 | 2024-04-07 | 2024-04-12 | Load balancers are functional, and servers handle traffic smoothly | 15000 | Load balancers implemented | IT Team
WBS-031.3 | Test and Deploy Load Balancing | Test the load balancing system and deploy | Testing | TR-010 | Testing and deployment | 10000 | Load balancing tested and deployed | 2 | 2024-04-13 | 2024-04-14 | No issues during high traffic loads, and the system is live | 10000 | Load balancing system deployed | QA & IT Teams
WBS-032 | Database Partitioning | Implement database partitioning to improve performance | Development | TR-011 | Database partitioning | 35000 | Partitioned database | 10 | 2024-04-15 | 2024-04-25 | Database partitions improve query performance | 35000 | Database partitioning completed | Database Development Team
WBS-032.1 | Analyze Data for Partitioning | Analyze data to determine optimal partitioning strategy | Development | TR-011 | Data analysis for partitioning | 10000 | Partitioning strategy report | 3 | 2024-04-15 | 2024-04-18 | Data is analyzed, and partitioning strategy is developed | 10000 | Data analysis completed | Database Team
WBS-032.2 | Implement Database Partitioning | Implement the partitioning strategy in the database | Development | TR-011 | Database partitioning | 15000 | Database partitioning implemented | 5 | 2024-04-19 | 2024-04-24 | Database is partitioned according to the strategy | 15000 | Partitioning implemented | Database Development Team
WBS-032.3 | Test and Deploy Partitioning | Test the partitioned database and deploy | Testing | TR-011 | Testing and deployment | 10000 | Partitioned database tested and deployed | 2 | 2024-04-25 | 2024-04-26 | Database performance is improved with partitioning in place | 10000 | Partitioned database deployed | QA & Database Teams
WBS-033 | Multi-Factor Authentication (MFA) | Implement MFA for secure user access | Development | TR-004 | Multi-factor authentication | 40000 | MFA feature | 14 | 2024-05-01 | 2024-05-15 | Users are required to verify their identity with MFA | 40000 | MFA system deployed | Security & Development Teams
WBS-033.1 | Design MFA UI | Design the user interface for multi-factor authentication | Development | TR-004 | MFA user interface | 10000 | MFA UI | 4 | 2024-05-01 | 2024-05-05 | The MFA UI allows users to enter a second authentication factor | 10000 | MFA UI completed | UI/UX Team
WBS-033.2 | Implement MFA Back-End | Implement the back-end logic for sending and verifying MFA codes | Development | TR-004 | MFA back-end | 20000 | MFA back-end system | 7 | 2024-05-06 | 2024-05-13 | MFA codes are sent via SMS/email and verified | 20000 | MFA back-end completed | Back-End Development Team
WBS-033.3 | Test and Deploy MFA | Test the MFA system and deploy | Testing | TR-004 | Testing and deployment | 10000 | MFA system tested and deployed | 2 | 2024-05-14 | 2024-05-15 | The MFA system works smoothly, and users are securely authenticated | 10000 | MFA system deployed | QA & Security Teams
WBS-034 | Push Notifications for Mobile | Implement push notifications to alert users on mobile devices | Development | NFR-018 | Push notifications for mobile | 35000 | Push notification system | 12 | 2024-06-15 | 2024-06-27 | Mobile users receive notifications for order updates and offers | 35000 | Push notification system deployed | Development Team
WBS-034.1 | Design Notification UI | Design the user interface for mobile notifications | Development | NFR-018 | Push notification UI | 10000 | Notification UI | 4 | 2024-06-15 | 2024-06-19 | The UI allows users to manage notification preferences | 10000 | Notification UI completed | UI/UX Team
WBS-034.2 | Implement Push Notification Logic | Build the back-end logic for sending and receiving notifications | Development | NFR-018 | Push notification logic | 15000 | Push notification logic | 6 | 2024-06-20 | 2024-06-26 | Push notifications are sent for key updates and alerts | 15000 | Push notification logic completed | Back-End Development Team
WBS-034.3 | Test and Deploy Push Notifications | Test the push notification system and deploy | Testing | NFR-018 | Testing and deployment | 10000 | Push notification system tested and deployed | 2 | 2024-06-27 | 2024-06-28 | Notifications work as expected and system is deployed | 10000 | Push notification system deployed | QA & Development Teams
WBS-035 | Secure API Integration | Implement secure APIs for third-party integrations | Development | TR-002 | Secure API integration | 45000 | Secure API system | 14 | 2024-06-30 | 2024-07-14 | API endpoints are secured and data is exchanged securely | 45000 | Secure API system deployed | Development Team
WBS-035.1 | Design API Security Protocols | Design security protocols for API access and data exchange | Development | TR-009 | API security protocols | 15000 | API security protocols | 5 | 2024-06-30 | 2024-07-05 | APIs follow best security practices, such as OAuth and SSL | 15000 | API security protocols completed | Security & Development Teams
WBS-035.2 | Implement Secure API Endpoints | Implement secure API endpoints for data exchange with third parties | Development | TR-002 | Secure API endpoints | 20000 | Secure API endpoints | 7 | 2024-07-06 | 2024-07-12 | API endpoints are functional and securely handle data transfers | 20000 | API endpoints implemented | Back-End Development Team
WBS-035.3 | Test and Deploy API Integration | Test the secure API integration and deploy | Testing | TR-002 | Testing and deployment | 10000 | Secure API system tested and deployed | 2 | 2024-07-13 | 2024-07-14 | Secure API integration works seamlessly and is live | 10000 | API integration system deployed | QA & Development Teams
WBS-036 | Performance Optimization | Improve system performance for high traffic and load | Development | NFR-001 | System performance optimization | 50000 | Optimized system | 15 | 2024-07-15 | 2024-07-30 | The system performs optimally under high load and traffic | 50000 | Performance optimization completed | Development Team
WBS-036.1 | Analyze System Bottlenecks | Analyze the system to identify bottlenecks affecting performance | Development | NFR-001 | System bottleneck analysis | 20000 | Performance bottleneck report | 6 | 2024-07-15 | 2024-07-21 | Bottlenecks are identified and reported for optimization | 20000 | Bottleneck analysis completed | Development & IT Teams
WBS-036.2 | Implement Performance Enhancements | Apply optimizations such as caching, database tuning, and load balancing | Development | NFR-001 | Performance enhancements | 20000 | System optimizations implemented | 7 | 2024-07-22 | 2024-07-29 | System performance is improved with applied optimizations | 20000 | Performance optimizations completed | Development & IT Teams
WBS-036.3 | Test and Deploy Optimized System | Test the optimized system under high load and deploy | Testing | NFR-001 | Testing and deployment | 10000 | Optimized system tested and deployed | 2 | 2024-07-30 | 2024-07-31 | The system performs optimally under stress testing | 10000 | Optimized system deployed | QA & Development Teams
WBS-037 | Data Backup and Recovery | Implement a system for daily backups and quick recovery | Development | NFR-007 | Backup and recovery system | 45000 | Data backup and recovery system | 14 | 2024-08-01 | 2024-08-15 | System ensures daily backups and recovery in less than 24 hours | 45000 | Backup and recovery system deployed | Development & IT Teams
WBS-037.1 | Design Backup Strategy | Develop a comprehensive backup and recovery plan | Planning | NFR-007 | Backup and recovery strategy | 10000 | Backup strategy document | 4 | 2024-08-01 | 2024-08-05 | Backup strategy includes frequency, storage, and recovery timelines | 10000 | Backup strategy completed | IT Team
WBS-037.2 | Implement Backup System | Implement automated daily backups for all critical data | Development | NFR-007 | Automated backup system | 20000 | Automated backup system | 7 | 2024-08-06 | 2024-08-12 | Daily backups are completed successfully with no data loss | 20000 | Backup system implemented | IT Team
WBS-037.3 | Test and Monitor Backup System | Test backup and recovery system and monitor its functionality | Testing | NFR-007 | Testing and monitoring | 15000 | Backup system tested and monitored | 3 | 2024-08-13 | 2024-08-15 | Backup and recovery system is functional and meets requirements | 15000 | Backup system deployed | QA & IT Teams
WBS-038 | Mobile App Responsiveness | Ensure the app is responsive across all devices (mobile, tablet, desktop) | Development | NFR-009 | Mobile app responsiveness | 50000 | Responsive mobile app | 15 | 2024-08-16 | 2024-08-31 | App functions seamlessly across all screen sizes and devices | 50000 | Mobile responsiveness achieved | UI/UX & Development Teams
WBS-038.1 | Design Responsive Layout | Design layouts for various screen sizes (mobile, tablet, desktop) | Development | NFR-009 | Responsive UI design | 20000 | Responsive layouts | 6 | 2024-08-16 | 2024-08-22 | Layouts automatically adjust for different screen sizes | 20000 | Responsive UI design completed | UI/UX Team
WBS-038.2 | Implement Responsive Front-End | Develop front-end code for responsive behavior | Development | NFR-009 | Responsive front-end system | 20000 | Responsive front-end code | 6 | 2024-08-23 | 2024-08-29 | Front-end adjusts to screen size without loss of functionality | 20000 | Responsive front-end completed | Front-End Development Team
WBS-038.3 | Test Responsiveness on Devices | Test the app across multiple devices and screen sizes | Testing | NFR-009 | Testing and deployment | 10000 | Responsive app tested and deployed | 3 | 2024-08-30 | 2024-08-31 | App performs well across various devices and screen sizes | 10000 | Mobile responsiveness deployed | QA & Development Teams
WBS-039 | ADA Compliance for Accessibility | Ensure the app meets ADA compliance for accessibility | Development | NFR-012 | ADA compliance features | 45000 | ADA-compliant app | 14 | 2024-09-01 | 2024-09-15 | The app is accessible for users with disabilities | 45000 | ADA compliance achieved | Accessibility & Development Teams
WBS-039.1 | Conduct ADA Accessibility Audit | Audit the app to identify areas requiring ADA compliance | Planning | NFR-012 | Accessibility audit | 15000 | Accessibility audit report | 4 | 2024-09-01 | 2024-09-05 | Audit identifies necessary updates for ADA compliance | 15000 | Audit completed | Accessibility Team
WBS-039.2 | Implement ADA Compliance Features | Implement features such as screen reader support, high contrast, and text resizing | Development | NFR-012 | Accessibility features | 20000 | ADA-compliant features implemented | 8 | 2024-09-06 | 2024-09-14 | Accessibility features are fully functional and implemented | 20000 | ADA compliance features completed | Development Team
WBS-039.3 | Test and Deploy ADA Features | Test the accessibility features and deploy them | Testing | NFR-012 | Testing and deployment | 10000 | ADA-compliant system tested and deployed | 2 | 2024-09-15 | 2024-09-16 | All accessibility features meet ADA requirements and are live | 10000 | ADA compliance achieved | QA & Development Teams
WBS-040 | Group Purchasing for Bulk Orders | Implement a feature allowing group purchasing for bulk discounts | Development | UR-018 | Group purchasing for bulk orders | 50000 | Group purchasing system | 14 | 2024-09-17 | 2024-10-01 | Multiple users can group orders to receive bulk discounts | 50000 | Group purchasing feature deployed | Development Team
WBS-040.1 | Design Group Purchasing UI | Design the user interface for group purchasing | Development | UR-018 | Group purchasing UI | 15000 | Group purchasing UI | 5 | 2024-09-17 | 2024-09-22 | The UI allows multiple users to participate in group purchasing | 15000 | Group purchasing UI completed | UI/UX Team
WBS-040.2 | Implement Group Purchasing Logic | Implement the logic for calculating and applying bulk discounts for group purchases | Development | UR-018 | Group purchasing logic | 25000 | Group purchasing logic | 7 | 2024-09-23 | 2024-09-30 | Group orders are processed correctly, and discounts are applied | 25000 | Group purchasing logic implemented | Back-End Development Team
WBS-040.3 | Test and Deploy Group Purchasing | Test the group purchasing system and deploy | Testing | UR-018 | Testing and deployment | 10000 | Group purchasing system tested and deployed | 2 | 2024-10-01 | 2024-10-03 | Group purchasing works correctly, and users can participate in bulk orders | 10000 | Group purchasing system deployed | QA & Development Teams
WBS-041 | Forgot Password System | Implement a secure system for resetting forgotten passwords | Development | UR-016 | Forgot password system | 35000 | Password reset feature | 10 | 2024-10-04 | 2024-10-14 | Users can securely reset passwords using email or SMS | 35000 | Forgot password system deployed | Development & Security Teams
WBS-041.1 | Design Forgot Password UI | Design the user interface for the password reset process | Development | UR-016 | Password reset UI | 10000 | Password reset UI | 4 | 2024-10-04 | 2024-10-08 | The UI allows users to request a password reset via email or SMS | 10000 | Forgot password UI completed | UI/UX Team
WBS-041.2 | Implement Reset Logic | Implement the back-end logic for sending and verifying password reset requests | Development | UR-016 | Password reset logic | 15000 | Password reset logic | 5 | 2024-10-09 | 2024-10-13 | Password reset emails/SMS are sent and verified successfully | 15000 | Password reset logic completed | Back-End Development Team
WBS-041.3 | Test and Deploy Forgot Password System | Test the password reset system and deploy | Testing | UR-016 | Testing and deployment | 10000 | Password reset system tested and deployed | 2 | 2024-10-14 | 2024-10-16 | Password reset system works securely, and no issues are found | 10000 | Forgot password system deployed | QA & Development Teams