## Sheet1
Project: School Supplies App
Date: 05/27/2024
Project Manager: John Doe
Risk ID | Risk Description | Impact | Likelihood | Risk Category | Mitigation Plan | Risk Owner | Status | Action Deadline
R-001 | Delay in supplier API integration due to third-party issues | High | Medium | Technical | Engage suppliers early, create a fallback plan, and schedule additional support. | Project Manager | Open | 2024-02-28
R-002 | Data security vulnerabilities identified during testing | Critical | Low | Security | Prioritize encryption tasks, conduct security audits, and involve a security expert. | Security Team | Open | 2024-03-15
R-003 | Resource constraints affecting bulk ordering system development | Medium | Medium | Schedule/Resource | Assign additional resources, extend deadlines, and adjust task prioritization. | Development Team Lead | Open | 2024-04-12
R-004 | User adoption rate lower than expected post-launch | High | Low | Business | Implement a user engagement strategy, including training sessions and marketing. | Marketing Team | Open | 2024-05-01
R-005 | Unexpected changes in regulatory requirements (GDPR compliance) | High | Low | Regulatory/Compliance | Monitor regulatory updates, ensure legal team is engaged in all compliance reviews. | Legal & Compliance Team | Open | Ongoing