# Risk Review Meeting Minutes: Risk R-001 (Supplier API Integration Delay)

Date: 02/10/2024
Time: 11:00 AM – 11:30 AM
Location: Zoom
Participants: Project Manager, Development Team, Risk Team

#### Key Discussion Points:

- Risk Status: Supplier API integration is delayed due to third-party technical issues. The supplier team is facing difficulties aligning with the project’s timeline.

- Impact: The delay could affect the overall system’s functionality, specifically for real-time inventory updates and order management.

- Mitigation Plan Review:

  - Project manager has reached out to suppliers and provided a new timeline for integration.

  - A fallback plan for manual updates is in place in case of further delays.

#### Decisions Made:

- Supplier to provide a weekly update on progress.

- If the delay continues past 02/20/2024, manual workarounds will be implemented.

#### Action Items:

- Project manager to follow up with supplier on 02/15/2024 for an update.

- Development team to finalize fallback plan by 02/18/2024.

# Risk Review Meeting Minutes: Risk R-002 (Data Security Vulnerabilities)

Date: 03/01/2024
Time: 10:00 AM – 10:30 AM
Location: Microsoft Teams
Participants: Project Manager, Security Team, Development Team

#### Key Discussion Points:

- Risk Status: Data security vulnerabilities were identified during testing, especially concerning payment and personal information encryption.

- Impact: Potential breach of sensitive data could lead to legal implications and loss of user trust.

- Mitigation Plan Review:

  - Security team has been prioritizing encryption of all sensitive data, including payment details and personal information.

  - A security audit is scheduled for 03/10/2024.

#### Decisions Made:

- Security team to complete encryption tasks by 03/07/2024.

- Third-party security firm to conduct a vulnerability audit on 03/10/2024.

#### Action Items:

- Security team to complete encryption by 03/07/2024.

- Project manager to confirm audit date and share findings by 03/12/2024.

# Risk Review Meeting Minutes: Risk R-003 (Resource Constraints Affecting Bulk Ordering System)

Date: 03/20/2024
Time: 02:00 PM – 02:30 PM
Location: Zoom
Participants: Project Manager, Development Team Lead, Project Sponsor

#### Key Discussion Points:

- Risk Status: The development of the bulk ordering system is behind schedule due to limited development resources.

- Impact: Delays in the bulk ordering system could affect key functionalities for school administrators.

- Mitigation Plan Review:

  - The project manager proposed reallocating resources from the AI model team temporarily.

  - The timeline for bulk ordering system completion was extended by one week.

#### Decisions Made:

- Reassign one developer from the AI model team to assist with the bulk ordering UI development.

- Deadline extended to 04/12/2024.

#### Action Items:

- Development team lead to adjust team assignments and communicate new deadlines by 03/21/2024.

- Project manager to track progress weekly until the bulk ordering system is completed.

# Risk Review Meeting Minutes: Risk R-004 (Low User Adoption Post-Launch)

Date: 05/05/2024
Time: 09:00 AM – 09:30 AM
Location: Zoom
Participants: Project Manager, Marketing Team, Stakeholders

#### Key Discussion Points:

- Risk Status: Low user adoption rates post-launch are projected based on early user surveys and limited pre-launch engagement.

- Impact: Reduced user engagement could lead to fewer transactions and overall failure to meet business goals.

- Mitigation Plan Review:

  - The marketing team suggested creating user engagement strategies, including personalized email campaigns, social media engagement, and training webinars for parents and school admins.

#### Decisions Made:

- Marketing team to launch a targeted user engagement campaign starting 05/10/2024.

- Training webinars to be scheduled by the end of May 2024.

#### Action Items:

- Marketing team to prepare a communication plan by 05/08/2024.

- Training sessions to be scheduled and shared with stakeholders by 05/15/2024.

# Risk Review Meeting Minutes: Risk R-005 (Regulatory Compliance - GDPR)

Date: 02/15/2024
Time: 03:00 PM – 03:30 PM
Location: Microsoft Teams
Participants: Project Manager, Legal Team, Compliance Team

#### Key Discussion Points:

- Risk Status: There are concerns about potential regulatory changes to GDPR, which may affect how user data is handled within the app.

- Impact: Non-compliance with GDPR could result in legal penalties and impact user trust.

- Mitigation Plan Review:

  - The legal and compliance teams are monitoring regulatory updates closely.

  - Data portability and deletion requests are already part of the app’s functionality, ensuring compliance.

#### Decisions Made:

- Legal team to continue monitoring for changes and provide updates every month.

- No immediate action required, as the app is currently compliant.

#### Action Items:

- Project manager to review the GDPR-compliance checklist by 03/01/2024.

- Legal team to provide a compliance update at the next review meeting.