# 1. Issue: Delay in Payment Gateway Integration

- Issue Description: The development team encountered difficulties integrating the third-party payment gateway, causing delays in the overall project schedule.

- Date of Escalation: 04/08/2024

- Parties Involved: Project Manager, Development Team Lead, Payment Gateway Vendor

- Resolution Decision: Escalated to the payment gateway vendor’s support team. Decided to reallocate resources to ensure integration without further delays.

- Actions Taken: Engaged with the vendor’s technical team to resolve the issue, temporarily paused non-critical tasks to focus on payment gateway integration.

- Final Outcome: Payment gateway was successfully integrated by 04/15/2024 after vendor provided additional support.

- Follow-Up Actions: Monitor system stability and performance over the next month to ensure no further issues with payment processing.

# 2. Issue: UI/UX Team Resource Shortage

- Issue Description: The UI/UX team was short-staffed due to unexpected absences, leading to delays in the completion of wireframes and interface designs.

- Date of Escalation: 03/05/2024

- Parties Involved: Project Manager, UI/UX Team Lead, HR Department

- Resolution Decision: Escalated to HR to assign temporary contract designers to assist with the workload.

- Actions Taken: Hired a contract designer to provide additional support. Re-prioritized tasks to ensure critical designs were completed first.

- Final Outcome: Design work was completed within the extended timeline of 03/20/2024.

- Follow-Up Actions: Review and update the resource contingency plan for future team shortages.

# 3. Issue: Delayed Response from Supplier on API Integration

- Issue Description: The supplier responsible for providing API data feeds failed to respond to integration requests, delaying the development of real-time inventory features.

- Date of Escalation: 02/25/2024

- Parties Involved: Project Manager, Supplier Representative, Project Sponsor

- Resolution Decision: Escalated to the supplier’s management to expedite the response and integration process. In parallel, developed a temporary manual data input system.

- Actions Taken: Scheduled weekly follow-up meetings with the supplier. The temporary solution was implemented to prevent further delays.

- Final Outcome: The supplier integrated the API on 03/10/2024, and the manual system was retired.

- Follow-Up Actions: Monitor supplier response times for future interactions to avoid similar issues.

# 4. Issue: Discrepancies in Performance Metrics Reporting

- Issue Description: Testing revealed discrepancies in the performance metrics being reported in the admin dashboard, leading to incorrect data presentation.

- Date of Escalation: 04/15/2024

- Parties Involved: Project Manager, QA Team, Development Team

- Resolution Decision: Escalated to the technical lead to resolve the logic errors in the reporting system. Temporary data export tools were created to provide accurate reports while fixes were applied.

- Actions Taken: Development team corrected the reporting logic. The QA team re-tested the system to ensure accuracy before final deployment.

- Final Outcome: The reporting tool was fixed and successfully deployed on 04/20/2024.

- Follow-Up Actions: QA to monitor and validate report accuracy over the next quarter.

# 5. Issue: Compliance with New Data Protection Regulations

- Issue Description: A new data protection regulation was introduced mid-project, requiring immediate changes to data handling processes.

- Date of Escalation: 05/01/2024

- Parties Involved: Project Manager, Legal Team, Compliance Team, Development Team

- Resolution Decision: Escalated to the compliance team and legal department to assess the new requirements. Agreed to allocate additional development resources to meet the regulatory deadline.

- Actions Taken: Legal team provided a detailed breakdown of new compliance requirements. Development team implemented the necessary changes to the data protection framework.

- Final Outcome: Compliance was achieved by 05/15/2024, ensuring the project adhered to the new regulations.

- Follow-Up Actions: Schedule periodic reviews of compliance protocols to ensure continued adherence.