## Power Interest Grid
Power | Satisfy | Manage
| High Power, Low Interest | High Power, High Interest
| Legal Consultant: Emily Thompson | Project Sponsor: John Smith
| Supplier Representatives: Sarah Brown, Michael Lee | Development Lead: Alex Brown
School Administrators: Lisa Clark, Robert Jones
| Monitor | Inform
| Low Power, Low Interest | Low Power, High Interest
| HR Specialist: Mark Green | Parents (End Users)
| Marketing Specialist: David White | QA Team: Melissa Green, Anna Roberts, Tim Clark
Interest

## Stakeholder Register
Stakeholder Register
Stakeholder Designation | Name | Priority Grid |  | Strategy for managing risks | Communication Preference | Communication Info | Communication Notes | Additional Notes
|  | Power | Interest
Project Sponsor | John Smith | High | High | Frequent updates, involve in key decisions | Weekly meetings, email | john.smith@schoolapp.com, Phone: 123-456-7890 | Schedule bi-weekly check-in calls | Critical to overall project success
Development Lead | Alex Brown | High | High | Regular sprint updates, assign additional resources | Daily stand-ups, email | alex.brown@schoolapp.com, Phone: 123-456-7891 | Include in all technical discussions
School Administrator | Lisa Clark | High | High | Collect user feedback frequently, involve in testing | Weekly meetings, email | lisa.clark@schoolapp.com, Phone: 123-456-7892 | Update after each feature release
School Administrator | Robert Jones | High | High | Focus group discussions, involve in testing | Weekly meetings, email | robert.jones@schoolapp.com, Phone: 123-456-7893 | Schedule in-person demo sessions
Legal Consultant | Emily Thompson | High | Low | Provide compliance updates, conduct regular audits | Monthly email updates | emily.thompson@schoolapp.com, Phone: 123-456-7894 | Summarize key compliance milestones
Supplier Representative | Sarah Brown | High | Low | Regular follow-ups on API progress | Monthly meetings, email | sarah.brown@suppliers.com, Phone: 123-456-7895 | Coordinate updates through supplier teams
Parents (End Users) | Multiple | Low | High | Provide clear user guides, implement feedback surveys | App notifications, surveys | In-app, feedback surveys | Keep updated on new feature launches
QA Team | Melissa Green | Low | High | Daily sync-ups, prioritize bug-fixing | Daily stand-ups, email | melissa.green@schoolapp.com, Phone: 123-456-7896 | Provide detailed test cases and timelines
HR Specialist | Mark Green | Low | Low | Notify of resource changes, provide staffing reports | Monthly updates | mark.green@schoolapp.com, Phone: 123-456-7897 | Only engage during major changes
Marketing Specialist | David White | Low | Low | Keep informed of launch timelines, engage for promotions | Monthly updates | david.white@schoolapp.com, Phone: 123-456-7898 | Provide campaign material by 04/30/2024