### Human Resource Monitoring Report: Month 1 (January 2024)

Project Name: School Supplies App
Prepared By: Project Manager Sarah Lee
Reporting Period: January 2024
Human Resource Allocation: Developers, Designers, Project Managers, QA Team

#### Weekly Breakdown for January 2024

| Week | Team | Planned Hours | Actual Hours | Variance | Notes |
| --- | --- | --- | --- | --- | --- |
| Week 1 | Development Team | 160 | 150 | -10 | Initial setup, slightly underworked. |
| Week 1 | Design Team | 120 | 110 | -10 | Designers involved in early-stage mockups. |
| Week 2 | Development Team | 160 | 165 | +5 | Backend development ramping up. |
| Week 2 | QA Team | 80 | 70 | -10 | Limited QA involvement at this stage. |
| Week 3 | Development Team | 160 | 160 | 0 | Fully utilized, focusing on backend setup. |
| Week 3 | Design Team | 120 | 130 | +10 | Extra design work needed for UI mockups. |
| Week 4 | Development Team | 160 | 155 | -5 | Developers working slightly under planned hours. |
| Week 4 | QA Team | 100 | 90 | -10 | QA team is slowly ramping up, still under capacity. |

Summary for January
The project is progressing according to plan, with slight variances in design and development team hours. The development team logged 630 hours out of a planned 640, while the design team worked 370 out of a planned 360 hours. QA team involvement will increase in the following months.

### Human Resource Monitoring Report: Month 2 (February 2024)

Project Name: School Supplies App
Prepared By: Project Manager Sarah Lee
Reporting Period: February 2024
Human Resource Allocation: Developers, Designers, Project Managers, QA Team

#### Weekly Breakdown for February 2024

| Week | Team | Planned Hours | Actual Hours | Variance | Notes |
| --- | --- | --- | --- | --- | --- |
| Week 1 | Development Team | 160 | 170 | +10 | Increased focus on backend development. |
| Week 1 | Design Team | 120 | 115 | -5 | Design team slightly under capacity, UI revisions ongoing. |
| Week 2 | Development Team | 160 | 155 | -5 | Development progressing on schedule. |
| Week 2 | QA Team | 100 | 95 | -5 | QA team starting to increase involvement. |
| Week 3 | Development Team | 160 | 160 | 0 | On schedule, back-end nearing completion. |
| Week 3 | QA Team | 120 | 120 | 0 | Full involvement of QA for testing tasks. |
| Week 4 | Development Team | 160 | 165 | +5 | Developers working extra hours to meet backend milestones. |
| Week 4 | Design Team | 100 | 95 | -5 | Design tasks wrapping up for initial screens. |

Summary for February
February saw slight overuse of development resources, with 650 hours logged compared to the 640 planned hours. The QA team has now fully ramped up, logging 310 hours out of 320 planned. Design tasks for UI screens are nearly complete.

### Human Resource Monitoring Report: Month 3 (March 2024)

Project Name: School Supplies App
Prepared By: Project Manager Sarah Lee
Reporting Period: March 2024
Human Resource Allocation: Developers, Designers, QA Team, Project Managers

#### Weekly Breakdown for March 2024

| Week | Team | Planned Hours | Actual Hours | Variance | Notes |
| --- | --- | --- | --- | --- | --- |
| Week 1 | Development Team | 160 | 155 | -5 | Backend near completion, working on final tweaks. |
| Week 1 | QA Team | 140 | 135 | -5 | QA team testing initial modules. |
| Week 2 | Development Team | 160 | 160 | 0 | On schedule, working on frontend modules. |
| Week 2 | Design Team | 100 | 100 | 0 | Final design revisions. |
| Week 3 | Development Team | 160 | 170 | +10 | Extra hours due to complexity in UI implementation. |
| Week 3 | QA Team | 160 | 155 | -5 | Testing ramping up with full feature set. |
| Week 4 | Development Team | 160 | 160 | 0 | Finalizing UI design and testing. |
| Week 4 | QA Team | 160 | 160 | 0 | QA team at full capacity, all test cases being executed. |

Summary for March
March saw the development team putting in extra hours to address UI complexity, with a total of 645 hours logged versus the planned 640. The QA team logged 610 hours out of 620, with testing reaching full capacity as more modules were completed.

### Human Resource Monitoring Report: Month 4 (April 2024)

Project Name: School Supplies App
Prepared By: Project Manager Sarah Lee
Reporting Period: April 2024
Human Resource Allocation: Developers, Designers, QA Team, Project Managers

#### Weekly Breakdown for April 2024

| Week | Team | Planned Hours | Actual Hours | Variance | Notes |
| --- | --- | --- | --- | --- | --- |
| Week 1 | Development Team | 160 | 165 | +5 | Development finalizing backend integration. |
| Week 1 | QA Team | 160 | 150 | -10 | Minor delays in testing new features. |
| Week 2 | Development Team | 160 | 155 | -5 | Development team focusing on bug fixes. |
| Week 2 | QA Team | 160 | 160 | 0 | Full capacity reached as more features are tested. |
| Week 3 | Development Team | 160 | 165 | +5 | Additional development resources allocated for integration. |
| Week 3 | QA Team | 160 | 160 | 0 | Continued testing of integrated features. |
| Week 4 | Development Team | 160 | 160 | 0 | Development nearing final completion. |
| Week 4 | QA Team | 160 | 160 | 0 | QA wrapping up final testing. |

Summary for April
The development team logged 645 hours against a planned 640, with extra hours focused on backend integration and bug fixes. The QA team completed 630 hours of testing out of a planned 640. The development phase is nearing completion, with final testing expected in May.

### Human Resource Monitoring Report: Month 5 (May 2024)

Project Name: School Supplies App
Prepared By: Project Manager Sarah Lee
Reporting Period: May 2024
Human Resource Allocation: Developers, QA Team, Project Managers

#### Weekly Breakdown for May 2024

| Week | Team | Planned Hours | Actual Hours | Variance | Notes |
| --- | --- | --- | --- | --- | --- |
| Week 1 | Development Team | 160 | 165 | +5 | Final development sprint. |
| Week 1 | QA Team | 160 | 155 | -5 | Final bug testing and user acceptance testing. |
| Week 2 | Development Team | 160 | 160 | 0 | Development completed on time. |
| Week 2 | QA Team | 160 | 160 | 0 | Full capacity for user acceptance |
| Week 3 | Development Team | 160 | 155 | -5 | Minor bug fixes based on QA feedback. |
| Week 3 | QA Team | 160 | 165 | +5 | QA team putting in extra hours for final testing. |
| Week 4 | Development Team | 160 | 160 | 0 | Final deployment and post-launch support. |
| Week 4 | QA Team | 160 | 160 | 0 | QA wrapping up, post-launch testing completed. |

Summary for May
May was a critical month as the project reached its final development and testing phases. The development team logged 640 hours, with minor variances, while the QA team put in extra effort to ensure the product was tested thoroughly, logging 640 hours. Final testing and deployment were completed as scheduled.

### Human Resource Monitoring Report: Month 6 (June 2024)

Project Name: School Supplies App
Prepared By: Project Manager Sarah Lee
Reporting Period: June 2024
Human Resource Allocation: Developers, QA Team, Project Managers, Post-Launch Support Team

#### Weekly Breakdown for June 2024

| Week | Team | Planned Hours | Actual Hours | Variance | Notes |
| --- | --- | --- | --- | --- | --- |
| Week 1 | Post-Launch Support Team | 120 | 130 | +10 | Post-launch bug fixes and minor adjustments. |
| Week 1 | Development Team | 100 | 95 | -5 | Transitioning to post-launch support phase. |
| Week 2 | Post-Launch Support Team | 120 | 125 | +5 | Resolving post-launch issues reported by users. |
| Week 2 | QA Team | 100 | 95 | -5 | QA team handling ongoing post-launch testing. |
| Week 3 | Post-Launch Support Team | 120 | 120 | 0 | Support team managing user requests and system adjustments. |
| Week 3 | Development Team | 100 | 100 | 0 | Final development tasks and support. |
| Week 4 | Post-Launch Support Team | 120 | 125 | +5 | Continued post-launch adjustments and user training support. |
| Week 4 | QA Team | 100 | 105 | +5 | Final QA tasks wrapping up post-launch. |

Summary for June
In June, the post-launch support phase kicked off, with a slight increase in hours spent resolving issues and ensuring a smooth transition. The support team logged 500 hours out of a planned 480, and the development team assisted with 390 hours, ensuring all issues were addressed post-launch.

# Conclusion for Months 1-6

Throughout the six-month period, the development, design, and QA teams have worked efficiently, with minor variances in planned vs. actual hours. The project reached its critical post-launch phase in June, with extra hours put in by the support team to handle user feedback and system issues. Resource utilization has been effectively managed, with no significant disruptions to the overall schedule.