# 1. Overview of Budget Performance

The Budget Performance report provides a detailed analysis of the project's financial status, highlighting areas of expenditure, variance from the budget, and forecasting of future costs. This document will serve as a tool for monitoring and controlling project costs to ensure alignment with the project’s financial plan.

# 2. Initial Budget Allocation

The total allocated budget for the School Supplies App project is $1,000,000. This budget covers all phases of the project, including development, design, testing, deployment, and post-launch support. The budget was broken down as follows:

| Category | Allocated Budget |
| --- | --- |
| Development | $400,000 |
| Design (UI/UX) | $150,000 |
| Testing (QA) | $100,000 |
| Infrastructure (AWS, Tools) | $200,000 |
| Project Management | $50,000 |
| Contingency Fund | $100,000 |

# 3. Monthly Budget Breakdown

## Month 1 (January 2024)

- Planned Budget: $100,000

- Actual Expenditure: $95,000

- Variance: -$5,000

Details:

- Development team onboarding costs were slightly under budget.

- Initial project setup and design phase expenditures aligned with projections.

## Month 2 (February 2024)

- Planned Budget: $120,000

- Actual Expenditure: $125,000

- Variance: +$5,000

Details:

- Design costs exceeded expectations due to additional resources needed for user testing and interface revisions.

- Minor variances in testing tools procurement.

## Month 3 (March 2024)

- Planned Budget: $150,000

- Actual Expenditure: $140,000

- Variance: -$10,000

Details:

- Development and design were slightly under budget due to efficient use of internal resources.

- AWS infrastructure setup costs were within budget.

## Month 4 (April 2024)

- Planned Budget: $200,000

- Actual Expenditure: $205,000

- Variance: +$5,000

Details:

- Development team required additional resources for integrating third-party APIs, resulting in higher development costs.

- Contingency funds were not utilized.

## Month 5 (May 2024)

- Planned Budget: $150,000

- Actual Expenditure: $150,000

- Variance: $0

Details:

- Testing and QA phases proceeded as planned, with no significant variances.

- Post-development infrastructure costs remained within budget.

## Month 6 (June 2024)

- Planned Budget: $180,000

- Actual Expenditure: $185,000

- Variance: +$5,000

Details:

- Post-launch support and bug fixes incurred slightly higher-than-expected costs.

- Additional infrastructure and hosting costs arose due to increased user load during launch.

# 4. Cumulative Budget Performance

| Category | Planned Budget | Actual Expenditure | Variance | Percentage Used |
| --- | --- | --- | --- | --- |
| Development | $400,000 | $395,000 | -$5,000 | 98.75% |
| Design (UI/UX) | $150,000 | $155,000 | +$5,000 | 103.33% |
| Testing (QA) | $100,000 | $98,000 | -$2,000 | 98% |
| Infrastructure (AWS, Tools) | $200,000 | $205,000 | +$5,000 | 102.5% |
| Project Management | $50,000 | $48,000 | -$2,000 | 96% |
| Contingency Fund | $100,000 | $0 | $0 | 0% |

# 5. Variance Analysis

Key Observations:

- Design Phase: Costs slightly exceeded the budget due to additional user research and interface changes after feedback from early testing.

- Development Phase: A minor surplus is observed due to more efficient use of internal resources and automation tools.

- Infrastructure Costs: AWS costs were higher than anticipated due to increased traffic at launch, requiring additional server capacity.

- Contingency Fund: The contingency fund remains untouched and will be reserved for unexpected costs in the final stages of the project.

# 6. Forecast for Remaining Phases

| Phase | Planned Budget | Forecasted Expenditure | Variance |
| --- | --- | --- | --- |
| Final Development | $50,000 | $50,000 | $0 |
| Post-Launch Support | $30,000 | $32,000 | +$2,000 |
| Documentation and Handover | $20,000 | $18,000 | -$2,000 |
| Maintenance and Updates | $60,000 | $58,000 | -$2,000 |

# 7. Budget Control Strategies

- Monitoring & Tracking: Weekly budget tracking meetings are held with the finance team to ensure all expenditures align with the planned budget.

- Cost Optimization: Ongoing review of AWS and other infrastructure resources to optimize cloud spending.

- Contingency Fund Management: The remaining $100,000 contingency fund will be utilized only if necessary, primarily for unforeseen post-launch issues.

- Vendor Negotiation: Ongoing negotiations with external suppliers and service providers to ensure services are delivered within the agreed budget.

# 8. Conclusion

Overall, the budget performance of the project is on track, with slight variances that are well within acceptable limits. The project remains within the total budget of $1,000,000, and the contingency fund will be used judiciously to manage any further unforeseen costs.

Ongoing monitoring and proactive budget adjustments will ensure the project completes within its financial limits.