## Sheet1
Task/Deliverable | Project Manager | Lead Developer | Back-End Developer | Front-End Developer | UX/UI Designer | QA Lead | Security Specialist | Cloud Infrastructure Specialist
Project Planning | A | C | I | I | I | I | C | I
Create Registration UI | I | C | I | R | R | C | I | I
Develop Back-End for Registration | I | R | R | I | I | C | C | I
Integrate Social Media Logins | I | R | R | I | I | C | C | I
Design Parent Dashboard | I | C | I | I | R | C | I | I
Develop Order History Feature | I | R | R | I | I | C | C | I
Implement Secure Payment Gateway | I | R | R | I | I | C | A | C
Data Encryption for Payment and User Data | I | C | C | I | I | C | R | I
Create Test Plans and Cases | I | C | I | I | I | R | I | I
Perform Functional Testing | bar: I to C
Perform Security Testing | I | I | I | I | I | C | R | I
Setup Cloud Infrastructure | I | C | I | I | I | I | C | R
Monitor Cloud Performance | I | I | I | I | I | I | C | R
Release to Production | A | R | R | R | C | R | C | I
Post-Launch Support | A | R | R | R | C | R | C | R
Security Audits and Compliance | I | C | I | I | I | C | R | C
Manage Project Risks | A | C | I | I | I | I | C | I
Weekly Status Reports | bar: A to I