## Sheet1
Task ID | Task Name | Estimated Duration (Days) | Required Resources | Resource Description | Responsible Team/Person
WBS-001 | User Registration System | 14 | Front-End Developer, Back-End Developer, UX/UI Designer, AWS | Design and implement user registration UI and back-end logic | Development Team
WBS-001.1 | Create Registration UI | 5 | UX/UI Designer, Front-End Developer | Design the user interface for registration | UX/UI Team
WBS-001.2 | Build Back-End for Registration | 6 | Back-End Developer, AWS | Develop server-side code for handling user registration | Back-End Team
WBS-001.3 | Integrate Social Media Logins | 3 | Back-End Developer, Front-End Developer, OAuth API | Integrate third-party login providers (Google, Facebook, etc.) | Development Team
WBS-001.4 | Test and Deploy Registration | 3 | QA Specialist, AWS | Test and deploy the registration system | QA & Development Teams
WBS-002 | Admin Inventory Management | 20 | Front-End Developer, Back-End Developer, UX/UI Designer, AWS | Develop inventory management tools for administrators | Development Team
WBS-002.1 | Create Inventory Dashboard UI | 5 | UX/UI Designer, Front-End Developer | Design the inventory dashboard interface for admins | UX/UI Team
WBS-002.2 | Build Inventory Database | 8 | Back-End Developer, Database Admin, AWS | Set up the inventory database to track stock levels | Back-End Team
WBS-002.3 | Implement Low Stock Alerts | 5 | Back-End Developer, Front-End Developer | Develop system to alert admins of low inventory | Development Team
WBS-002.4 | Test and Deploy Inventory System | 2 | QA Specialist, AWS | Test and deploy the inventory management system | QA & Development Teams
WBS-003 | Parent Dashboard | 15 | UX/UI Designer, Front-End Developer, Back-End Developer | Develop the dashboard for parents to track orders and supplies | Development Team
WBS-003.1 | Design Parent Dashboard UI | 5 | UX/UI Designer | Design the dashboard layout | UX/UI Team
WBS-003.2 | Build Order History Display | 5 | Back-End Developer, Front-End Developer | Develop the order history feature for parents | Development Team
WBS-003.3 | Build Supply Suggestions System | 5 | Back-End Developer, Front-End Developer | Implement suggestions based on school schedule | Development Team
WBS-003.4 | Test and Deploy Parent Dashboard | 3 | QA Specialist, AWS | Test and deploy the parent dashboard | QA & Development Teams
WBS-004 | Secure Payment Integration | 12 | UX/UI Designer, Back-End Developer, Security Specialist, Payment Gateway | Implement secure payment processing | Development & Security Teams
WBS-004.1 | Design Checkout UI | 4 | UX/UI Designer | Design the user interface for checkout | UX/UI Team
WBS-004.2 | Integrate Payment Gateway | 5 | Back-End Developer, Payment Gateway API | Integrate payment system with external providers | Back-End Team
WBS-004.3 | Implement Data Encryption | 3 | Security Specialist, Back-End Developer | Ensure all sensitive data is encrypted in transit and at rest | Security & Development Teams
WBS-004.4 | Test and Deploy Payment System | 2 | QA Specialist, AWS | Test and deploy the payment system | QA & Development Teams
WBS-005 | Product Comparison Tool | 10 | UX/UI Designer, Front-End Developer, Back-End Developer | Develop the product comparison feature | Development Team
WBS-005.1 | Design Comparison Tool UI | 4 | UX/UI Designer, Front-End Developer | Design the interface for comparing products | UX/UI Team
WBS-005.2 | Build Comparison Engine | 4 | Back-End Developer, AWS | Build the engine to compare product features and prices | Back-End Team
WBS-005.3 | Implement Sorting and Filters | 2 | Front-End Developer, Back-End Developer | Add filters for sorting products by price, rating, and availability | Development Team
WBS-005.4 | Test and Deploy Comparison Tool | 2 | QA Specialist, AWS | Test and deploy the comparison tool | QA & Development Teams
WBS-006 | Order Tracking System | 14 | UX/UI Designer, Back-End Developer, Front-End Developer | Develop the order tracking system for parents and admins | Development Team
WBS-006.1 | Design Order Tracking UI | 5 | UX/UI Designer, Front-End Developer | Design the order tracking interface | UX/UI Team
WBS-006.2 | Build Order Tracking Engine | 6 | Back-End Developer | Develop logic to track orders at each stage | Back-End Team
WBS-006.3 | Test and Deploy Order Tracking | 3 | QA Specialist, AWS | Test and deploy the order tracking system | QA & Development Teams
WBS-007 | AI-Powered Supply Prediction | 30 | Data Scientist, Back-End Developer, AI Specialist, AWS | Develop AI model to predict future supply needs | AI & Development Teams
WBS-007.1 | Data Collection and Analysis | 10 | Data Scientist, AWS | Gather and analyze historical order data for model training | Data Science Team
WBS-007.2 | AI Model Training | 15 | AI Specialist, Data Scientist, AWS | Train machine learning models using historical data | AI Team
WBS-007.3 | Integrate AI Model with Platform | 5 | Back-End Developer, AWS | Integrate AI model with backend for real-time predictions | Development Team
WBS-007.4 | Test and Optimize AI Predictions | 5 | QA Specialist, Data Scientist, AWS | Test and fine-tune AI predictions | AI & QA Teams
WBS-008 | Role-Based Access Control | 14 | Back-End Developer, Front-End Developer, Security Specialist | Implement role-based access for different users (admins, parents) | Development & Security Teams
WBS-008.1 | Define User Roles and Permissions | 4 | Project Manager, Security Specialist | Define user roles (admins, parents, suppliers) | Project Management & Security Teams
WBS-008.2 | Build Access Control System | 8 | Back-End Developer, AWS | Develop backend logic to manage user permissions | Back-End Team
WBS-008.3 | Integrate with Front-End | 4 | Front-End Developer | Integrate access control with the user interface | Front-End Team
WBS-008.4 | Test and Deploy Access Control | 3 | QA Specialist, Security Specialist | Test and deploy access control features | QA & Security Teams
WBS-009 | In-App Chat Support | 8 | UX/UI Designer, Back-End Developer, Front-End Developer | Implement real-time chat functionality for user support | Development Team
WBS-009.1 | Design Chat UI | 3 | UX/UI Designer, Front-End Developer | Design the user interface for in-app chat | UX/UI Team
WBS-009.2 | Implement Chat Back-End | 4 | Back-End Developer, AWS | Build real-time chat backend with server infrastructure | Back-End Team
WBS-009.3 | Test and Deploy Chat System | 1 | QA Specialist | Test and deploy the chat system | QA & Development Teams
WBS-010 | Bulk Ordering System | 12 | Front-End Developer, Back-End Developer, UX/UI Designer | Develop bulk ordering functionality for school admins | Development Team
WBS-010.1 | Design Bulk Ordering UI | 4 | UX/UI Designer, Front-End Developer | Design the bulk ordering interface | UX/UI Team
WBS-010.2 | Build Bulk Ordering Back-End | 6 | Back-End Developer, AWS | Develop backend logic for bulk ordering | Back-End Team
WBS-010.3 | Test and Deploy Bulk Ordering | 2 | QA Specialist | Test and deploy bulk ordering system | QA & Development Teams
WBS-010.4 | Add Bulk Discounts Integration | 4 | Back-End Developer, Front-End Developer | Integrate discount features for bulk orders | Development Team
WBS-011 | Product Search and Filter | 12 | Front-End Developer, Back-End Developer, UX/UI Designer | Implement product search and filtering features | Development Team
WBS-011.1 | Design Product Search UI | 4 | UX/UI Designer, Front-End Developer | Design the user interface for product search | UX/UI Team
WBS-011.2 | Implement Search Engine | 6 | Back-End Developer, AWS | Develop the search engine logic | Back-End Team
WBS-011.3 | Add Filtering Options | 2 | Front-End Developer | Add filtering options to the search interface | Development Team
WBS-011.4 | Test and Deploy Search System | 2 | QA Specialist | Test and deploy the product search system | QA & Development Teams
WBS-012 | Reports Dashboard (Admin) | 20 | UX/UI Designer, Back-End Developer, Front-End Developer | Develop admin dashboard with reports and analytics | Development Team
WBS-012.1 | Design Reports Dashboard UI | 6 | UX/UI Designer, Front-End Developer | Design the admin reports dashboard | UX/UI Team
WBS-012.2 | Implement Report Generation | 10 | Back-End Developer, AWS | Develop the backend logic for generating reports | Back-End Team
WBS-012.3 | Integrate with Supplier Data | 4 | Back-End Developer, AWS | Integrate supplier data for reports | Back-End Team
WBS-012.4 | Test and Deploy Reports Dashboard | 4 | QA Specialist | Test and deploy the reports dashboard | QA & Development Teams
WBS-013 | Notifications and Alerts | 10 | UX/UI Designer, Back-End Developer, Front-End Developer | Implement notifications and alerts for users | Development Team
WBS-013.1 | Design Notification UI | 3 | UX/UI Designer, Front-End Developer | Design the user interface for notifications | UX/UI Team
WBS-013.2 | Implement Notification Logic | 5 | Back-End Developer, AWS | Develop logic for real-time notifications | Back-End Team
WBS-013.3 | Set Up Push Notifications | 2 | Mobile Developer, AWS | Implement push notifications for mobile devices | Mobile Development Team
WBS-013.4 | Test and Deploy Notification System | 2 | QA Specialist | Test and deploy the notification system | QA & Development Teams
WBS-014 | Supplier Product Management | 15 | Front-End Developer, Back-End Developer, UX/UI Designer | Develop product management features for suppliers | Development Team
WBS-014.1 | Design Supplier Product UI | 5 | UX/UI Designer, Front-End Developer | Design the product management interface | UX/UI Team
WBS-014.2 | Build Product Management Back-End | 7 | Back-End Developer, AWS | Develop backend logic for supplier product management | Back-End Team
WBS-014.3 | Implement Stock Level Management | 3 | Back-End Developer | Integrate stock level management features | Development Team
WBS-014.4 | Test and Deploy Product Management | 3 | QA Specialist | Test and deploy the product management system | QA & Development Teams
WBS-015 | Multi-Language Support | 8 | UX/UI Designer, Front-End Developer, Localization Specialist | Implement multi-language support for the app | Development & Localization Team
WBS-015.1 | Language Selection UI | 2 | UX/UI Designer, Front-End Developer | Design the language selection interface | UX/UI Team
WBS-015.2 | Translation and Localization | 4 | Localization Specialist, Front-End Developer | Localize content for multiple languages (English, Spanish, etc.) | Localization Team
WBS-015.3 | Integrate Multi-Language Back-End | 2 | Back-End Developer | Develop the back-end to handle language selection | Development Team
WBS-015.4 | Test and Deploy Multi-Language | 2 | QA Specialist, Localization Specialist | Test and deploy the multi-language system | QA & Localization Team
WBS-016 | Product Wishlist/Favorites | 10 | UX/UI Designer, Front-End Developer, Back-End Developer | Develop wishlist and favorites functionality | Development Team
WBS-016.1 | Design Wishlist UI | 3 | UX/UI Designer, Front-End Developer | Design the user interface for wishlist functionality | UX/UI Team
WBS-016.2 | Build Wishlist Back-End | 5 | Back-End Developer, AWS | Develop the back-end system for wishlist management | Back-End Team
WBS-016.3 | Integrate with Cart System | 2 | Front-End Developer | Integrate the wishlist system with the shopping cart | Development Team
WBS-016.4 | Test and Deploy Wishlist Feature | 2 | QA Specialist | Test and deploy the wishlist feature | QA & Development Teams
WBS-017 | Data Encryption for Security | 14 | Security Specialist, Back-End Developer | Implement encryption for user and payment data | Development & Security Teams
WBS-017.1 | Encrypt Payment Data | 6 | Security Specialist, Back-End Developer | Ensure all payment data is encrypted in transit and at rest | Security & Development Teams
WBS-017.2 | Encrypt Personal Information | 6 | Security Specialist, Back-End Developer | Encrypt personal data such as login credentials, addresses, etc. | Security Team
WBS-017.3 | Test and Deploy Encryption System | 2 | QA Specialist, Security Specialist | Test and deploy encryption system | QA & Security Teams
WBS-018 | Recurring Orders Setup (Parent) | 12 | UX/UI Designer, Back-End Developer, Front-End Developer | Implement recurring order functionality for parents | Development Team
WBS-018.1 | Design Recurring Order UI | 4 | UX/UI Designer, Front-End Developer | Design the user interface for recurring orders | UX/UI Team
WBS-018.2 | Build Recurring Order Back-End | 6 | Back-End Developer | Develop the back-end system for recurring order management | Back-End Team
WBS-018.3 | Test and Deploy Recurring Order | 2 | QA Specialist | Test and deploy the recurring order system | QA & Development Teams
WBS-019 | Admin Multi-Location Dashboard | 14 | UX/UI Designer, Front-End Developer, Back-End Developer | Develop a multi-location dashboard for administrators | Development Team
WBS-019.1 | Design Location Selection UI | 5 | UX/UI Designer, Front-End Developer | Design the location selection interface | UX/UI Team
WBS-019.2 | Implement Location Data Tracking | 6 | Back-End Developer, AWS | Develop back-end logic for tracking data across multiple locations | Back-End Team
WBS-019.3 | Test and Deploy Multi-Location Dashboard | 3 | QA Specialist, AWS | Test and deploy the multi-location dashboard | QA & Development Teams
WBS-020 | Voice-Assisted Search | 14 | UX/UI Designer, Back-End Developer, AI Specialist | Implement voice search functionality | Development Team
WBS-020.1 | Design Voice Search UI | 5 | UX/UI Designer, Front-End Developer | Design the user interface for voice search | UX/UI Team
WBS-020.2 | Build Voice Recognition Back-End | 7 | AI Specialist, Back-End Developer, AWS | Develop back-end logic for voice recognition | AI & Back-End Teams
WBS-020.3 | Test and Deploy Voice Search | 3 | QA Specialist, AI Specialist | Test and deploy voice search feature | QA & Development Teams
WBS-021 | Automatic Server Scaling | 18 | IT Specialist, AWS Specialist | Implement auto-scaling functionality for servers | IT & Cloud Infrastructure Teams
WBS-021.1 | Set Up Cloud Infrastructure | 8 | IT Specialist, AWS Specialist | Set up cloud infrastructure to handle server scaling | IT Team
WBS-021.2 | Implement Auto-Scaling Rules | 8 | AWS Specialist, IT Specialist | Set up auto-scaling rules for server traffic management | IT & Development Teams
WBS-021.3 | Test and Monitor Auto-Scaling | 3 | QA Specialist, AWS Specialist | Test and deploy auto-scaling system | QA & IT Teams
WBS-022 | Supplier Performance Evaluation | 14 | UX/UI Designer, Front-End Developer, Back-End Developer | Implement supplier performance evaluation tools | Development Team
WBS-022.1 | Design Supplier Evaluation UI | 5 | UX/UI Designer, Front-End Developer | Design the interface for supplier evaluation | UX/UI Team
WBS-022.2 | Build Evaluation Metrics System | 7 | Back-End Developer | Develop back-end system for tracking supplier performance | Back-End Team
WBS-022.3 | Test and Deploy Evaluation System | 3 | QA Specialist | Test and deploy supplier evaluation tools | QA & Development Teams
WBS-023 | Vendor Feedback and Rating System | 10 | UX/UI Designer, Front-End Developer, Back-End Developer | Implement vendor feedback and rating system | Development Team
WBS-023.1 | Design Feedback and Rating UI | 4 | UX/UI Designer, Front-End Developer | Design the interface for vendor feedback | UX/UI Team
WBS-023.2 | Implement Rating System Logic | 5 | Back-End Developer, AWS | Develop the back-end system for managing ratings and feedback | Back-End Team
WBS-023.3 | Test and Deploy Feedback System | 2 | QA Specialist | Test and deploy the vendor feedback system | QA & Development Teams
WBS-024 | Custom Reporting Tool | 12 | UX/UI Designer, Front-End Developer, Back-End Developer | Develop a custom reporting tool for admins and users | Development Team
WBS-024.1 | Design Custom Report UI | 5 | UX/UI Designer, Front-End Developer | Design the user interface for custom reports | UX/UI Team
WBS-024.2 | Implement Report Generation Logic | 5 | Back-End Developer, AWS | Build the logic to generate reports based on selected criteria | Back-End Team
WBS-024.3 | Test and Deploy Custom Report Tool | 2 | QA Specialist | Test and deploy the custom reporting tool | QA & Development Teams
WBS-025 | Loyalty Programs for User Retention | 14 | UX/UI Designer, Front-End Developer, Back-End Developer | Develop loyalty programs to increase user retention | Development Team
WBS-025.1 | Design Loyalty Program UI | 5 | UX/UI Designer, Front-End Developer | Design the user interface for loyalty programs | UX/UI Team
WBS-025.2 | Build Loyalty Points System | 7 | Back-End Developer, AWS | Develop the backend system for tracking loyalty points | Back-End Team
WBS-025.3 | Integrate Loyalty Offers and Rewards | 5 | Back-End Developer, Front-End Developer | Integrate offers and rewards for the loyalty system | Development Team
WBS-025.4 | Test and Deploy Loyalty Program | 2 | QA Specialist | Test and deploy the loyalty program system | QA & Development Teams
WBS-026 | Order Splitting Across Suppliers | 10 | UX/UI Designer, Front-End Developer, Back-End Developer | Implement order splitting feature for multiple suppliers | Development Team
WBS-026.1 | Design Order Splitting UI | 4 | UX/UI Designer, Front-End Developer | Design the user interface for splitting orders | UX/UI Team
WBS-026.2 | Implement Splitting Logic | 6 | Back-End Developer | Develop the logic to split orders across multiple suppliers | Back-End Team
WBS-026.3 | Test and Deploy Order Splitting System | 2 | QA Specialist | Test and deploy the order splitting feature | QA & Development Teams
WBS-027 | Discount and Promotions Feature | 12 | UX/UI Designer, Front-End Developer, Back-End Developer | Implement discount and promotion features | Development Team
WBS-027.1 | Design Discounts UI | 4 | UX/UI Designer, Front-End Developer | Design the interface for discounts and promotions | UX/UI Team
WBS-027.2 | Build Discount Logic | 6 | Back-End Developer | Develop the logic for applying discounts and promotions | Back-End Team
WBS-027.3 | Test and Deploy Discounts Feature | 2 | QA Specialist | Test and deploy the discount and promotions system | QA & Development Teams
WBS-028 | Shopping Cart and Checkout System | 20 | UX/UI Designer, Front-End Developer, Back-End Developer | Develop the shopping cart and checkout system | Development Team
WBS-028.1 | Design Shopping Cart UI | 6 | UX/UI Designer, Front-End Developer | Design the user interface for the shopping cart | UX/UI Team
WBS-028.2 | Build Secure Checkout Logic | 10 | Back-End Developer, Security Specialist | Develop the logic for secure checkout and payment processing | Back-End & Security Teams
WBS-028.3 | Test and Deploy Shopping Cart | 3 | QA Specialist | Test and deploy the shopping cart and checkout system | QA & Development Teams
WBS-029 | AI-Powered Supply Prediction Tool | 18 | Data Scientist, Back-End Developer, AI Specialist | Implement AI to predict supply needs based on past usage | AI & Development Teams
WBS-029.1 | Data Collection and Model Training | 7 | Data Scientist, AI Specialist | Collect data and train the AI model for supply prediction | Data Science & AI Teams
WBS-029.2 | Build Prediction Engine | 7 | Back-End Developer, AI Specialist | Develop the prediction engine to suggest supply needs | Back-End & AI Teams
WBS-029.3 | Test and Deploy Prediction Tool | 2 | QA Specialist, Data Scientist | Test and deploy the AI-powered supply prediction system | QA & Development Teams
WBS-030 | ADA Compliance for Accessibility | 14 | UX/UI Designer, Back-End Developer, Accessibility Specialist | Ensure the app is compliant with ADA accessibility standards | Development & Accessibility Teams
WBS-030.1 | Conduct Accessibility Audit | 4 | Accessibility Specialist, UX/UI Designer | Audit the app for ADA compliance | Accessibility Team
WBS-030.2 | Implement ADA Compliance Features | 8 | Front-End Developer, Back-End Developer | Implement features to ensure ADA compliance | Development Team
WBS-030.3 | Test and Deploy ADA-Compliant Features | 2 | QA Specialist | Test and deploy ADA-compliant features | QA & Accessibility Teams
WBS-031 | Load Balancing for High Traffic | 12 | IT Specialist, AWS Specialist | Implement load balancing for high-traffic management | IT & Cloud Infrastructure Teams
WBS-031.1 | Design Load Balancing Logic | 5 | IT Specialist, AWS Specialist | Develop the logic for load balancing | IT Team
WBS-031.2 | Implement Load Balancing | 5 | AWS Specialist, IT Specialist | Implement load balancing systems | IT Team
WBS-031.3 | Test and Deploy Load Balancing | 2 | QA Specialist, AWS Specialist | Test and deploy the load balancing system | QA & IT Teams
WBS-032 | Database Partitioning | 10 | Database Administrator, Back-End Developer | Implement database partitioning to optimize performance | Database Team
WBS-032.1 | Analyze Data for Partitioning | 3 | Database Administrator | Analyze the data structure for effective partitioning | Database Team
WBS-032.2 | Implement Database Partitioning | 5 | Back-End Developer, Database Administrator | Develop and apply database partitioning | Database Team
WBS-032.3 | Test and Deploy Partitioning | 2 | QA Specialist, Database Administrator | Test and deploy the partitioned database | QA & Database Teams
WBS-033 | Multi-Factor Authentication (MFA) | 14 | UX/UI Designer, Back-End Developer, Security Specialist | Implement MFA for secure login | Development & Security Teams
WBS-033.1 | Design MFA UI | 4 | UX/UI Designer, Front-End Developer | Design the user interface for MFA | UX/UI Team
WBS-033.2 | Implement MFA Back-End | 7 | Back-End Developer, Security Specialist | Develop MFA logic and back-end system | Back-End & Security Teams
WBS-033.3 | Test and Deploy MFA | 2 | QA Specialist, Security Specialist | Test and deploy the MFA system | QA & Security Teams
WBS-034 | Push Notifications for Mobile | 12 | UX/UI Designer, Mobile Developer, Back-End Developer | Implement push notifications for mobile devices | Development Team
WBS-034.1 | Design Notification UI | 4 | UX/UI Designer, Front-End Developer | Design the user interface for mobile notifications | UX/UI Team
WBS-034.2 | Implement Push Notification Logic | 6 | Back-End Developer, Mobile Developer | Develop push notification logic | Back-End & Mobile Development Teams
WBS-034.3 | Test and Deploy Push Notifications | 2 | QA Specialist | Test and deploy the push notification system | QA & Development Teams
WBS-035 | Secure API Integration | 14 | Back-End Developer, Security Specialist, API Specialist | Implement secure API integration for third-party services | Development & Security Teams
WBS-035.1 | Design API Security Protocols | 5 | Security Specialist, Back-End Developer | Design security protocols for API integration | Security & Development Teams
WBS-035.2 | Implement Secure API Endpoints | 7 | Back-End Developer, API Specialist | Develop and secure API endpoints for external services | Back-End Team
WBS-035.3 | Test and Deploy API Integration | 2 | QA Specialist, Security Specialist | Test and deploy secure API integration | QA & Security Teams
WBS-036 | Performance Optimization | 15 | Back-End Developer, IT Specialist | Optimize system performance for better load times and user experience | Development & IT Teams
WBS-036.1 | Analyze System Bottlenecks | 6 | IT Specialist, Back-End Developer | Identify system bottlenecks affecting performance | IT & Development Teams
WBS-036.2 | Implement Performance Enhancements | 7 | Back-End Developer, IT Specialist | Apply enhancements to improve performance | Development & IT Teams
WBS-036.3 | Test and Deploy Optimized System | 2 | QA Specialist, IT Specialist | Test and deploy performance improvements | QA & Development Teams
WBS-037 | Data Backup and Recovery | 14 | IT Specialist, Back-End Developer | Implement backup and recovery systems for critical data | Development & IT Teams
WBS-037.1 | Design Backup Strategy | 4 | IT Specialist | Design backup and recovery strategies | IT Team
WBS-037.2 | Implement Backup System | 7 | IT Specialist, AWS | Set up the backup and recovery system in the cloud | IT Team
WBS-037.3 | Test and Monitor Backup System | 3 | QA Specialist, IT Specialist | Test and deploy the backup and recovery system | QA & IT Teams
WBS-038 | Mobile App Responsiveness | 15 | UX/UI Designer, Front-End Developer | Ensure mobile app responsiveness on all devices | Development Team
WBS-038.1 | Design Responsive Layout | 6 | UX/UI Designer, Front-End Developer | Design responsive layouts for mobile devices | UX/UI Team
WBS-038.2 | Implement Responsive Front-End | 6 | Front-End Developer | Implement responsive front-end logic | Front-End Development Team
WBS-038.3 | Test Responsiveness on Devices | 3 | QA Specialist | Test the app's responsiveness on various devices | QA & Development Teams
WBS-039 | ADA Compliance for Accessibility | 14 | UX/UI Designer, Back-End Developer, Accessibility Specialist | Implement ADA-compliant features for accessibility | Development & Accessibility Teams
WBS-039.1 | Conduct ADA Accessibility Audit | 4 | Accessibility Specialist | Perform an audit to identify gaps in ADA compliance | Accessibility Team
WBS-039.2 | Implement ADA Compliance Features | 8 | Front-End Developer, Back-End Developer | Apply ADA-compliant features to ensure accessibility | Development Team
WBS-039.3 | Test and Deploy ADA Features | 2 | QA Specialist, Accessibility Specialist | Test and deploy ADA-compliant features | QA & Development Teams
WBS-040 | Group Purchasing for Bulk Orders | 14 | UX/UI Designer, Front-End Developer, Back-End Developer | Implement group purchasing features for bulk orders | Development Team
WBS-040.1 | Design Group Purchasing UI | 5 | UX/UI Designer, Front-End Developer | Design the user interface for group purchasing | UX/UI Team
WBS-040.2 | Implement Group Purchasing Logic | 7 | Back-End Developer, AWS | Develop the logic to allow users to participate in group purchases | Back-End Team
WBS-040.3 | Test and Deploy Group Purchasing | 2 | QA Specialist | Test and deploy the group purchasing feature | QA & Development Teams
WBS-041 | Forgot Password System | 10 | UX/UI Designer, Back-End Developer, Security Specialist | Implement the forgot password feature | Development & Security Teams
WBS-041.1 | Design Forgot Password UI | 4 | UX/UI Designer, Front-End Developer | Design the user interface for the forgot password system | UX/UI Team
WBS-041.2 | Implement Reset Logic | 5 | Back-End Developer, Security Specialist | Develop the logic to allow users to reset their passwords | Back-End & Security Teams
WBS-041.3 | Test and Deploy Forgot Password System | 2 | QA Specialist | Test and deploy the forgot password system | QA & Development Teams
WBS-042 | Performance Monitoring and Optimization | 12 | IT Specialist, Back-End Developer, QA Specialist | Continuously monitor and optimize system performance | IT & QA Teams
WBS-042.1 | Set Up Monitoring Tools | 5 | IT Specialist | Set up performance monitoring tools (e.g., New Relic, Datadog) | IT Team
WBS-042.2 | Monitor System Performance | 5 | IT Specialist, Back-End Developer | Monitor system performance and log data | IT & Development Teams
WBS-042.3 | Optimize Based on Findings | 2 | Back-End Developer, IT Specialist | Implement optimizations based on monitoring data | IT & Development Teams
WBS-043 | User Acceptance Testing (UAT) | 14 | QA Specialist, End Users, Development Team | Perform user acceptance testing to ensure requirements are met | QA & End User Teams
WBS-043.1 | Develop UAT Test Plan | 3 | QA Specialist | Create test plan for user acceptance testing | QA Team
WBS-043.2 | Conduct UAT | 7 | QA Specialist, End Users | Conduct UAT with selected users to validate system functionality | QA & End User Teams
WBS-043.3 | Document UAT Results | 2 | QA Specialist | Document the results and feedback from UAT | QA Team
WBS-043.4 | Address UAT Issues | 2 | Development Team | Fix any issues identified during UAT | Development Team
WBS-044 | Final System Deployment | 7 | IT Specialist, Development Team, QA Specialist | Deploy the system to the production environment | IT & Development Teams
WBS-044.1 | Prepare Production Environment | 3 | IT Specialist, AWS Specialist | Set up and configure the production environment | IT Team
WBS-044.2 | Deploy System to Production | 3 | IT Specialist, Development Team | Deploy the final system to the production environment | IT & Development Teams
WBS-044.3 | Post-Deployment Monitoring | 1 | IT Specialist | Monitor the system after deployment to ensure stability | IT Team
WBS-045 | Training for Admins and Users | 10 | Training Specialist, End Users | Provide training for admins and users on system usage | Training Team
WBS-045.1 | Develop Training Materials | 4 | Training Specialist, UX/UI Designer | Create guides, videos, and documentation for training | Training & UX/UI Teams
WBS-045.2 | Conduct Training Sessions | 5 | Training Specialist, Admins, End Users | Host live training sessions for admins and end users | Training Team
WBS-045.3 | Gather Feedback from Training | 1 | Training Specialist | Collect feedback from participants to improve training materials | Training Team
WBS-046 | Post-Implementation Support | 15 | IT Support Team, QA Specialist, Development Team | Provide ongoing support after deployment | IT & Development Teams
WBS-046.1 | Set Up Support Channels | 3 | IT Support Team | Set up channels (e.g., email, chat, phone) for support | IT Support Team
WBS-046.2 | Handle User Support Requests | 10 | IT Support Team, QA Specialist | Address user issues and provide technical support | IT Support & QA Teams
WBS-046.3 | Monitor and Improve Support Process | 2 | IT Support Team, QA Specialist | Continuously monitor and improve the support process | IT Support Team