## Sheet1
RBS ID | Resource Category | Resource Type | Description | Department | Responsible Person/Team
RBS-001 | Human Resources | Project Manager | Responsible for overall project management and coordination | Project Management | Project Manager
RBS-002 | Human Resources | UX/UI Designer | Designs the user interface and user experience | Design | UX/UI Design Team
RBS-003 | Human Resources | Front-End Developer | Implements the front-end of the application | Development | Front-End Development Team
RBS-004 | Human Resources | Back-End Developer | Develops the back-end logic and database integration | Development | Back-End Development Team
RBS-005 | Human Resources | QA Specialist | Conducts testing to ensure the quality and performance of the app | QA | QA Team
RBS-006 | Human Resources | IT Specialist | Manages infrastructure, cloud services, and deployment | IT Infrastructure | IT Support Team
RBS-007 | Human Resources | Security Specialist | Ensures security compliance and implements encryption | Security | Security Team
RBS-008 | Human Resources | Data Scientist/AI Specialist | Develops AI models for supply prediction | Data Science/AI | AI & Data Science Team
RBS-009 | Human Resources | Training Specialist | Develops and conducts user and admin training | Training | Training Team
RBS-010 | Human Resources | Localization Specialist | Translates and localizes content for multi-language support | Localization | Localization Team
RBS-011 | Technical Resources | AWS Cloud Services | Provides cloud infrastructure for hosting and scaling | IT Infrastructure | IT Team
RBS-012 | Technical Resources | API Integration Tools | Tools for integrating third-party APIs | Development | API Development Team
RBS-013 | Technical Resources | Performance Monitoring Tools | Tools like Datadog or New Relic for monitoring performance | IT Infrastructure | IT Team
RBS-014 | Technical Resources | Load Balancers | Manages traffic and load balancing for high availability | IT Infrastructure | IT Team
RBS-015 | Technical Resources | Database Systems (MySQL/PostgreSQL) | Stores application data securely | Database Management | Database Team
RBS-016 | Technical Resources | Backup and Recovery Systems | Provides backup and disaster recovery for critical data | IT Infrastructure | IT Team
RBS-017 | Technical Resources | Mobile Development Tools | Tools for developing the mobile version of the application | Mobile Development | Mobile Development Team
RBS-018 | Technical Resources | AI/ML Frameworks (TensorFlow, PyTorch) | Used for developing AI-powered supply prediction | AI/ML Development | AI & Data Science Team
RBS-019 | Financial Resources | Project Budget | Allocated budget for project development and operations | Finance | Finance Department
RBS-020 | Other Resources | Third-Party Suppliers | Vendors for school supplies | Vendor Management | Procurement Team