## Sheet1
Resource Name | Role | Availability (Days/Week) | Start Date | End Date | Time Off/Leave | Comments
John Smith | Project Manager | 5 | 2024-01-01 | 2024-06-30 | None | Full availability throughout
Emily Taylor | UX/UI Designer | 4 | 2024-03-01 | 2024-04-30 | 1 week (03/15/2024) | Reduced availability due to leave
Michael Johnson | Front-End Developer | 5 | 2024-03-15 | 2024-05-31 | None | Available full-time for the project
Samantha Lee | Back-End Developer | 5 | 2024-03-15 | 2024-05-31 | 3 days (04/10/2024) | Minor leave, but available full-time
Lisa Wong | QA Specialist | 4 | 2024-04-01 | 2024-06-15 | None | Available part-time for testing
David White | IT Specialist | 3 | 2024-03-01 | 2024-06-30 | None | IT support required on-demand
Sarah Green | Data Scientist/AI Specialist | 3 | 2024-04-10 | 2024-05-30 | None | Available for AI model development
Mark Brown | Security Specialist | 3 | 2024-03-01 | 2024-06-30 | 2 days (05/01/2024) | Security audits and reviews
Olivia Turner | Training Specialist | 2 | 2024-05-01 | 2024-06-30 | None | Available for training and support
Thomas Gray | Procurement Officer | 5 | 2024-02-01 | 2024-06-30 | None | Available full-time for procurement