## Sheet1
Project Title: School Supplies Application
Project Manager: John Doe
Date: 01/01/2024
Resource Name/Type | Role/Function/Category | Description/Tasks/Activities | Required Time (Days/Weeks) | Start Date | End Date | Estimated Cost | Comments
John Smith | Project Manager | Oversee project execution, risk management, schedule management | Full project duration | 2024-01-01 | 2024-06-30 | 120000 | Full-time commitment
Emily Taylor | UX/UI Designer | Create wireframes, design user interfaces, and user testing | 2 months (4 days/week) | 2024-03-01 | 2024-04-30 | 50000 | Part-time availability
Michael Johnson | Front-End Developer | Implement front-end features, responsive design | 3 months (5 days/week) | 2024-03-15 | 2024-05-31 | 80000 | Full-time front-end development
Samantha Lee | Back-End Developer | Develop server-side logic, database integration, API development | 3 months (5 days/week) | 2024-03-15 | 2024-05-31 | 85000 | Full-time back-end development
Lisa Wong | QA Specialist | Conduct testing, bug tracking, and quality assurance | 3 months (4 days/week) | 2024-04-01 | 2024-06-30 | 45000 | Part-time for testing phases
David White | IT Specialist | Set up infrastructure, monitor servers, perform backups | On-demand (as needed) | 2024-03-01 | 2024-06-30 | 60000 | IT support throughout the project
Sarah Green | Data Scientist/AI Specialist | Develop and train AI models, perform data analysis | 2 months (3 days/week) | 2024-04-10 | 2024-05-30 | 70000 | Part-time for AI development
Mark Brown | Security Specialist | Implement encryption, perform security audits, manage compliance | Ongoing (3 days/week) | 2024-03-01 | 2024-06-30 | 65000 | On-demand for security tasks
Olivia Turner | Training Specialist | Develop training materials, conduct user and admin training | 1 month (2 days/week) | 2024-05-01 | 2024-06-30 | 30000 | Training phase and post-deployment
Thomas Gray | Procurement Officer | Manage procurement of software, services, and third-party vendors | Full project duration | 2024-02-01 | 2024-06-30 | 50000 | Full-time procurement management
Cloud Hosting Service | Infrastructure | Provide hosting for app deployment, manage traffic and scaling | 1-year subscription | 2024-04-01 | Ongoing | 30000 | Annual subscription
Development Software Tools | Tools for Development | IDEs, version control systems, bug tracking tools | 15 licenses | 2024-03-01 | 2024-06-30 | 10000 | Licenses required for dev team
Security Software | Security Tools | Encryption tools, security audit systems | Annual license | 2024-05-01 | Ongoing | 10000 | Annual cost
Servers & Load Balancers | Infrastructure | Hardware for app hosting and balancing high traffic | 2 servers, 2 load balancers | 2024-03-15 | Ongoing | 20000 | Critical for app deployment