## Sheet1
Project Title: School Supplies Application
Project Manager: John Doe
Date: 01/01/2024
WBS ID | Task Name | Duration (Days) | Start Date | End Date | Milestones | Dependencies | Assigned Team/Person
WBS-001 | User Registration System | 14 | 2024-03-01 | 2024-03-15 | Registration system completed | Design Phase | Development Team
WBS-001.1 | Create Registration UI | 5 | 2024-03-01 | 2024-03-06 | UI design completed | UI/UX Design | UI/UX Team
WBS-001.2 | Build Back-End for Registration | 6 | 2024-03-07 | 2024-03-13 | Back-end system completed | UI Design | Back-End Development Team
WBS-001.3 | Integrate Social Media Logins | 3 | 2024-03-14 | 2024-03-16 | Social media login integrated | Back-End System | Development Team
WBS-001.4 | Test and Deploy Registration | 3 | 2024-03-17 | 2024-03-20 | Registration system live | Integration, Development | QA & Development Teams
WBS-002 | Admin Inventory Management | 20 | 2024-03-16 | 2024-04-05 | Inventory system deployment | Design Phase | Development Team
WBS-002.1 | Create Inventory Dashboard UI | 5 | 2024-03-16 | 2024-03-21 | Dashboard UI completed | UI/UX Design | UI/UX Team
WBS-002.2 | Build Inventory Database | 8 | 2024-03-22 | 2024-03-30 | Inventory database completed | Database Design | Database Team
WBS-002.3 | Implement Low Stock Alerts | 5 | 2024-03-31 | 2024-04-05 | Low-stock alert system completed | Development Phase | Development Team
WBS-002.4 | Test and Deploy Inventory System | 2 | 2024-04-06 | 2024-04-07 | Inventory system live | Development, QA | QA & Development Teams
WBS-003 | Parent Dashboard | 15 | 2024-03-16 | 2024-03-31 | Dashboard completion | Design Phase | Development Team
WBS-003.1 | Design Parent Dashboard UI | 5 | 2024-03-16 | 2024-03-21 | UI design completed | UI/UX Design | UI/UX Team
WBS-003.2 | Build Order History Display | 5 | 2024-03-22 | 2024-03-27 | Order history feature completed | UI Design, Development | Development Team
WBS-003.3 | Build Supply Suggestions System | 5 | 2024-03-28 | 2024-04-02 | Supply suggestion feature completed | Development Phase | Development Team
WBS-003.4 | Test and Deploy Parent Dashboard | 3 | 2024-04-03 | 2024-04-06 | Parent dashboard live | QA Phase | QA & Development Teams
WBS-004 | Secure Payment Integration | 12 | 2024-04-01 | 2024-04-13 | Payment integration completed | Design Phase | Development Team
WBS-004.1 | Design Checkout UI | 4 | 2024-04-01 | 2024-04-05 | Checkout UI completed | UI/UX Design | UI/UX Team
WBS-004.2 | Integrate Payment Gateway | 5 | 2024-04-06 | 2024-04-10 | Payment gateway integrated | Back-End System | Development Team
WBS-004.3 | Implement Data Encryption | 3 | 2024-04-11 | 2024-04-13 | Data encryption completed | Security Systems | Security Team
WBS-004.4 | Test and Deploy Payment System | 2 | 2024-04-14 | 2024-04-15 | Payment system live | QA & Security Phase | QA & Development Teams
WBS-005 | Product Comparison Tool | 10 | 2024-04-06 | 2024-04-16 | Product comparison tool completed | Design Phase | Development Team
WBS-005.1 | Design Comparison Tool UI | 4 | 2024-04-06 | 2024-04-09 | UI design completed | UI/UX Design | UI/UX Team
WBS-005.2 | Build Comparison Engine | 4 | 2024-04-10 | 2024-04-13 | Comparison engine built | Development Phase | Back-End Development Team
WBS-005.3 | Implement Sorting and Filters | 2 | 2024-04-14 | 2024-04-15 | Sorting and filtering completed | Development Phase | Development Team
WBS-005.4 | Test and Deploy Comparison Tool | 2 | 2024-04-16 | 2024-04-17 | Comparison tool live | QA Phase | QA & Development Teams
WBS-006 | Order Tracking System | 14 | 2024-03-17 | 2024-03-31 | Order tracking feature deployed | Design Phase | Development Team
WBS-006.1 | Design Order Tracking UI | 5 | 2024-03-17 | 2024-03-21 | UI design completed | UI/UX Design | UI/UX Team
WBS-006.2 | Build Order Tracking Engine | 6 | 2024-03-22 | 2024-03-28 | Order tracking engine completed | Development Phase | Back-End Development Team
WBS-006.3 | Test and Deploy Order Tracking | 3 | 2024-03-29 | 2024-03-31 | Order tracking system live | QA Phase | QA & Development Teams
WBS-007 | AI-Powered Supply Prediction | 30 | 2024-04-05 | 2024-05-05 | AI prediction system completed | Data Analysis, AI Development | AI & Development Team
WBS-007.1 | Data Collection and Analysis | 10 | 2024-04-05 | 2024-04-15 | Data collection completed | Data Science | Data Science Team
WBS-007.2 | AI Model Training | 15 | 2024-04-16 | 2024-05-01 | AI model trained | AI Development Phase | AI Team
WBS-007.3 | Integrate AI Model with Platform | 5 | 2024-05-02 | 2024-05-07 | AI model integrated | AI Development Phase | AI & Development Teams
WBS-007.4 | Test and Optimize AI Predictions | 5 | 2024-05-08 | 2024-05-12 | AI system optimized | QA & AI Development | AI & QA Teams
WBS-008 | Role-Based Access Control | 14 | 2024-03-25 | 2024-04-08 | Role-based access control completed | Design Phase | Development Team
WBS-008.1 | Define User Roles and Permissions | 4 | 2024-03-25 | 2024-03-28 | Roles and permissions defined | Requirement Gathering | Project Management Team
WBS-008.2 | Build Access Control System | 8 | 2024-03-29 | 2024-04-06 | Access control system completed | Development Phase | Back-End Development Team
WBS-008.3 | Integrate with Front-End | 4 | 2024-04-02 | 2024-04-07 | UI integration completed | Front-End Design | Front-End Development Team
WBS-008.4 | Test and Deploy Access Control | 3 | 2024-04-08 | 2024-04-10 | Access control system live | QA Phase | QA & Development Teams
WBS-009 | In-App Chat Support | 8 | 2024-03-29 | 2024-04-06 | In-app chat feature completed | Design Phase | Development Team
WBS-009.1 | Design Chat UI | 3 | 2024-03-29 | 2024-04-01 | Chat UI design completed | UI/UX Design | UI/UX Team
WBS-009.2 | Implement Chat Back-End | 4 | 2024-04-02 | 2024-04-05 | Chat back-end completed | Development Phase | Back-End Development Team
WBS-009.3 | Test and Deploy Chat System | 1 | 2024-04-06 | 2024-04-06 | Chat system deployed | QA Phase | QA & Development Teams
WBS-010 | Bulk Ordering System | 12 | 2024-04-02 | 2024-04-14 | Bulk ordering system deployed | Design Phase | Development Team
WBS-010.1 | Design Bulk Ordering UI | 4 | 2024-04-02 | 2024-04-06 | Bulk ordering UI completed | UI/UX Design | UI/UX Team
WBS-010.2 | Build Bulk Ordering Back-End | 6 | 2024-04-07 | 2024-04-12 | Back-end system completed | Development Phase | Back-End Development Team
WBS-010.3 | Test and Deploy Bulk Ordering | 2 | 2024-04-13 | 2024-04-14 | Bulk ordering system live | QA Phase | QA & Development Teams
WBS-011 | Product Search and Filter | 12 | 2024-04-10 | 2024-04-22 | Product search system completed | Design Phase | Development Team
WBS-011.1 | Design Product Search UI | 4 | 2024-04-10 | 2024-04-14 | Product search UI completed | UI/UX Design | UI/UX Team
WBS-011.2 | Implement Search Engine | 6 | 2024-04-15 | 2024-04-21 | Search engine completed | Development Phase | Back-End Development Team
WBS-011.3 | Add Filtering Options | 2 | 2024-04-22 | 2024-04-23 | Filtering system completed | Development Phase | Development Team
WBS-011.4 | Test and Deploy Search System | 2 | 2024-04-24 | 2024-04-25 | Product search system live | QA Phase | QA & Development Teams
WBS-012 | Reports Dashboard (Admin) | 20 | 2024-04-15 | 2024-05-05 | Reporting tools completed | Design Phase | Development Team
WBS-012.1 | Design Reports Dashboard UI | 6 | 2024-04-15 | 2024-04-21 | Reports dashboard UI completed | UI/UX Design | UI/UX Team
WBS-012.2 | Implement Report Generation | 10 | 2024-04-22 | 2024-05-01 | Report generation system completed | Development Phase | Back-End Development Team
WBS-012.3 | Integrate with Supplier Data | 4 | 2024-05-02 | 2024-05-05 | Supplier data integration completed | Development Phase | Development Team
WBS-012.4 | Test and Deploy Reports Dashboard | 4 | 2024-05-06 | 2024-05-09 | Reports dashboard deployed | QA Phase | QA & Development Teams
WBS-013 | Notifications and Alerts | 10 | 2024-03-21 | 2024-03-31 | Notification system deployment | Design Phase | Development Team
WBS-013.1 | Design Notification UI | 3 | 2024-03-21 | 2024-03-24 | Notification UI design completed | UI/UX Design | UI/UX Team
WBS-013.2 | Implement Notification Logic | 5 | 2024-03-25 | 2024-03-29 | Notification system implemented | Development Phase | Back-End Development Team
WBS-013.3 | Set Up Push Notifications | 2 | 2024-03-30 | 2024-03-31 | Push notification system completed | Development Phase | Mobile Development Team
WBS-013.4 | Test and Deploy Notification System | 2 | 2024-04-01 | 2024-04-02 | Notification system deployed | QA Phase | QA & Development Teams
WBS-014 | Supplier Product Management | 15 | 2024-04-15 | 2024-04-30 | Supplier product management completed | Design Phase | Development Team
WBS-014.1 | Design Supplier Product UI | 5 | 2024-04-15 | 2024-04-20 | Supplier product UI completed | UI/UX Design | UI/UX Team
WBS-014.2 | Build Product Management Back-End | 7 | 2024-04-21 | 2024-04-28 | Product management back-end completed | Development Phase | Back-End Development Team
WBS-014.3 | Implement Stock Level Management | 3 | 2024-04-29 | 2024-04-30 | Stock level management completed | Development Phase | Development Team
WBS-014.4 | Test and Deploy Product Management | 3 | 2024-05-01 | 2024-05-03 | Product management system deployed | QA Phase | QA & Development Teams
WBS-015 | Multi-Language Support | 8 | 2024-04-20 | 2024-04-28 | Multi-language support completed | Development Phase | Development Team
WBS-015.1 | Language Selection UI | 2 | 2024-04-20 | 2024-04-22 | Language selection UI completed | UI/UX Design | UI/UX Team
WBS-015.2 | Translation and Localization | 4 | 2024-04-23 | 2024-04-26 | Content localization completed | Localization | Localization Team
WBS-015.3 | Integrate Multi-Language Back-End | 2 | 2024-04-27 | 2024-04-28 | Multi-language integration completed | Back-End Development | Development Team
WBS-015.4 | Test and Deploy Multi-Language | 2 | 2024-04-29 | 2024-04-30 | Multi-language support deployed | QA Phase | QA & Development Teams
WBS-016 | Product Wishlist/Favorites | 10 | 2024-04-22 | 2024-05-02 | Wishlist system deployed | Design Phase | Development Team
WBS-016.1 | Design Wishlist UI | 3 | 2024-04-22 | 2024-04-25 | Wishlist UI completed | UI/UX Design | UI/UX Team
WBS-016.2 | Build Wishlist Back-End | 5 | 2024-04-26 | 2024-05-01 | Wishlist back-end completed | Back-End Development | Back-End Development Team
WBS-016.3 | Integrate with Cart System | 2 | 2024-05-01 | 2024-05-02 | Wishlist-cart integration completed | Development Phase | Development Team
WBS-016.4 | Test and Deploy Wishlist Feature | 2 | 2024-05-03 | 2024-05-05 | Wishlist system deployed | QA Phase | QA & Development Teams
WBS-017 | Data Encryption for Security | 14 | 2024-04-25 | 2024-05-09 | Encryption system completed | Development Phase | Security Team
WBS-017.1 | Encrypt Payment Data | 6 | 2024-04-25 | 2024-05-01 | Payment data encryption completed | Security Systems | Security & Development Team
WBS-017.2 | Encrypt Personal Information | 6 | 2024-05-02 | 2024-05-08 | Personal data encryption completed | Security Systems | Security Team
WBS-017.3 | Test and Deploy Encryption System | 2 | 2024-05-09 | 2024-05-10 | Encryption system deployed | QA Phase | QA & Security Teams
WBS-018 | Recurring Orders Setup (Parent) | 12 | 2024-05-01 | 2024-05-13 | Recurring order system deployed | Design Phase | Development Team
WBS-018.1 | Design Recurring Order UI | 4 | 2024-05-01 | 2024-05-05 | Recurring order UI completed | UI/UX Design | UI/UX Team
WBS-018.2 | Build Recurring Order Back-End | 6 | 2024-05-06 | 2024-05-11 | Recurring order back-end completed | Development Phase | Back-End Development Team
WBS-018.3 | Test and Deploy Recurring Order | 2 | 2024-05-12 | 2024-05-13 | Recurring order system live | QA Phase | QA & Development Teams
WBS-019 | Admin Multi-Location Dashboard | 14 | 2024-06-10 | 2024-06-24 | Multi-location dashboard completed | Design Phase | Development Team
WBS-019.1 | Design Location Selection UI | 5 | 2024-06-10 | 2024-06-15 | Location selection UI completed | UI/UX Design | UI/UX Team
WBS-019.2 | Implement Location Data Tracking | 6 | 2024-06-16 | 2024-06-21 | Location data tracking completed | Development Phase | Back-End Development Team
WBS-019.3 | Test and Deploy Multi-Location Dashboard | 3 | 2024-06-22 | 2024-06-24 | Multi-location dashboard deployed | QA Phase | QA & Development Teams
WBS-020 | Voice-Assisted Search | 14 | 2024-06-25 | 2024-07-09 | Voice search feature completed | Development Phase | Development Team
WBS-020.1 | Design Voice Search UI | 5 | 2024-06-25 | 2024-06-30 | Voice search UI completed | UI/UX Design | UI/UX Team
WBS-020.2 | Build Voice Recognition Back-End | 7 | 2024-07-01 | 2024-07-08 | Voice recognition back-end completed | Development Phase | Back-End Development Team
WBS-020.3 | Test and Deploy Voice Search | 3 | 2024-07-09 | 2024-07-11 | Voice search system deployed | QA Phase | QA & Development Teams
WBS-021 | Automatic Server Scaling | 18 | 2024-07-10 | 2024-07-28 | Auto-scaling system completed | IT Infrastructure | IT & Cloud Infrastructure Team
WBS-021.1 | Set Up Cloud Infrastructure | 8 | 2024-07-10 | 2024-07-18 | Cloud infrastructure set up | Infrastructure Design | IT Team
WBS-021.2 | Implement Auto-Scaling Rules | 8 | 2024-07-19 | 2024-07-27 | Auto-scaling logic completed | IT Infrastructure | IT & Development Teams
WBS-021.3 | Test and Monitor Auto-Scaling | 3 | 2024-07-28 | 2024-07-30 | Auto-scaling system deployed | QA Phase | QA & IT Teams
WBS-022 | Supplier Performance Evaluation | 14 | 2024-07-15 | 2024-07-29 | Supplier evaluation tool completed | Development Phase | Development Team
WBS-022.1 | Design Supplier Evaluation UI | 5 | 2024-07-15 | 2024-07-20 | Supplier evaluation UI completed | UI/UX Design | UI/UX Team
WBS-022.2 | Build Evaluation Metrics System | 7 | 2024-07-21 | 2024-07-27 | Evaluation metrics system completed | Development Phase | Back-End Development Team
WBS-022.3 | Test and Deploy Supplier Evaluation | 3 | 2024-07-28 | 2024-07-30 | Evaluation system deployed | QA Phase | QA & Development Teams
WBS-023 | Vendor Feedback and Rating System | 10 | 2024-07-30 | 2024-08-10 | Vendor feedback tool completed | Development Phase | Development Team
WBS-023.1 | Design Feedback and Rating UI | 4 | 2024-07-30 | 2024-08-03 | Feedback UI completed | UI/UX Design | UI/UX Team
WBS-023.2 | Implement Rating System Logic | 5 | 2024-08-04 | 2024-08-09 | Rating system logic completed | Development Phase | Back-End Development Team
WBS-023.3 | Test and Deploy Feedback System | 2 | 2024-08-10 | 2024-08-11 | Vendor feedback system deployed | QA Phase | QA & Development Teams
WBS-024 | Custom Reporting Tool | 12 | 2024-08-01 | 2024-08-13 | Custom reporting tool completed | Design Phase | Development Team
WBS-024.1 | Design Custom Report UI | 5 | 2024-08-01 | 2024-08-06 | Custom report UI completed | UI/UX Design | UI/UX Team
WBS-024.2 | Implement Report Generation Logic | 5 | 2024-08-07 | 2024-08-12 | Report generation system completed | Development Phase | Back-End Development Team
WBS-024.3 | Test and Deploy Custom Report Tool | 2 | 2024-08-13 | 2024-08-15 | Custom reporting tool deployed | QA Phase | QA & Development Teams
WBS-025 | Loyalty Programs for User Retention | 14 | 2024-08-10 | 2024-08-24 | Loyalty program deployed | Development Phase | Development Team
WBS-025.1 | Design Loyalty Program UI | 5 | 2024-08-10 | 2024-08-15 | Loyalty program UI completed | UI/UX Design | UI/UX Team
WBS-025.2 | Build Loyalty Points System | 7 | 2024-08-16 | 2024-08-22 | Loyalty points system completed | Development Phase | Back-End Development Team
WBS-025.3 | Integrate Loyalty Offers and Rewards | 5 | 2024-08-16 | 2024-08-21 | Offers and rewards feature completed | Development Phase | Development Team
WBS-025.4 | Test and Deploy Loyalty Program | 2 | 2024-08-23 | 2024-08-24 | Loyalty program deployed | QA Phase | QA & Development Teams
WBS-026 | Order Splitting Across Suppliers | 10 | 2024-08-20 | 2024-08-30 | Order splitting system completed | Design Phase | Development Team
WBS-026.1 | Design Order Splitting UI | 4 | 2024-08-20 | 2024-08-24 | Order splitting UI completed | UI/UX Design | UI/UX Team
WBS-026.2 | Implement Splitting Logic | 6 | 2024-08-25 | 2024-08-30 | Order splitting logic completed | Development Phase | Back-End Development Team
WBS-026.3 | Test and Deploy Order Splitting | 2 | 2024-09-01 | 2024-09-02 | Order splitting system deployed | QA Phase | QA & Development Teams
WBS-027 | Discount and Promotions Feature | 12 | 2024-08-28 | 2024-09-09 | Discounts and promotions feature deployed | Development Phase | Development Team
WBS-027.1 | Design Discounts UI | 4 | 2024-08-28 | 2024-09-01 | Discounts UI completed | UI/UX Design | UI/UX Team
WBS-027.2 | Build Discount Logic | 6 | 2024-09-02 | 2024-09-08 | Discount logic completed | Development Phase | Back-End Development Team
WBS-027.3 | Test and Deploy Discounts Feature | 2 | 2024-09-09 | 2024-09-11 | Discount system deployed | QA Phase | QA & Development Teams
WBS-028 | Shopping Cart and Checkout System | 20 | 2024-09-10 | 2024-09-30 | Shopping cart and checkout system deployed | Development Phase | Development Team
WBS-028.1 | Design Shopping Cart UI | 6 | 2024-09-10 | 2024-09-16 | Shopping cart UI completed | UI/UX Design | UI/UX Team
WBS-028.2 | Build Secure Checkout Logic | 10 | 2024-09-17 | 2024-09-27 | Secure checkout logic completed | Development Phase | Back-End Development Team
WBS-028.3 | Test and Deploy Shopping Cart | 3 | 2024-09-28 | 2024-09-30 | Shopping cart and checkout system deployed | QA Phase | QA & Development Teams
WBS-029 | AI-Powered Supply Prediction Tool | 18 | 2024-10-01 | 2024-10-18 | AI prediction system completed | AI & Development Phase | AI & Development Teams
WBS-029.1 | Data Collection and Model Training | 7 | 2024-10-01 | 2024-10-08 | AI model training completed | Data Science & AI Teams | Data Science & AI Teams
WBS-029.2 | Build Prediction Engine | 7 | 2024-10-09 | 2024-10-16 | Prediction engine completed | Development Phase | Back-End Development Team
WBS-029.3 | Test and Deploy Prediction Tool | 2 | 2024-10-17 | 2024-10-18 | Prediction tool deployed | QA Phase | QA & Development Teams
WBS-030 | ADA Compliance for Accessibility | 14 | 2024-10-20 | 2024-11-03 | ADA-compliant system completed | Development Phase | Development & Accessibility Teams
WBS-030.1 | Conduct Accessibility Audit | 4 | 2024-10-20 | 2024-10-24 | Accessibility audit completed | Accessibility Team | Accessibility Team
WBS-030.2 | Implement ADA Compliance Features | 8 | 2024-10-25 | 2024-11-02 | ADA compliance features completed | Development Phase | Development Team
WBS-030.3 | Test and Deploy ADA-Compliant Features | 2 | 2024-11-03 | 2024-11-04 | ADA-compliant system deployed | QA Phase | QA & Accessibility Teams
WBS-031 | Load Balancing for High Traffic | 12 | 2024-04-01 | 2024-04-13 | Load balancing system deployed | IT Infrastructure | IT & Cloud Infrastructure Team
WBS-031.1 | Design Load Balancing Logic | 5 | 2024-04-01 | 2024-04-06 | Load balancing logic completed | IT Team | IT Team
WBS-031.2 | Implement Load Balancing | 5 | 2024-04-07 | 2024-04-12 | Load balancers implemented | Development Phase | IT Team
WBS-031.3 | Test and Deploy Load Balancing | 2 | 2024-04-13 | 2024-04-14 | Load balancing system deployed | QA Phase | QA & IT Teams
WBS-032 | Database Partitioning | 10 | 2024-04-15 | 2024-04-25 | Database partitioning completed | Database Development Phase | Database Development Team
WBS-032.1 | Analyze Data for Partitioning | 3 | 2024-04-15 | 2024-04-18 | Data analysis completed | Database Team | Database Team
WBS-032.2 | Implement Database Partitioning | 5 | 2024-04-19 | 2024-04-24 | Partitioning implemented | Development Phase | Database Development Team
WBS-032.3 | Test and Deploy Partitioning | 2 | 2024-04-25 | 2024-04-26 | Partitioned database deployed | QA Phase | QA & Database Teams
WBS-033 | Multi-Factor Authentication (MFA) | 14 | 2024-05-01 | 2024-05-15 | MFA system deployed | Development & Security Teams | Security & Development Teams
WBS-033.1 | Design MFA UI | 4 | 2024-05-01 | 2024-05-05 | MFA UI completed | UI/UX Design | UI/UX Team
WBS-033.2 | Implement MFA Back-End | 7 | 2024-05-06 | 2024-05-13 | MFA back-end completed | Development Phase | Back-End Development Team
WBS-033.3 | Test and Deploy MFA | 2 | 2024-05-14 | 2024-05-15 | MFA system deployed | QA Phase | QA & Security Teams
WBS-034 | Push Notifications for Mobile | 12 | 2024-06-15 | 2024-06-27 | Push notification system deployed | Development Phase | Development Team
WBS-034.1 | Design Notification UI | 4 | 2024-06-15 | 2024-06-19 | Notification UI completed | UI/UX Design | UI/UX Team
WBS-034.2 | Implement Push Notification Logic | 6 | 2024-06-20 | 2024-06-26 | Push notification logic completed | Development Phase | Back-End Development Team
WBS-034.3 | Test and Deploy Push Notifications | 2 | 2024-06-27 | 2024-06-28 | Push notification system deployed | QA Phase | QA & Development Teams
WBS-035 | Secure API Integration | 14 | 2024-06-30 | 2024-07-14 | Secure API system deployed | Security & Development Teams | Development Team
WBS-035.1 | Design API Security Protocols | 5 | 2024-06-30 | 2024-07-05 | API security protocols completed | Security Systems | Security & Development Teams
WBS-035.2 | Implement Secure API Endpoints | 7 | 2024-07-06 | 2024-07-12 | API endpoints implemented | Development Phase | Back-End Development Team
WBS-035.3 | Test and Deploy API Integration | 2 | 2024-07-13 | 2024-07-14 | API integration system deployed | QA Phase | QA & Development Teams
WBS-036 | Performance Optimization | 15 | 2024-07-15 | 2024-07-30 | Performance optimization completed | IT & Development Teams | Development Team
WBS-036.1 | Analyze System Bottlenecks | 6 | 2024-07-15 | 2024-07-21 | Bottleneck analysis completed | Development Team | IT & Development Teams
WBS-036.2 | Implement Performance Enhancements | 7 | 2024-07-22 | 2024-07-29 | Performance optimizations completed | IT & Development Teams | IT & Development Teams
WBS-036.3 | Test and Deploy Optimized System | 2 | 2024-07-30 | 2024-07-31 | Optimized system deployed | QA & Development Teams | QA & Development Teams
WBS-037 | Data Backup and Recovery | 14 | 2024-08-01 | 2024-08-15 | Backup and recovery system deployed | IT & Development Teams | IT & Development Teams
WBS-037.1 | Design Backup Strategy | 4 | 2024-08-01 | 2024-08-05 | Backup strategy completed | IT Team | IT Team
WBS-037.2 | Implement Backup System | 7 | 2024-08-06 | 2024-08-12 | Backup system implemented | IT Team | IT Team
WBS-037.3 | Test and Monitor Backup System | 3 | 2024-08-13 | 2024-08-15 | Backup system deployed | QA & IT Teams | QA & IT Teams
WBS-038 | Mobile App Responsiveness | 15 | 2024-08-16 | 2024-08-31 | Mobile responsiveness achieved | UI/UX & Development Teams | UI/UX & Development Teams
WBS-038.1 | Design Responsive Layout | 6 | 2024-08-16 | 2024-08-22 | Responsive UI design completed | UI/UX Team | UI/UX Team
WBS-038.2 | Implement Responsive Front-End | 6 | 2024-08-23 | 2024-08-29 | Responsive front-end completed | Front-End Development Team | Front-End Development Team
WBS-038.3 | Test Responsiveness on Devices | 3 | 2024-08-30 | 2024-08-31 | Mobile responsiveness deployed | QA & Development Teams | QA & Development Teams
WBS-039 | ADA Compliance for Accessibility | 14 | 2024-09-01 | 2024-09-15 | ADA compliance achieved | Accessibility & Development Teams | Accessibility Team
WBS-039.1 | Conduct ADA Accessibility Audit | 4 | 2024-09-01 | 2024-09-05 | Audit completed | Accessibility Team | Accessibility Team
WBS-039.2 | Implement ADA Compliance Features | 8 | 2024-09-06 | 2024-09-14 | ADA compliance features completed | Development Phase | Development Team
WBS-039.3 | Test and Deploy ADA Features | 2 | 2024-09-15 | 2024-09-16 | ADA compliance achieved | QA & Development Teams | QA & Development Teams
WBS-040 | Group Purchasing for Bulk Orders | 14 | 2024-09-17 | 2024-10-01 | Group purchasing feature deployed | Development Phase | Development Team
WBS-040.1 | Design Group Purchasing UI | 5 | 2024-09-17 | 2024-09-22 | Group purchasing UI completed | UI/UX Team | UI/UX Team
WBS-040.2 | Implement Group Purchasing Logic | 7 | 2024-09-23 | 2024-09-30 | Group purchasing logic implemented | Development Phase | Back-End Development Team
WBS-040.3 | Test and Deploy Group Purchasing | 2 | 2024-10-01 | 2024-10-03 | Group purchasing system deployed | QA & Development Teams | QA & Development Teams
WBS-041 | Forgot Password System | 10 | 2024-10-04 | 2024-10-14 | Forgot password system deployed | Development & Security Teams | Development & Security Teams
WBS-041.1 | Design Forgot Password UI | 4 | 2024-10-04 | 2024-10-08 | Forgot password UI completed | UI/UX Team | UI/UX Team
WBS-041.2 | Implement Reset Logic | 5 | 2024-10-09 | 2024-10-13 | Password reset logic completed | Development Phase | Back-End Development Team
WBS-041.3 | Test and Deploy Forgot Password System | 2 | 2024-10-14 | 2024-10-16 | Forgot password system deployed | QA & Development Teams | QA & Development Teams