## Sheet1
Project: School Supplies App
Date: 05/27/2024
Project Manager: John Doe
WBS ID | Task Name | Duration (Days) | Team/Person Responsible | Labor Cost Estimate (USD) | Material/Resource Cost Estimate (USD) | Total Cost Estimate (USD) | Notes
WBS-001 | User Registration System | 14 | Development Team | 5000 | 2000 | 7000 | Includes UI design, back-end, and testing
WBS-001.1 | Create Registration UI | 5 | UI/UX Team | 2000 | 500 | 2500 | UI/UX design cost
WBS-001.2 | Build Back-End for Registration | 6 | Back-End Development Team | 3000 | 1000 | 4000 | Backend API development
WBS-001.3 | Integrate Social Media Logins | 3 | Development Team | 1500 | 500 | 2000 | API Integration for social logins
WBS-001.4 | Test and Deploy Registration | 3 | QA & Development Teams | 500 | 0 | 500 | Testing and deployment
WBS-002 | Admin Inventory Management | 20 | Development Team | 7000 | 3000 | 10000 | Inventory system including alerts
WBS-002.1 | Create Inventory Dashboard UI | 5 | UI/UX Team | 2500 | 500 | 3000 | Dashboard UI design
WBS-002.2 | Build Inventory Database | 8 | Database Team | 4000 | 1000 | 5000 | Database setup
WBS-002.3 | Implement Low Stock Alerts | 5 | Development Team | 2500 | 500 | 3000 | Alerts feature implementation
WBS-002.4 | Test and Deploy Inventory System | 2 | QA & Development Teams | 500 | 0 | 500 | Testing and deployment
WBS-003 | Parent Dashboard | 15 | Development Team | 6000 | 2500 | 8500 | Parent-specific dashboard development
WBS-003.1 | Design Parent Dashboard UI | 5 | UI/UX Team | 2500 | 500 | 3000 | UI/UX design
WBS-003.2 | Build Order History Display | 5 | Development Team | 2000 | 1000 | 3000 | Order history module
WBS-003.3 | Build Supply Suggestions System | 5 | Development Team | 2000 | 1000 | 3000 | Supply suggestion system
WBS-003.4 | Test and Deploy Parent Dashboard | 3 | QA & Development Teams | 500 | 0 | 500 | Testing and deployment
WBS-004 | Secure Payment Integration | 12 | Development Team | 7000 | 3000 | 10000 | Payment integration and encryption
WBS-004.1 | Design Checkout UI | 4 | UI/UX Team | 2000 | 500 | 2500 | Checkout UI design
WBS-004.2 | Integrate Payment Gateway | 5 | Development Team | 3000 | 1500 | 4500 | Payment gateway integration
WBS-004.3 | Implement Data Encryption | 3 | Security Team | 2000 | 500 | 2500 | Encryption of payment data
WBS-004.4 | Test and Deploy Payment System | 2 | QA & Development Teams | 500 | 0 | 500 | Testing and deployment
WBS-005 | Product Comparison Tool | 10 | Development Team | 5000 | 2000 | 7000 | Comparison feature deployment
WBS-005.1 | Design Comparison Tool UI | 4 | UI/UX Team | 2000 | 500 | 2500 | UI design for comparison tool
WBS-005.2 | Build Comparison Engine | 4 | Back-End Development Team | 2500 | 1000 | 3500 | Comparison engine development
WBS-005.3 | Implement Sorting and Filters | 2 | Development Team | 500 | 500 | 1000 | Sorting/filter functionality
WBS-005.4 | Test and Deploy Comparison Tool | 2 | QA & Development Teams | 500 | 0 | 500 | Testing and deployment
WBS-006 | Order Tracking System | 14 | Development Team | 6000 | 2500 | 8500 | Order tracking system deployment
WBS-006.1 | Design Order Tracking UI | 5 | UI/UX Team | 2500 | 500 | 3000 | Order tracking UI design
WBS-006.2 | Build Order Tracking Engine | 6 | Back-End Development Team | 3000 | 1500 | 4500 | Engine for tracking orders
WBS-006.3 | Test and Deploy Order Tracking | 3 | QA & Development Teams | 500 | 500 | 1000 | Testing and deployment
WBS-007 | AI-Powered Supply Prediction | 30 | AI & Development Teams | 12000 | 5000 | 17000 | AI prediction model integration
WBS-007.1 | Data Collection and Analysis | 10 | Data Science Team | 5000 | 2000 | 7000 | Data collection and analysis
WBS-007.2 | AI Model Training | 15 | AI Team | 6000 | 2500 | 8500 | AI model training
WBS-007.3 | Integrate AI Model with Platform | 5 | AI & Development Teams | 2000 | 500 | 2500 | AI model integration
WBS-007.4 | Test and Optimize AI Predictions | 5 | AI & QA Teams | 1000 | 500 | 1500 | AI optimization and testing
WBS-008 | Role-Based Access Control | 14 | Development Team | 5500 | 2000 | 7500 | Role-based access system
WBS-008.1 | Define User Roles and Permissions | 4 | Project Management Team | 1500 | 500 | 2000 | Role definitions and permissions
WBS-008.2 | Build Access Control System | 8 | Back-End Development Team | 3500 | 1000 | 4500 | Access control system
WBS-008.3 | Integrate with Front-End | 4 | Front-End Development Team | 1500 | 500 | 2000 | Front-end integration
WBS-008.4 | Test and Deploy Access Control | 3 | QA & Development Teams | 500 | 0 | 500 | Testing and deployment
WBS-009 | In-App Chat Support | 8 | Development Team | 3500 | 1000 | 4500 | In-app chat system deployment
WBS-009.1 | Design Chat UI | 3 | UI/UX Team | 1500 | 500 | 2000 | Chat UI design
WBS-009.2 | Implement Chat Back-End | 4 | Back-End Development Team | 2000 | 500 | 2500 | Chat back-end implementation
WBS-009.3 | Test and Deploy Chat System | 1 | QA & Development Teams | 500 | 0 | 500 | Testing and deployment
WBS-010 | Bulk Ordering System | 12 | Development Team | 5000 | 2000 | 7000 | Bulk ordering system
WBS-010.1 | Design Bulk Ordering UI | 4 | UI/UX Team | 2000 | 500 | 2500 | Bulk ordering UI design
WBS-010.2 | Build Bulk Ordering Back-End | 6 | Back-End Development Team | 3000 | 1000 | 4000 | Bulk ordering back-end
WBS-010.3 | Test and Deploy Bulk Ordering | 2 | QA & Development Teams | 500 | 500 | 1000 | Testing and deployment
WBS-011 | Product Search and Filter | 12 | Development Team | 5500 | 2000 | 7500 | Search and filter system
WBS-011.1 | Design Product Search UI | 4 | UI/UX Team | 2000 | 500 | 2500 | Product search UI design
WBS-011.2 | Implement Search Engine | 6 | Back-End Development Team | 3000 | 1000 | 4000 | Search engine implementation
WBS-011.3 | Add Filtering Options | 2 | Development Team | 500 | 500 | 1000 | Filter options
WBS-011.4 | Test and Deploy Search System | 2 | QA & Development Teams | 500 | 500 | 1000 | Testing and deployment
WBS-012 | Reports Dashboard (Admin) | 20 | Development Team | 8000 | 3000 | 11000 | Admin reports dashboard deployment
WBS-012.1 | Design Reports Dashboard UI | 6 | UI/UX Team | 3000 | 500 | 3500 | Reports dashboard UI design
WBS-012.2 | Implement Report Generation | 10 | Back-End Development Team | 4000 | 1500 | 5500 | Report generation functionality
WBS-012.3 | Integrate with Supplier Data | 4 | Development Team | 1500 | 500 | 2000 | Supplier data integration
WBS-012.4 | Test and Deploy Reports Dashboard | 4 | QA & Development Teams | 500 | 500 | 1000 | Testing and deployment
WBS-013 | Notifications and Alerts | 10 | Development Team | 4000 | 1500 | 5500 | Notification system deployment
WBS-013.1 | Design Notification UI | 3 | UI/UX Team | 1500 | 500 | 2000 | Notification UI design
WBS-013.2 | Implement Notification Logic | 5 | Back-End Development Team | 2500 | 1000 | 3500 | Notification logic implementation
WBS-013.3 | Set Up Push Notifications | 2 | Mobile Development Team | 500 | 500 | 1000 | Push notification setup
WBS-013.4 | Test and Deploy Notification System | 2 | QA & Development Teams | 500 | 500 | 1000 | Testing and deployment
WBS-014 | Supplier Product Management | 15 | Development Team | 6000 | 2500 | 8500 | Supplier product management system
WBS-014.1 | Design Supplier Product UI | 5 | UI/UX Team | 2500 | 500 | 3000 | Supplier product UI design
WBS-014.2 | Build Product Management Back-End | 7 | Back-End Development Team | 3000 | 1500 | 4500 | Product management back-end
WBS-014.3 | Implement Stock Level Management | 3 | Development Team | 1000 | 500 | 1500 | Stock management system
WBS-014.4 | Test and Deploy Product Management | 3 | QA & Development Teams | 500 | 500 | 1000 | Testing and deployment
WBS-015 | Multi-Language Support | 8 | Development Team | 4000 | 2000 | 6000 | Multi-language support deployment
WBS-015.1 | Language Selection UI | 2 | UI/UX Team | 1000 | 500 | 1500 | Language selection UI design
WBS-015.2 | Translation and Localization | 4 | Localization Team | 2000 | 1000 | 3000 | Content localization
WBS-015.3 | Integrate Multi-Language Back-End | 2 | Development Team | 1000 | 500 | 1500 | Multi-language back-end
WBS-015.4 | Test and Deploy Multi-Language | 2 | QA & Development Teams | 500 | 500 | 1000 | Testing and deployment
WBS-016 | Product Wishlist/Favorites | 10 | Development Team | 4000 | 1500 | 5500 | Wishlist and favorites feature
WBS-016.1 | Design Wishlist UI | 3 | UI/UX Team | 1500 | 500 | 2000 | Wishlist UI design
WBS-016.2 | Build Wishlist Back-End | 5 | Back-End Development Team | 2500 | 1000 | 3500 | Wishlist back-end
WBS-016.3 | Integrate with Cart System | 2 | Development Team | 500 | 500 | 1000 | Cart integration
WBS-016.4 | Test and Deploy Wishlist Feature | 2 | QA & Development Teams | 500 | 500 | 1000 | Testing and deployment
WBS-017 | Data Encryption for Security | 14 | Security & Development Teams | 5500 | 2000 | 7500 | Data encryption system
WBS-017.1 | Encrypt Payment Data | 6 | Security Team | 3000 | 1000 | 4000 | Payment data encryption
WBS-017.2 | Encrypt Personal Information | 6 | Security Team | 2500 | 1000 | 3500 | Personal data encryption
WBS-017.3 | Test and Deploy Encryption System | 2 | QA & Security Teams | 500 | 500 | 1000 | Testing and deployment
WBS-018 | Recurring Orders Setup (Parent) | 12 | Development Team | 5000 | 2000 | 7000 | Recurring order system
WBS-018.1 | Design Recurring Order UI | 4 | UI/UX Team | 2000 | 500 | 2500 | Recurring order UI design
WBS-018.2 | Build Recurring Order Back-End | 6 | Back-End Development Team | 3000 | 1000 | 4000 | Recurring order back-end
WBS-018.3 | Test and Deploy Recurring Order | 2 | QA & Development Teams | 500 | 500 | 1000 | Testing and deployment
WBS-019 | Admin Multi-Location Dashboard | 14 | Development Team | 6000 | 2500 | 8500 | Multi-location admin dashboard
WBS-019.1 | Design Location Selection UI | 5 | UI/UX Team | 2500 | 500 | 3000 | UI for location selection
WBS-019.2 | Implement Location Data Tracking | 6 | Back-End Development Team | 3000 | 1500 | 4500 | Data tracking across locations
WBS-019.3 | Test and Deploy Multi-Location Dashboard | 3 | QA & Development Teams | 500 | 500 | 1000 | Testing and deployment
WBS-020 | Voice-Assisted Search | 14 | Development Team | 6500 | 2500 | 9000 | Voice search feature implementation
WBS-020.1 | Design Voice Search UI | 5 | UI/UX Team | 2500 | 500 | 3000 | Voice search UI design
WBS-020.2 | Build Voice Recognition Back-End | 7 | Back-End Development Team | 3500 | 1500 | 5000 | Voice recognition back-end
WBS-020.3 | Test and Deploy Voice Search | 3 | QA & Development Teams | 500 | 500 | 1000 | Testing and deployment
WBS-021 | Automatic Server Scaling | 18 | IT & Cloud Infrastructure Team | 7500 | 3000 | 10500 | Auto-scaling for cloud servers
WBS-021.1 | Set Up Cloud Infrastructure | 8 | IT Team | 3500 | 1500 | 5000 | Cloud infrastructure setup
WBS-021.2 | Implement Auto-Scaling Rules | 8 | IT & Development Teams | 3500 | 1000 | 4500 | Scaling rules and monitoring
WBS-021.3 | Test and Monitor Auto-Scaling | 3 | QA & IT Teams | 500 | 500 | 1000 | Testing and deployment
WBS-022 | Supplier Performance Evaluation | 14 | Development Team | 6500 | 2500 | 9000 | Supplier evaluation tools
WBS-022.1 | Design Supplier Evaluation UI | 5 | UI/UX Team | 2500 | 500 | 3000 | Evaluation UI design
WBS-022.2 | Build Evaluation Metrics System | 7 | Back-End Development Team | 3500 | 1500 | 5000 | Metrics system for evaluation
WBS-022.3 | Test and Deploy Supplier Evaluation | 3 | QA & Development Teams | 500 | 500 | 1000 | Testing and deployment
WBS-023 | Vendor Feedback and Rating System | 10 | Development Team | 5000 | 2000 | 7000 | Vendor feedback and rating system
WBS-023.1 | Design Feedback and Rating UI | 4 | UI/UX Team | 2000 | 500 | 2500 | Feedback UI design
WBS-023.2 | Implement Rating System Logic | 5 | Back-End Development Team | 2500 | 1000 | 3500 | Rating system logic implementation
WBS-023.3 | Test and Deploy Feedback System | 2 | QA & Development Teams | 500 | 500 | 1000 | Testing and deployment
WBS-024 | Custom Reporting Tool | 12 | Development Team | 6000 | 2500 | 8500 | Custom report generation tool
WBS-024.1 | Design Custom Report UI | 5 | UI/UX Team | 2500 | 500 | 3000 | Custom report UI design
WBS-024.2 | Implement Report Generation Logic | 5 | Back-End Development Team | 3000 | 1500 | 4500 | Report generation logic implementation
WBS-024.3 | Test and Deploy Custom Report Tool | 2 | QA & Development Teams | 500 | 500 | 1000 | Testing and deployment
WBS-025 | Loyalty Programs for User Retention | 14 | Development Team | 6500 | 2500 | 9000 | Loyalty program implementation
WBS-025.1 | Design Loyalty Program UI | 5 | UI/UX Team | 2500 | 500 | 3000 | Loyalty program UI design
WBS-025.2 | Build Loyalty Points System | 7 | Back-End Development Team | 3500 | 1500 | 5000 | Loyalty points system
WBS-025.3 | Integrate Loyalty Offers and Rewards | 5 | Development Team | 2500 | 1000 | 3500 | Offers and rewards integration
WBS-025.4 | Test and Deploy Loyalty Program | 2 | QA & Development Teams | 500 | 500 | 1000 | Testing and deployment
WBS-026 | Order Splitting Across Suppliers | 10 | Development Team | 5000 | 2000 | 7000 | Order splitting system deployment
WBS-026.1 | Design Order Splitting UI | 4 | UI/UX Team | 2000 | 500 | 2500 | Order splitting UI design
WBS-026.2 | Implement Splitting Logic | 6 | Back-End Development Team | 3000 | 1500 | 4500 | Logic implementation for splitting
WBS-026.3 | Test and Deploy Order Splitting | 2 | QA & Development Teams | 500 | 500 | 1000 | Testing and deployment
WBS-027 | Discount and Promotions Feature | 12 | Development Team | 6000 | 2500 | 8500 | Discount and promotion features
WBS-027.1 | Design Discounts UI | 4 | UI/UX Team | 2000 | 500 | 2500 | Discounts UI design
WBS-027.2 | Build Discount Logic | 6 | Back-End Development Team | 3000 | 1500 | 4500 | Discount logic implementation
WBS-027.3 | Test and Deploy Discounts Feature | 2 | QA & Development Teams | 500 | 500 | 1000 | Testing and deployment
WBS-028 | Shopping Cart and Checkout System | 20 | Development Team | 8000 | 3000 | 11000 | Shopping cart and secure checkout
WBS-028.1 | Design Shopping Cart UI | 6 | UI/UX Team | 3000 | 500 | 3500 | Shopping cart UI design
WBS-028.2 | Build Secure Checkout Logic | 10 | Back-End Development Team | 4500 | 2000 | 6500 | Secure checkout system
WBS-028.3 | Test and Deploy Shopping Cart | 3 | QA & Development Teams | 500 | 500 | 1000 | Testing and deployment
WBS-029 | AI-Powered Supply Prediction Tool | 18 | AI & Development Teams | 7500 | 3000 | 10500 | AI-powered prediction tool
WBS-029.1 | Data Collection and Model Training | 7 | Data Science & AI Teams | 3500 | 1500 | 5000 | AI model training
WBS-029.2 | Build Prediction Engine | 7 | Back-End Development Team | 3500 | 1000 | 4500 | Prediction engine development
WBS-029.3 | Test and Deploy Prediction Tool | 2 | QA & Development Teams | 500 | 500 | 1000 | Testing and deployment
WBS-030 | ADA Compliance for Accessibility | 14 | Development & Accessibility Teams | 6500 | 2500 | 9000 | ADA-compliance implementation
WBS-030.1 | Conduct Accessibility Audit | 4 | Accessibility Team | 2000 | 500 | 2500 | Accessibility audit
WBS-030.2 | Implement ADA Compliance Features | 8 | Development Team | 3500 | 1500 | 5000 | ADA-compliance features
WBS-030.3 | Test and Deploy ADA-Compliant Features | 2 | QA & Development Teams | 500 | 500 | 1000 | Testing and deployment
WBS-031 | Load Balancing for High Traffic | 12 | IT & Cloud Infrastructure Team | 5500 | 2500 | 8000 | Load balancing system
WBS-031.1 | Design Load Balancing Logic | 5 | IT Team | 2500 | 500 | 3000 | Load balancing logic design
WBS-031.2 | Implement Load Balancing | 5 | IT Team | 2500 | 1500 | 4000 | Load balancer implementation
WBS-031.3 | Test and Deploy Load Balancing | 2 | QA & IT Teams | 500 | 500 | 1000 | Testing and deployment
WBS-032 | Database Partitioning | 10 | Database Development Team | 4500 | 2000 | 6500 | Database partitioning for optimization
WBS-032.1 | Analyze Data for Partitioning | 3 | Database Team | 2000 | 500 | 2500 | Data analysis for partitioning
WBS-032.2 | Implement Database Partitioning | 5 | Database Development Team | 2500 | 1000 | 3500 | Partitioning implementation
WBS-032.3 | Test and Deploy Partitioning | 2 | QA & Database Teams | 500 | 500 | 1000 | Testing and deployment
WBS-033 | Multi-Factor Authentication (MFA) | 14 | Security & Development Teams | 6500 | 2500 | 9000 | MFA system deployment
WBS-033.1 | Design MFA UI | 4 | UI/UX Team | 2500 | 500 | 3000 | MFA UI design
WBS-033.2 | Implement MFA Back-End | 7 | Back-End Development Team | 3500 | 1500 | 5000 | MFA back-end system
WBS-033.3 | Test and Deploy MFA | 2 | QA & Security Teams | 500 | 500 | 1000 | Testing and deployment
WBS-034 | Push Notifications for Mobile | 12 | Development Team | 6000 | 2500 | 8500 | Push notification system for mobile
WBS-034.1 | Design Notification UI | 4 | UI/UX Team | 2000 | 500 | 2500 | Notification UI design
WBS-034.2 | Implement Push Notification Logic | 6 | Back-End Development Team | 3000 | 1500 | 4500 | Push notification logic
WBS-034.3 | Test and Deploy Push Notifications | 2 | QA & Development Teams | 500 | 500 | 1000 | Testing and deployment
WBS-035 | Secure API Integration | 14 | Development Team | 7000 | 2500 | 9500 | Secure API integration system
WBS-035.1 | Design API Security Protocols | 5 | Security & Development Teams | 2500 | 500 | 3000 | API security protocol design
WBS-035.2 | Implement Secure API Endpoints | 7 | Back-End Development Team | 3500 | 1500 | 5000 | Secure API endpoints implementation
WBS-035.3 | Test and Deploy API Integration | 2 | QA & Development Teams | 500 | 500 | 1000 | Testing and deployment
WBS-036 | Performance Optimization | 15 | Development Team | 7500 | 3000 | 10500 | System performance optimization
WBS-036.1 | Analyze System Bottlenecks | 6 | Development & IT Teams | 3000 | 1500 | 4500 | Bottleneck analysis
WBS-036.2 | Implement Performance Enhancements | 7 | Development & IT Teams | 3500 | 1000 | 4500 | Performance optimization
WBS-036.3 | Test and Deploy Optimized System | 2 | QA & Development Teams | 500 | 500 | 1000 | Testing and deployment
WBS-037 | Data Backup and Recovery | 14 | Development & IT Teams | 7000 | 3000 | 10000 | Data backup and recovery system
WBS-037.1 | Design Backup Strategy | 4 | IT Team | 3000 | 500 | 3500 | Backup strategy design
WBS-037.2 | Implement Backup System | 7 | IT Team | 3500 | 1500 | 5000 | Backup system implementation
WBS-037.3 | Test and Monitor Backup System | 3 | QA & IT Teams | 500 | 500 | 1000 | Testing and monitoring
WBS-038 | Mobile App Responsiveness | 15 | UI/UX & Development Teams | 7500 | 3000 | 10500 | Mobile app responsiveness
WBS-038.1 | Design Responsive Layout | 6 | UI/UX Team | 3000 | 500 | 3500 | Responsive layout design
WBS-038.2 | Implement Responsive Front-End | 6 | Front-End Development Team | 3500 | 1500 | 5000 | Responsive front-end implementation
WBS-038.3 | Test Responsiveness on Devices | 3 | QA & Development Teams | 500 | 500 | 1000 | Testing responsiveness on devices
WBS-039 | ADA Compliance for Accessibility | 14 | Accessibility & Development Teams | 7000 | 3000 | 10000 | ADA-compliance for accessibility
WBS-039.1 | Conduct ADA Accessibility Audit | 4 | Accessibility Team | 3000 | 500 | 3500 | Accessibility audit
WBS-039.2 | Implement ADA Compliance Features | 8 | Development Team | 3500 | 1500 | 5000 | ADA-compliance features
WBS-039.3 | Test and Deploy ADA Features | 2 | QA & Development Teams | 500 | 500 | 1000 | Testing and deployment
WBS-040 | Group Purchasing for Bulk Orders | 14 | Development Team | 7000 | 3000 | 10000 | Group purchasing feature
WBS-040.1 | Design Group Purchasing UI | 5 | UI/UX Team | 3000 | 500 | 3500 | Group purchasing UI design
WBS-040.2 | Implement Group Purchasing Logic | 7 | Back-End Development Team | 3500 | 1500 | 5000 | Group purchasing logic implementation
WBS-040.3 | Test and Deploy Group Purchasing | 2 | QA & Development Teams | 500 | 500 | 1000 | Testing and deployment
WBS-041 | Forgot Password System | 10 | Development & Security Teams | 5000 | 2000 | 7000 | Forgot password system
WBS-041.1 | Design Forgot Password UI | 4 | UI/UX Team | 2000 | 500 | 2500 | Forgot password UI design
WBS-041.2 | Implement Reset Logic | 5 | Back-End Development Team | 3000 | 1000 | 4000 | Reset logic implementation
WBS-041.3 | Test and Deploy Forgot Password | 2 | QA & Development Teams | 500 | 500 | 1000 | Testing and deployment
Total Planned Value (PV) | 1000000
Total Earned Value (EV) | 621000
Cost Control Process Purpose of Cost Control Cost control ensures that project spending is aligned with the budget, cost variances are identified early, and corrective actions are taken to manage deviations from the cost baseline. Key Activities Monitoring Expenditures: Tracking actual costs against planned expenditures. Variance Analysis: Identifying and analyzing variances between planned and actual costs. Earned Value Management (EVM): Measuring project performance using cost and schedule metrics. Key metrics include: Cost Performance Index (CPI): A measure of cost efficiency. (CPI = EV / AC) Schedule Performance Index (SPI): A measure of schedule efficiency. (SPI = EV / PV) Estimate at Completion (EAC): Forecast of the total cost based on current performance. Estimate to Complete (ETC): Forecast of how much more it will cost to complete the project. Change Control: Managing changes to the cost baseline through a formal change request process. Corrective Actions If significant cost variances are identified, the project manager will: Analyze the cause of the variance. Develop a corrective action plan to mitigate the impact on the project budget. Communicate the corrective action plan to stakeholders. Monitoring Tools Earned Value Management (EVM) for tracking cost performance. Variance Analysis to identify deviations. Forecasting Techniques to predict future costs. Project Management Software (e.g., MS Project, Primavera) for ongoing cost tracking and analysis.
Change Control Any changes to the project budget or cost baseline must be formally requested, reviewed, and approved through the Change Control Process. Changes must be documented, and their impacts on the overall project cost must be evaluated.