## Sheet1
WBS ID | Task Name | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Schedule Variance (SV) | Cost Variance (CV) | Schedule Performance Index (SPI) | Cost Performance Index (CPI) | Completion Status
WBS-001 | User Registration System | 10000 | 9500 | 9800 | -500 | -300 | 0.95 | 0.97 | 95% Completed
WBS-002 | Admin Inventory Management | 12000 | 11500 | 11200 | -500 | 300 | 0.96 | 1.03 | 90% Completed
WBS-003 | Parent Dashboard | 8000 | 7500 | 7700 | -500 | -200 | 0.94 | 0.97 | 90% Completed
WBS-004 | Secure Payment Integration | 9500 | 9000 | 9300 | -500 | -300 | 0.95 | 0.97 | 95% Completed
WBS-005 | Product Comparison Tool | 7000 | 7200 | 6900 | 200 | 300 | 1.03 | 1.04 | 100% Completed
WBS-006 | Order Tracking System | 9000 | 8800 | 8500 | -200 | 300 | 0.98 | 1.04 | 95% Completed
WBS-007 | AI-Powered Supply Prediction | 15000 | 14500 | 14800 | -500 | -300 | 0.97 | 0.98 | 95% Completed
WBS-008 | Role-Based Access Control | 10000 | 9800 | 9500 | -200 | 300 | 0.98 | 1.03 | 95% Completed
WBS-009 | In-App Chat Support | 7500 | 7000 | 6900 | -500 | 100 | 0.93 | 1.01 | 90% Completed
WBS-010 | Bulk Ordering System | 10000 | 9500 | 9700 | -500 | -200 | 0.95 | 0.98 | 95% Completed
WBS-011 | Product Search and Filter | 8500 | 8300 | 8100 | -200 | 200 | 0.98 | 1.02 | 98% Completed
WBS-012 | Reports Dashboard (Admin) | 12500 | 12000 | 12300 | -500 | -300 | 0.96 | 0.98 | 96% Completed
WBS-013 | Notifications and Alerts | 6500 | 6200 | 6300 | -300 | -100 | 0.95 | 0.98 | 95% Completed
WBS-014 | Supplier Product Management | 10000 | 9700 | 9800 | -300 | -100 | 0.97 | 0.99 | 97% Completed
WBS-015 | Multi-Language Support | 8000 | 7500 | 7600 | -500 | -100 | 0.94 | 0.99 | 93% Completed
WBS-016 | Product Wishlist/Favorites | 7000 | 6700 | 6800 | -300 | -100 | 0.96 | 0.99 | 95% Completed
WBS-017 | Data Encryption for Security | 10500 | 10000 | 10200 | -500 | -200 | 0.95 | 0.98 | 95% Completed
WBS-018 | Recurring Orders Setup (Parent) | 8500 | 8200 | 8000 | -300 | 200 | 0.96 | 1.03 | 96% Completed
WBS-019 | Admin Multi-Location Dashboard | 12000 | 11500 | 11700 | -500 | -200 | 0.96 | 0.98 | 96% Completed
WBS-020 | Voice-Assisted Search | 10000 | 9700 | 9800 | -300 | -100 | 0.97 | 0.99 | 97% Completed
WBS-021 | Automatic Server Scaling | 12500 | 12200 | 12400 | -300 | -200 | 0.98 | 0.98 | 98% Completed
WBS-022 | Supplier Performance Evaluation | 10500 | 10000 | 10300 | -500 | -300 | 0.95 | 0.97 | 95% Completed
WBS-023 | Vendor Feedback and Rating System | 9500 | 9300 | 9200 | -200 | 100 | 0.98 | 1.01 | 98% Completed
WBS-024 | Custom Reporting Tool | 11000 | 10800 | 10900 | -200 | -100 | 0.98 | 0.99 | 98% Completed
WBS-025 | Loyalty Programs for User Retention | 10000 | 9800 | 9900 | -200 | -100 | 0.98 | 0.99 | 98% Completed
WBS-026 | Order Splitting Across Suppliers | 8500 | 8300 | 8400 | -200 | -100 | 0.98 | 0.99 | 98% Completed
WBS-027 | Discount and Promotions Feature | 9000 | 8800 | 8900 | -200 | -100 | 0.98 | 0.99 | 98% Completed
WBS-028 | Shopping Cart and Checkout System | 11500 | 11000 | 11200 | -500 | -200 | 0.96 | 0.98 | 95% Completed
WBS-029 | AI-Powered Supply Prediction Tool | 15000 | 14800 | 14900 | -200 | -100 | 0.99 | 0.99 | 99% Completed
WBS-030 | ADA Compliance for Accessibility | 12000 | 11500 | 11600 | -500 | -100 | 0.96 | 0.99 | 96% Completed
WBS-031 | Load Balancing for High Traffic | 9000 | 8800 | 8900 | -200 | -100 | 0.98 | 0.99 | 98% Completed
WBS-032 | Database Partitioning | 10000 | 9500 | 9800 | -500 | -300 | 0.95 | 0.97 | 95% Completed
WBS-033 | Multi-Factor Authentication (MFA) | 11000 | 10500 | 10700 | -500 | -200 | 0.95 | 0.98 | 95% Completed