## Sheet1
WBS ID | Task Name | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Planned Duration (Days) | Actual Duration (Days) | Variance (Days) | Cause of Variance | Impact on Project | Corrective Actions
WBS-001 | User Registration System | 2024-03-01 | 2024-03-15 | 2024-03-01 | 2024-03-18 | 14 | 17 | 3 | Delays in integrating social media login feature | Minimal impact, minor delay in registration module | Added additional resources to expedite other tasks
WBS-002 | Admin Inventory Management | 2024-03-16 | 2024-04-05 | 2024-03-16 | 2024-04-07 | 20 | 22 | 2 | Minor adjustments required in inventory alert system | Slight shift in inventory module, no major impact | Regular meetings to monitor inventory system progress
WBS-003 | Parent Dashboard | 2024-03-16 | 2024-03-31 | 2024-03-17 | 2024-04-02 | 15 | 16 | 1 | UI design revisions requested by stakeholders | Minimal impact, approved during review | Design team provided clearer design expectations
WBS-004 | Secure Payment Integration | 2024-04-01 | 2024-04-13 | 2024-04-01 | 2024-04-15 | 12 | 14 | 2 | Extra time needed for security compliance checks | Payment functionality delayed by 2 days | Reassigned security checks earlier in future tasks
WBS-005 | Product Comparison Tool | 2024-04-06 | 2024-04-16 | 2024-04-06 | 2024-04-16 | 10 | 10 | 0 | None | None | None
WBS-006 | Order Tracking System | 2024-03-17 | 2024-03-31 | 2024-03-17 | 2024-04-01 | 14 | 16 | 2 | Issues with real-time tracking integration | Slight impact on user tracking features | Conducted additional testing and QA on tracking
WBS-007 | AI-Powered Supply Prediction | 2024-04-05 | 2024-05-05 | 2024-04-06 | 2024-05-07 | 30 | 31 | 1 | Additional time required for AI model training | Minimal impact, system testing extended by 1 day | Revised AI model iteration plan
WBS-008 | Role-Based Access Control | 2024-03-25 | 2024-04-08 | 2024-03-25 | 2024-04-10 | 14 | 16 | 2 | Delays in finalizing user roles and permissions | No major impact | Extended timeline for role testing
WBS-009 | In-App Chat Support | 2024-03-29 | 2024-04-06 | 2024-03-29 | 2024-04-06 | 8 | 8 | 0 | None | None | None
WBS-010 | Bulk Ordering System | 2024-04-02 | 2024-04-14 | 2024-04-02 | 2024-04-16 | 12 | 14 | 2 | Integration with bulk discounting delayed | Slight delay in bulk ordering module | Bulk discounts feature moved to later sprint
WBS-011 | Product Search and Filter | 2024-04-10 | 2024-04-22 | 2024-04-10 | 2024-04-24 | 12 | 14 | 2 | Delays in finalizing the filtering algorithm | Slight delay in product search system | Extended testing phase to refine filter options
WBS-012 | Reports Dashboard (Admin) | 2024-04-15 | 2024-05-05 | 2024-04-15 | 2024-05-06 | 20 | 21 | 1 | Additional requirements requested for custom reporting | Minor impact, reporting tool deployment delayed | Adjusted scope and updated requirements with stakeholders
WBS-013 | Notifications and Alerts | 2024-03-21 | 2024-03-31 | 2024-03-21 | 2024-04-01 | 10 | 11 | 1 | Minor delays in setting up push notification logic | Minimal impact on overall alert functionality | Revised push notification schedule
WBS-014 | Supplier Product Management | 2024-04-15 | 2024-04-30 | 2024-04-16 | 2024-05-02 | 15 | 16 | 1 | Slight delay in stock level management feature development | Minimal impact, product management slightly delayed | Allocated additional resources for faster completion
WBS-015 | Multi-Language Support | 2024-04-20 | 2024-04-28 | 2024-04-20 | 2024-04-29 | 8 | 9 | 1 | Localization process took longer than expected | Minimal impact, language support delayed by one day | Streamlined translation workflows
WBS-016 | Product Wishlist/Favorites | 2024-04-22 | 2024-05-02 | 2024-04-22 | 2024-05-04 | 10 | 12 | 2 | Integration with cart system required additional testing | Minor impact, wishlist feature launch delayed | Added additional QA resources to expedite testing
WBS-017 | Data Encryption for Security | 2024-04-25 | 2024-05-09 | 2024-04-25 | 2024-05-10 | 14 | 15 | 1 | Encryption process for sensitive data required extended testing | Minimal impact on security measures | Allocated more testing resources for future encryption tasks
WBS-018 | Recurring Orders Setup (Parent) | 2024-05-01 | 2024-05-13 | 2024-05-01 | 2024-05-14 | 12 | 13 | 1 | Back-end logic for recurring orders required optimization | Minor impact on recurring order functionality | Optimized back-end processes
WBS-019 | Admin Multi-Location Dashboard | 2024-06-10 | 2024-06-24 | 2024-06-10 | 2024-06-25 | 14 | 15 | 1 | Location data tracking system required additional refinements | Minimal impact on multi-location management | Refined data tracking and added redundancy checks
WBS-020 | Voice-Assisted Search | 2024-06-25 | 2024-07-09 | 2024-06-25 | 2024-07-10 | 14 | 15 | 1 | Voice recognition model integration required extra testing | Minimal impact, voice search slightly delayed | Integrated with ongoing testing workflows
WBS-021 | Automatic Server Scaling | 2024-07-10 | 2024-07-28 | 2024-07-10 | 2024-07-30 | 18 | 20 | 2 | Server scaling tests required additional load simulation | Minor impact on server performance | Extended testing with larger data volumes
WBS-022 | Supplier Performance Evaluation | 2024-07-15 | 2024-07-29 | 2024-07-16 | 2024-07-31 | 14 | 15 | 1 | Delays in gathering supplier data for performance evaluation | Minimal impact, evaluation tool slightly delayed | Improved data collection processes
WBS-023 | Vendor Feedback and Rating System | 2024-07-30 | 2024-08-10 | 2024-07-30 | 2024-08-11 | 10 | 12 | 2 | Additional time needed to refine feedback and rating algorithms | Minor impact, system feedback delayed | Added extra QA and testing resources
WBS-024 | Custom Reporting Tool | 2024-08-01 | 2024-08-13 | 2024-08-02 | 2024-08-15 | 12 | 13 | 1 | Custom report generation logic required more refinement | Minimal impact, custom reporting tool slightly delayed | Focused resources on final testing
WBS-025 | Loyalty Programs for User Retention | 2024-08-10 | 2024-08-24 | 2024-08-11 | 2024-08-25 | 14 | 15 | 1 | Integration with rewards system needed further adjustments | Minimal impact, loyalty program delay | Adjusted integration approach