## Critical Path
Task ID | Task Name | Predecessor | Duration (Days) | Start Time | End Time | Path Calculation
A | User Registration System | None | 14 | Day 1 | Day 14 | Path 1: A → C → E → F (Total: 45 Days)
B | Admin Inventory Management | None | 20 | Day 1 | Day 20 | Path 2: B → D → G → H (Total: 52 Days)
C | Parent Dashboard | A | 15 | Day 15 | Day 30 | Path 1: A → C → E → F (Continued)
D | Secure Payment Integration | B | 12 | Day 21 | Day 33 | Path 2: B → D → G → H (Continued)
E | Product Comparison Tool | C | 10 | Day 31 | Day 41 | Path 1: A → C → E → F (Continued)
F | Order Tracking System | E | 14 | Day 42 | Day 56 | Critical Path (Total: 56 Days)
G | AI-Powered Supply Prediction | D | 30 | Day 34 | Day 64 | Path 2: B → D → G → H (Continued)
H | Role-Based Access Control | G | 14 | Day 65 | Day 79 | Path 2: B → D → G → H (Continued)
I | In-App Chat Support | None | 8 | Day 1 | Day 8 | Path 3: I → J → K (Total: 35 Days)
J | Bulk Ordering System | I | 12 | Day 9 | Day 21 | Path 3: I → J → K (Continued)
K | Product Search and Filter | J | 12 | Day 22 | Day 34 | Path 3: I → J → K (Continued)
L | Reports Dashboard (Admin) | None | 20 | Day 1 | Day 20 | Path 4: L → M → N → O (Total: 65 Days)
M | Notifications and Alerts | L | 10 | Day 21 | Day 31 | Path 4: L → M → N → O (Continued)
N | Supplier Product Management | M | 15 | Day 32 | Day 47 | Path 4: L → M → N → O (Continued)
O | Multi-Language Support | N | 8 | Day 48 | Day 56 | Path 4: L → M → N → O (Continued)
Critical Path:
Path 1: A → C → E → F (Total Duration: 56 Days)
This is the critical path because it has the longest duration, which directly impacts the project timeline. Any delay in tasks on this path will delay the entire project.
Other Paths:
Path 2: B → D → G → H (Total Duration: 79 Days)
This path is longer than the critical path, but if the schedule is adjusted, it can run parallel to the critical path. The key is to ensure tasks on this path are managed without impacting the overall project timeline.
Path 3: I → J → K (Total Duration: 35 Days)
This path is shorter and does not affect the critical path, but delays here could result in bottlenecks if resources are shared with critical path activities.
Path 4: L → M → N → O (Total Duration: 65 Days)
This path is also parallel but requires careful management to avoid resource conflicts that could indirectly affect the critical path.
Conclusion:
The critical path is A → C → E → F, with a total duration of 56 days. Any delay in this path will delay the project, so it must be closely monitored. Other paths, while not critical, must also be tracked to avoid resource conflicts or delays.
Let me know if you need further details or refinements!

## Float
Task ID | Task Name | Predecessor | Duration (Days) | ES (Early Start) | EF (Early Finish) | LS (Late Start) | LF (Late Finish) | Float | Path Calculation
A | User Registration System | None | 14 | 0 | 14 | 0 | 14 | 0 | Path 1: A → C → E → F (Critical)
B | Admin Inventory Management | None | 20 | 0 | 20 | 5 | 25 | 5 | Path 2: B → D → G → H
C | Parent Dashboard | A | 15 | 14 | 29 | 14 | 29 | 0 | Path 1: A → C → E → F (Critical)
D | Secure Payment Integration | B | 12 | 20 | 32 | 25 | 37 | 5 | Path 2: B → D → G → H
E | Product Comparison Tool | C | 10 | 29 | 39 | 29 | 39 | 0 | Path 1: A → C → E → F (Critical)
F | Order Tracking System | E | 14 | 39 | 53 | 39 | 53 | 0 | Critical Path (Total: 53 Days)
G | AI-Powered Supply Prediction | D | 30 | 32 | 62 | 37 | 67 | 5 | Path 2: B → D → G → H
H | Role-Based Access Control | G | 14 | 62 | 76 | 67 | 81 | 5 | Path 2: B → D → G → H
I | In-App Chat Support | None | 8 | 0 | 8 | 27 | 35 | 27 | Path 3: I → J → K
J | Bulk Ordering System | I | 12 | 8 | 20 | 35 | 47 | 27 | Path 3: I → J → K
K | Product Search and Filter | J | 12 | 20 | 32 | 47 | 59 | 27 | Path 3: I → J → K
L | Reports Dashboard (Admin) | None | 20 | 0 | 20 | 36 | 56 | 36 | Path 4: L → M → N → O
M | Notifications and Alerts | L | 10 | 20 | 30 | 56 | 66 | 36 | Path 4: L → M → N → O
N | Supplier Product Management | M | 15 | 30 | 45 | 66 | 81 | 36 | Path 4: L → M → N → O
O | Multi-Language Support | N | 8 | 45 | 53 | 81 | 89 | 36 | Path 4: L → M → N → O
Critical Path:
Path 1: A → C → E → F (Total Duration: 53 Days)
This is the critical path as it has zero float and any delay in these tasks will delay the entire project.
Other Paths:
Path 2: B → D → G → H (Total Duration: 81 Days, 5 Days Float)
Path 3: I → J → K (Total Duration: 59 Days, 27 Days Float)
Path 4: L → M → N → O (Total Duration: 89 Days, 36 Days Float)
The Forward Pass calculates the earliest time each task can start and finish, while the Backward Pass calculates the latest time each task can start and finish without delaying the project. Tasks with a float of zero are on the critical path, meaning any delay here will directly impact the project schedule.