## Sheet1
Total Planned Value (PV) | 1000000
Total Earned Value (EV) | 319400
Total Actual Cost (AC) | 322000
Total Schedule Variance (SV) | -11600
Total Cost Variance (CV) | -2600
Average Schedule Performance Index (SPI) | 0.965
Average Cost Performance Index (CPI) | 0.993