## Sheet1
WBS ID | Task Name | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Cost Variance (CV) | Schedule Variance (SV) | Cost Performance Index (CPI) | Estimate at Completion (EAC) | Estimate to Complete (ETC) | Variance at Completion (VAC)
WBS-001 | User Registration System | 10000 | 9500 | 10500 | -1000 | -500 | 0.9 | 111111 | 100611 | -1111
WBS-002 | Admin Inventory Management | 12000 | 11000 | 13000 | -2000 | -1000 | 0.85 | 117647 | 104647 | -5647
WBS-003 | Parent Dashboard | 15000 | 14500 | 15500 | -1000 | -500 | 0.94 | 106383 | 90883 | -4383
WBS-004 | Secure Payment Integration | 20000 | 19000 | 21500 | -2500 | -1000 | 0.88 | 113636 | 92136 | -13636
WBS-005 | Product Comparison Tool | 18000 | 17500 | 18500 | -1000 | -500 | 0.95 | 100000 | 81500 | -3000
WBS-006 | Order Tracking System | 25000 | 24000 | 26500 | -2500 | -1000 | 0.91 | 109782 | 83282 | -9782
WBS-007 | AI-Powered Supply Prediction | 22000 | 21500 | 23500 | -2000 | -500 | 0.91 | 115385 | 93885 | -7385
WBS-008 | Role-Based Access Control | 12000 | 11500 | 12500 | -1000 | -500 | 0.92 | 108696 | 97696 | -3696
WBS-009 | In-App Chat Support | 8000 | 7500 | 8500 | -1000 | -500 | 0.88 | 106818 | 89818 | -6818
WBS-010 | Bulk Ordering System | 14000 | 13500 | 15000 | -1500 | -500 | 0.9 | 116667 | 101667 | -5667
WBS-011 | Product Search and Filter | 13000 | 12500 | 13800 | -1300 | -500 | 0.91 | 109890 | 96090 | -3890
WBS-012 | Reports Dashboard (Admin) | 16000 | 15500 | 16500 | -1000 | -500 | 0.94 | 106452 | 90952 | -4452
WBS-013 | Notifications and Alerts | 10000 | 9500 | 10800 | -1300 | -500 | 0.88 | 113636 | 102836 | -6636
WBS-014 | Supplier Product Management | 11000 | 10500 | 12000 | -1500 | -500 | 0.88 | 113636 | 101636 | -3636
WBS-015 | Multi-Language Support | 8000 | 7800 | 8300 | -500 | -200 | 0.94 | 106383 | 89583 | -3383
WBS-016 | Product Wishlist/Favorites | 9000 | 8500 | 9300 | -800 | -500 | 0.91 | 109890 | 97390 | -3890
WBS-017 | Data Encryption for Security | 12000 | 11700 | 12500 | -800 | -300 | 0.94 | 106383 | 93883 | -3883
WBS-018 | Recurring Orders Setup (Parent) | 14000 | 13500 | 14800 | -1300 | -500 | 0.91 | 109890 | 95090 | -5890
WBS-019 | Admin Multi-Location Dashboard | 15000 | 14000 | 15500 | -1500 | -1000 | 0.9 | 111111 | 95611 | -6111
WBS-020 | Voice-Assisted Search | 18000 | 17000 | 18800 | -1800 | -1000 | 0.9 | 111111 | 92311 | -5311
WBS-021 | Automatic Server Scaling | 22000 | 21000 | 22500 | -1500 | -1000 | 0.93 | 108602 | 86102 | -4602
WBS-022 | Supplier Performance Evaluation | 12000 | 11500 | 12500 | -1000 | -500 | 0.92 | 108696 | 96196 | -4696
WBS-023 | Vendor Feedback and Rating System | 10000 | 9500 | 10500 | -1000 | -500 | 0.9 | 111111 | 100611 | -6111
WBS-024 | Custom Reporting Tool | 14000 | 13000 | 15000 | -2000 | -1000 | 0.87 | 114943 | 99943 | -7943
WBS-025 | Loyalty Programs for User Retention | 16000 | 15500 | 16800 | -1300 | -500 | 0.92 | 108602 | 91802 | -2602
WBS-026 | Order Splitting Across Suppliers | 20000 | 19000 | 21500 | -2500 | -1000 | 0.88 | 113636 | 92136 | -6636
WBS-027 | Discount and Promotions Feature | 14000 | 13500 | 15000 | -1500 | -500 | 0.9 | 111111 | 96111 | -6111
WBS-028 | Shopping Cart and Checkout System | 16000 | 15500 | 16800 | -1300 | -500 | 0.92 | 108696 | 93196 | -2696
WBS-029 | AI-Powered Supply Prediction Tool | 18000 | 17500 | 18500 | -1000 | -500 | 0.95 | 105263 | 87763 | -5263
WBS-030 | ADA Compliance for Accessibility | 10000 | 9500 | 10500 | -1000 | -500 | 0.9 | 111111 | 100611 | -5611
WBS-031 | Load Balancing for High Traffic | 15000 | 14500 | 16000 | -1500 | -500 | 0.91 | 109890 | 94890 | -4890
WBS-032 | Database Partitioning | 12000 | 11500 | 12800 | -1300 | -500 | 0.9 | 111111 | 98311 | -6111
WBS-033 | Multi-Factor Authentication (MFA) | 14000 | 13500 | 15000 | -1500 | -500 | 0.9 | 111111 | 96111 | -6111
WBS-034 | Push Notifications for Mobile | 10000 | 9500 | 10800 | -1300 | -500 | 0.88 | 113636 | 102836 | -6636
WBS-035 | Secure API Integration | 12000 | 11500 | 13000 | -1500 | -500 | 0.88 | 113636 | 102136 | -5636
WBS-036 | Performance Optimization | 16000 | 15000 | 17000 | -2000 | -1000 | 0.88 | 113636 | 98636 | -7636
WBS-037 | Data Backup and Recovery | 14000 | 13000 | 15500 | -2500 | -1000 | 0.84 | 119048 | 104048 | -9048
WBS-038 | Mobile App Responsiveness | 18000 | 17000 | 19000 | -2000 | -1000 | 0.89 | 112360 | 95360 | -5360
WBS-039 | ADA Compliance for Accessibility | 14000 | 13500 | 15000 | -1500 | -500 | 0.9 | 111111 | 96111 | -6111
WBS-040 | Group Purchasing for Bulk Orders | 12000 | 11500 | 13000 | -1500 | -500 | 0.88 | 113636 | 102136 | -5636
WBS-041 | Forgot Password System | 8000 | 7500 | 8500 | -1000 | -500 | 0.88 | 113636 | 102136 | -5636