The To-Complete Performance Index (TCPI) is a measure used to determine the cost performance that must be achieved with the remaining resources in order to meet a specified management goal, such as completing the project within the Budget at Completion (BAC) or the Estimate at Completion (EAC).

It is calculated as:

- TCPI based on BAC: TCPIBAC=BAC−EVBAC−ACTCPI_{BAC} = \frac{BAC - EV}{BAC - AC}TCPIBAC​=BAC−ACBAC−EV​

- TCPI based on EAC: TCPIEAC=BAC−EVEAC−ACTCPI_{EAC} = \frac{BAC - EV}{EAC - AC}TCPIEAC​=EAC−ACBAC−EV​

### Assumptions for the Project:

- Budget at Completion (BAC) for the entire project: $200,000

- EAC: Calculated using the cost performance index (CPI) of each WBS element as discussed earlier.

### TCPI Table:

| WBS ID | Task Name | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Budget at Completion (BAC) | Estimate at Completion (EAC) | TCPI (BAC) | TCPI (EAC) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| WBS-001 | User Registration System | $10,000 | $9,500 | $10,500 | $12,000 | $11,111 | 1.05 | 1.06 |
| WBS-002 | Admin Inventory Management | $12,000 | $11,000 | $13,000 | $15,000 | $14,706 | 1.07 | 1.08 |
| WBS-003 | Parent Dashboard | $15,000 | $14,500 | $15,500 | $18,000 | $17,647 | 1.08 | 1.09 |
| WBS-004 | Secure Payment Integration | $20,000 | $19,000 | $21,500 | $22,000 | $21,111 | 1.07 | 1.08 |
| WBS-005 | Product Comparison Tool | $18,000 | $17,500 | $18,500 | $20,000 | $19,048 | 1.06 | 1.07 |
| WBS-006 | Order Tracking System | $25,000 | $24,000 | $26,500 | $30,000 | $29,412 | 1.08 | 1.09 |
| WBS-007 | AI-Powered Supply Prediction | $22,000 | $21,500 | $23,500 | $28,000 | $27,273 | 1.11 | 1.12 |
| WBS-008 | Role-Based Access Control | $12,000 | $11,500 | $12,500 | $16,000 | $15,152 | 1.10 | 1.11 |
| WBS-009 | In-App Chat Support | $8,000 | $7,500 | $8,500 | $10,000 | $9,091 | 1.07 | 1.08 |
| WBS-010 | Bulk Ordering System | $14,000 | $13,500 | $14,800 | $16,000 | $15,556 | 1.08 | 1.09 |
| WBS-011 | Product Search and Filter | $13,000 | $12,500 | $13,800 | $16,000 | $15,385 | 1.08 | 1.09 |
| WBS-012 | Reports Dashboard (Admin) | $16,000 | $15,500 | $16,500 | $18,000 | $17,143 | 1.07 | 1.08 |
| WBS-013 | Notifications and Alerts | $10,000 | $9,500 | $10,800 | $12,000 | $11,538 | 1.07 | 1.08 |
| WBS-014 | Supplier Product Management | $11,000 | $10,500 | $12,000 | $14,000 | $13,333 | 1.10 | 1.11 |
| WBS-015 | Multi-Language Support | $8,000 | $7,800 | $8,300 | $10,000 | $9,474 | 1.09 | 1.10 |
| WBS-016 | Product Wishlist/Favorites | $9,000 | $8,500 | $9,300 | $11,000 | $10,526 | 1.08 | 1.09 |
| WBS-017 | Data Encryption for Security | $12,000 | $11,700 | $12,500 | $14,000 | $13,636 | 1.07 | 1.08 |
| WBS-018 | Recurring Orders Setup (Parent) | $14,000 | $13,500 | $14,800 | $17,000 | $16,190 | 1.10 | 1.11 |
| WBS-019 | Admin Multi-Location Dashboard | $15,000 | $14,000 | $15,500 | $18,000 | $17,308 | 1.09 | 1.10 |
| WBS-020 | Voice-Assisted Search | $18,000 | $17,000 | $18,800 | $20,000 | $19,231 | 1.08 | 1.09 |
| WBS-021 | Automatic Server Scaling | $22,000 | $21,000 | $22,500 | $25,000 | $24,074 | 1.10 | 1.11 |
| WBS-022 | Supplier Performance Evaluation | $12,000 | $11,500 | $12,500 | $15,000 | $14,286 | 1.10 | 1.11 |
| WBS-023 | Vendor Feedback and Rating System | $10,000 | $9,500 | $10,500 | $12,000 | $11,429 | 1.09 | 1.10 |
| WBS-024 | Custom Reporting Tool | $14,000 | $13,000 | $15,000 | $18,000 | $17,143 | 1.10 | 1.11 |
| WBS-025 | Loyalty Programs for User Retention | $16,000 | $15,500 | $16,800 | $20,000 | $19,231 | 1.08 | 1.09 |
| WBS-026 | Order Splitting Across Suppliers | $20,000 | $19,000 | $21,500 | $25,000 | $23,636 | 1.10 | 1.11 |

### Key Takeaways:

- TCPI (BAC): This shows the efficiency required in cost performance to complete the project within the original budget (BAC). A TCPI value > 1 indicates that cost efficiency needs to improve to stay within the budget.

- TCPI (EAC): This shows the efficiency required in cost performance to complete the project based on the current Estimate at Completion (EAC). A TCPI value > 1 indicates that cost efficiency must improve to stay within the forecasted cost.