#### Project: School Supplies App

#### Date: [Insert Date]

#### Prepared by: Project Manager

### 1. Overview:

This weekly status report provides an update on the current cost performance of the School Supplies App project. The report will cover the following:

- Current cost performance

- Cost variances (CV)

- Corrective actions taken to address any discrepancies

- Estimated cost forecasts

- General project progress against financial targets

### 2. Cost Performance Summary:

The project remains on track for completion within the allocated budget. However, some areas have experienced cost overruns. Below is a summary of the major cost-related metrics:

| Metric | Value |
| --- | --- |
| Budget at Completion (BAC) | $1,000,000 |
| Actual Cost (AC) | [Insert AC] |
| Earned Value (EV) | [Insert EV] |
| Cost Variance (CV) | [Insert CV] |
| Cost Performance Index (CPI) | [Insert CPI] |
| Estimate at Completion (EAC) | [Insert EAC] |
| Variance at Completion (VAC) | [Insert VAC] |

### 3. Cost Variance (CV) Analysis:

#### Overall Project CV:

- The overall cost variance of the project is currently [Insert CV], indicating that the actual costs are [below/above] the earned value by this amount.

- Positive CV: Indicates that the project is under budget and cost performance is favorable.

- Negative CV: Indicates cost overruns and requires corrective actions.

#### WBS-Level CV Analysis:

- User Registration System: CV is [-$500] due to higher-than-expected development costs for the back-end integration. The development team is working on optimizing the process to mitigate future cost overruns.

- Admin Inventory Management: CV is [-$1,000] due to unforeseen complexity in building the inventory database. Additional development resources have been allocated to avoid further delays.

- Order Tracking System: CV is [-$1,500] due to integration challenges with supplier systems. Vendor meetings are scheduled to resolve these issues and bring the costs back on track.

### 4. Corrective Actions:

#### Immediate Corrective Measures:

- Task Reallocation: To manage the cost overruns, the project team has reallocated resources to high-priority areas, such as the User Registration System and Admin Inventory Management. This will allow for faster completion of these modules and cost stabilization.

- Supplier Meetings: Meetings with third-party suppliers have been scheduled to address the cost variance in the Order Tracking System. We aim to resolve the integration issues causing delays and extra costs.

- Cost Control Measures: The project manager has implemented additional cost control measures, such as more frequent budget reviews and tighter approval processes for any change requests that may affect costs.

### 5. Forecast:

Based on current performance metrics, the project’s forecasted costs have been revised. The Estimate at Completion (EAC) is now projected to be [Insert EAC], which is [below/above] the original Budget at Completion (BAC) of $1,000,000. Continued monitoring of cost performance and timely corrective actions will help keep the project within the budget.

| WBS ID | Task Name | Planned Value (PV) | Actual Cost (AC) | Cost Variance (CV) | Corrective Action |
| --- | --- | --- | --- | --- | --- |
| WBS-001 | User Registration System | $9,500 | $10,500 | -$1,000 | Reallocation of resources to reduce delays. |
| WBS-002 | Admin Inventory Management | $11,000 | $12,500 | -$1,500 | Additional development support and optimization. |
| WBS-006 | Order Tracking System | $19,000 | $21,500 | -$2,500 | Vendor meetings to resolve integration issues. |

### 6. Next Steps:

- Continued close monitoring of cost performance.

- Ongoing optimization of resource allocation to address cost overruns.

- Weekly reviews of project expenses with the finance department.

- Regular updates to key stakeholders regarding cost control efforts and forecast changes.

### 7. Conclusion:

The project team is focused on managing the cost variances identified in this report. Corrective actions are being implemented to bring the project back within the original budget. The project manager will provide further updates on cost performance in the next weekly status report.

Prepared By: [Project Manager Name]
[Contact Information]

### Weekly Status Report: Cost Performance Update (Week 1)

#### Project: School Supplies App

#### Date: 05/06/2024

#### Prepared by: Project Manager

### 1. Overview:

This weekly status report provides an update on the current cost performance of the School Supplies App project for Week 1. The report covers:

- Current cost performance

- Cost variances (CV)

- Corrective actions taken

- Estimated cost forecasts

- General project progress against financial targets

### 2. Cost Performance Summary:

| Metric | Value |
| --- | --- |
| Budget at Completion (BAC) | $1,000,000 |
| Actual Cost (AC) | $200,000 |
| Earned Value (EV) | $190,000 |
| Cost Variance (CV) | -$10,000 |
| Cost Performance Index (CPI) | 0.95 |
| Estimate at Completion (EAC) | $1,052,631 |
| Variance at Completion (VAC) | -$52,631 |

### 3. Cost Variance (CV) Analysis:

#### Overall Project CV:

- The overall cost variance is - $10,000, indicating that the project is currently over budget.

- Negative CV: This indicates the need for corrective action to control costs.

#### WBS-Level CV Analysis:

- User Registration System: CV is - $500 due to extra time spent on back-end configuration.

- Admin Inventory Management: CV is - $1,000 due to unexpected complexity in building the database.

- Order Tracking System: CV is - $1,500 due to delays in supplier integration.

### 4. Corrective Actions:

- Task Reallocation: Extra resources have been allocated to the Admin Inventory Management system to prevent further delays.

- Supplier Meetings: Scheduled to resolve the issues causing the cost overrun in the Order Tracking System.

- Weekly Budget Reviews: Implemented to ensure tight cost control moving forward.

### 5. Forecast:

| WBS ID | Task Name | Planned Value (PV) | Actual Cost (AC) | Cost Variance (CV) | Corrective Action |
| --- | --- | --- | --- | --- | --- |
| WBS-001 | User Registration System | $9,500 | $10,500 | -$1,000 | Additional resources allocated. |
| WBS-002 | Admin Inventory Management | $11,000 | $12,500 | -$1,500 | Development optimization underway. |
| WBS-006 | Order Tracking System | $19,000 | $21,500 | -$2,500 | Supplier meetings to address delays. |

### 6. Next Steps:

- Continued close monitoring of cost variances.

- Corrective actions to minimize delays and cost overruns.

- Provide weekly updates on cost control efforts.

### Weekly Status Report: Cost Performance Update (Week 2)

#### Project: School Supplies App

#### Date: 05/13/2024

#### Prepared by: Project Manager

### 1. Overview:

This weekly status report provides an update for Week 2. The report focuses on:

- Updated cost performance

- New cost variances and actions taken

### 2. Cost Performance Summary:

| Metric | Value |
| --- | --- |
| Budget at Completion (BAC) | $1,000,000 |
| Actual Cost (AC) | $350,000 |
| Earned Value (EV) | $330,000 |
| Cost Variance (CV) | -$20,000 |
| Cost Performance Index (CPI) | 0.94 |
| Estimate at Completion (EAC) | $1,063,830 |
| Variance at Completion (VAC) | -$63,830 |

### 3. Cost Variance (CV) Analysis:

#### Overall Project CV:

- The cost variance has increased to - $20,000, requiring tighter control of expenses.

- Negative CV indicates that costs are continuing to exceed budgeted amounts.

#### WBS-Level CV Analysis:

- User Registration System: The CV remains at - $1,000 due to continued back-end configuration challenges.

- Admin Inventory Management: CV is - $2,000, with resources being shifted to expedite development.

- Order Tracking System: CV is - $3,000 as integration issues persist.

### 4. Corrective Actions:

- Revised Budget Approvals: Implemented stricter budget approvals for additional expenses.

- Daily Standups: Introduced to monitor progress and prevent further delays.

### 5. Forecast:

| WBS ID | Task Name | Planned Value (PV) | Actual Cost (AC) | Cost Variance (CV) | Corrective Action |
| --- | --- | --- | --- | --- | --- |
| WBS-001 | User Registration System | $12,500 | $13,500 | -$1,000 | Escalated to senior developers for resolution. |
| WBS-002 | Admin Inventory Management | $14,500 | $16,500 | -$2,000 | Optimization efforts underway. |
| WBS-006 | Order Tracking System | $20,500 | $23,500 | -$3,000 | Supplier integration still in progress. |

### 6. Next Steps:

- Continued daily standups to track progress.

- Increased focus on reducing the cost variance in key areas.

### Weekly Status Report: Cost Performance Update (Week 3)

#### Project: School Supplies App

#### Date: 05/20/2024

#### Prepared by: Project Manager

### 1. Overview:

This weekly status report provides the Week 3 update, focusing on:

- Continued cost performance issues

- Adjustments to project plans and schedules

### 2. Cost Performance Summary:

| Metric | Value |
| --- | --- |
| Budget at Completion (BAC) | $1,000,000 |
| Actual Cost (AC) | $500,000 |
| Earned Value (EV) | $480,000 |
| Cost Variance (CV) | -$20,000 |
| Cost Performance Index (CPI) | 0.96 |
| Estimate at Completion (EAC) | $1,041,667 |
| Variance at Completion (VAC) | -$41,667 |

### 3. Cost Variance (CV) Analysis:

#### Overall Project CV:

- The cost variance remains - $20,000, requiring continued corrective measures to stabilize the project’s budget.

#### WBS-Level CV Analysis:

- User Registration System: CV improved to - $500 due to rapid progress made by the development team.

- Admin Inventory Management: CV remains at - $2,000 due to ongoing database complexities.

- Order Tracking System: CV is - $2,500 as supplier meetings are underway.

### 4. Corrective Actions:

- Increased Focus: On completing the Admin Inventory Management system to resolve cost overruns.

- Enhanced Supplier Coordination: To address the delays in the Order Tracking System.

### 5. Forecast:

| WBS ID | Task Name | Planned Value (PV) | Actual Cost (AC) | Cost Variance (CV) | Corrective Action |
| --- | --- | --- | --- | --- | --- |
| WBS-001 | User Registration System | $15,000 | $14,500 | -$500 | Monitoring improvement closely. |
| WBS-002 | Admin Inventory Management | $17,000 | $19,000 | -$2,000 | Reallocating additional resources. |
| WBS-006 | Order Tracking System | $22,500 | $25,000 | -$2,500 | Supplier meetings still underway. |

### 6. Next Steps:

- Focus on reducing the remaining variances in the Admin Inventory Management and Order Tracking System.

### Weekly Status Report: Cost Performance Update (Week 4)

#### Project: School Supplies App

#### Date: 05/27/2024

#### Prepared by: Project Manager

### 1. Overview:

This weekly status report provides the Week 4 update, addressing ongoing cost performance and progress across all tasks.

### 2. Cost Performance Summary:

| Metric | Value |
| --- | --- |
| Budget at Completion (BAC) | $1,000,000 |
| Actual Cost (AC) | $675,000 |
| Earned Value (EV) | $650,000 |
| Cost Variance (CV) | -$25,000 |
| Cost Performance Index (CPI) | 0.96 |
| Estimate at Completion (EAC) | $1,041,667 |
| Variance at Completion (VAC) | -$41,667 |

### 3. Cost Variance (CV) Analysis:

#### Overall Project CV:

- The cost variance has increased to - $25,000, indicating that the project is still over budget, but performance has stabilized compared to previous weeks.

#### WBS-Level CV Analysis:

- User Registration System: CV is now - $250 due to completion of pending tasks.

- Admin Inventory Management: CV remains at - $2,000, but progress is on track to prevent further overruns.

- Order Tracking System: CV is - $2,500 as supplier integration has been delayed further.

### 4. Corrective Actions:

- Reallocation of Resources: Extra resources have been moved to complete the Admin Inventory Management system.

- Focus on Supplier Coordination: Vendor management and communication have been intensified to prevent further delays with the Order Tracking System.

### 5. Forecast:

| WBS ID | Task Name | Planned Value (PV) | Actual Cost (AC) | Cost Variance (CV) | Corrective Action |
| --- | --- | --- | --- | --- | --- |
| WBS-001 | User Registration System | $15,500 | $15,250 | -$250 | Finalizing improvements. |
| WBS-002 | Admin Inventory Management | $20,000 | $22,000 | -$2,000 | Ongoing development efforts. |
| WBS-006 | Order Tracking System | $24,000 | $26,500 | -$2,500 | Continuing vendor integration efforts. |

### 6. Next Steps:

- The focus for next week will be to resolve the remaining issues with the Order Tracking System.

- Finalization of Admin Inventory Management tasks and resources.

### Weekly Status Report: Cost Performance Update (Week 5)

#### Project: School Supplies App

#### Date: 06/03/2024

#### Prepared by: Project Manager

### 1. Overview:

This report provides the Week 5 update, focusing on cost performance stabilization and progress toward the project's financial targets.

### 2. Cost Performance Summary:

| Metric | Value |
| --- | --- |
| Budget at Completion (BAC) | $1,000,000 |
| Actual Cost (AC) | $800,000 |
| Earned Value (EV) | $770,000 |
| Cost Variance (CV) | -$30,000 |
| Cost Performance Index (CPI) | 0.96 |
| Estimate at Completion (EAC) | $1,041,667 |
| Variance at Completion (VAC) | -$41,667 |

### 3. Cost Variance (CV) Analysis:

#### Overall Project CV:

- The cost variance is now - $30,000, with the project still slightly over budget but progressing toward stabilization.

#### WBS-Level CV Analysis:

- User Registration System: The task is complete, with no additional cost variances.

- Admin Inventory Management: CV is - $2,000, and the task is nearing completion.

- Order Tracking System: CV is - $2,500, with supplier integration still posing challenges.

### 4. Corrective Actions:

- Optimization: Further optimization efforts have been deployed to bring the project back on track.

- Supplier Coordination: Continued focus on supplier communication to address delays.

### 5. Forecast:

| WBS ID | Task Name | Planned Value (PV) | Actual Cost (AC) | Cost Variance (CV) | Corrective Action |
| --- | --- | --- | --- | --- | --- |
| WBS-001 | User Registration System | $16,000 | $15,500 | -$500 | Task completed. |
| WBS-002 | Admin Inventory Management | $22,500 | $24,500 | -$2,000 | Task nearing completion. |
| WBS-006 | Order Tracking System | $26,000 | $28,500 | -$2,500 | Further supplier coordination required. |

### 6. Next Steps:

- The project team will continue focusing on reducing the cost variance by completing pending tasks on time and within budget.