## Sheet1
Simulation Run | Task ID | Task Name | Estimated Duration (Days) | Min Duration (Days) | Max Duration (Days) | Simulated Duration (Days) | Planned Cost | Simulated Cost | Cost Variance | Probability of Completion | Comments
Run 1 | WBS-001 | User Registration System | 14 | 10 | 18 | 15 | 15000 | 16000 | 1000 | 85% | Slight delay expected
Run 2 | WBS-002 | Admin Inventory Management | 20 | 15 | 25 | 22 | 25000 | 26500 | 1500 | 75% | Minor cost overrun observed
Run 3 | WBS-003 | Parent Dashboard | 15 | 12 | 18 | 14 | 18000 | 17500 | -500 | 90% | On track
Run 4 | WBS-004 | Secure Payment Integration | 12 | 10 | 15 | 13 | 20000 | 20500 | 500 | 80% | Expected completion delay
Run 5 | WBS-005 | Product Comparison Tool | 10 | 8 | 13 | 11 | 12000 | 13000 | 1000 | 70% | Resource constraint noted
Run 6 | WBS-006 | Order Tracking System | 14 | 12 | 16 | 13 | 15000 | 15200 | 200 | 85% | Slightly ahead of schedule
Run 7 | WBS-007 | AI-Powered Supply Prediction | 30 | 25 | 35 | 28 | 50000 | 48000 | -2000 | 65% | Risk of model underperformance
Run 8 | WBS-008 | Role-Based Access Control | 14 | 12 | 18 | 16 | 14000 | 16000 | 2000 | 60% | High complexity in permissions
Run 9 | WBS-009 | In-App Chat Support | 8 | 6 | 10 | 7 | 8000 | 7800 | -200 | 95% | Efficient implementation
Run 10 | WBS-010 | Bulk Ordering System | 12 | 10 | 15 | 12 | 15000 | 14500 | -500 | 80% | On track