## Sheet1
Risk ID | Risk Description | Risk Category | Likelihood (1-5) | Impact (1-5) | Risk Score (L x I) | Priority (High/Medium/Low) | Risk Response Strategy | Mitigation Actions | Risk Owner | Status
R-001 | Delayed delivery of project requirements | Schedule | 4 | 4 | 16 | High | Mitigate | Increase communication with stakeholders; set buffer periods for critical requirements | Project Manager | Active
R-002 | Unavailability of key technical resources | Resource | 3 | 5 | 15 | High | Transfer | Hire external consultants or temporary staff to fill resource gaps | HR Manager | Active
R-003 | Scope changes during development phase | Scope | 4 | 3 | 12 | Medium | Accept | Allocate a contingency budget for scope changes | Project Sponsor | Active
R-004 | Data security breach | Security | 2 | 5 | 10 | Medium | Mitigate | Implement strong data encryption and regular security audits | Security Officer | Active
R-005 | Stakeholder engagement issues | Communication | 3 | 4 | 12 | Medium | Mitigate | Schedule regular stakeholder meetings and provide clear status updates | Project Manager | Active
R-006 | Vendor delays in supply delivery | Procurement | 4 | 3 | 12 | Medium | Transfer | Include penalties in vendor contracts for delayed delivery | Procurement Lead | Active
R-007 | Insufficient user training | User Adoption | 3 | 4 | 12 | Medium | Mitigate | Develop a comprehensive training program and user guides | Training Lead | Active
R-008 | Incompatibility with existing systems | Technical | 3 | 4 | 12 | Medium | Mitigate | Conduct thorough compatibility testing during integration phase | Technical Lead | Active
R-009 | Budget overrun | Financial | 2 | 5 | 10 | Medium | Mitigate | Regular cost tracking and reporting; contingency reserves | Finance Manager | Active
R-010 | Legislative or regulatory changes | Compliance | 3 | 3 | 9 | Low | Accept | Monitor regulatory environment and adjust project plans as needed | Compliance Officer | Active