## Sheet1
Risk ID | Risk Description | Probability (%) | Impact (Cost) | Impact (Time) | Expected Monetary Value (EMV) | Risk Score (Probability x Impact) | Mitigation Cost | Contingency Plan | Residual Risk | Owner | Status
QR-001 | Delay in project requirements delivery | 40% | 20000 | 10 days | 8000 | 8 | 3000 | Increase resource allocation | Low | Project Manager | Active
QR-002 | Unavailability of technical resources | 30% | 15000 | 7 days | 4500 | 4.5 | 5000 | Hire external resources | Medium | HR Manager | Active
QR-003 | Data security breach | 20% | 50000 | 15 days | 10000 | 10 | 7000 | Implement advanced security protocols | Low | Security Officer | Active
QR-004 | Vendor delays in supply delivery | 35% | 25000 | 12 days | 8750 | 8.75 | 2500 | Negotiate penalties in contracts | Medium | Procurement Lead | Active
QR-005 | Budget overrun due to scope changes | 25% | 30000 | 5 days | 7500 | 7.5 | 4000 | Allocate contingency budget | Low | Finance Manager | Active