## Sheet1
Metric ID | Metric Name | Description | Measurement Method | Target Value | Actual Value | Frequency | Owner | Status
QM-001 | Defect Density | Number of defects per 1,000 lines of code | Count of defects / Total lines of code | < 5 defects/1,000 lines | 4 | Monthly | QA Team | On Track
QM-002 | Test Coverage | Percentage of requirements covered by test cases | (Test cases executed / Total requirements) | > 90% | 92% | Monthly | QA Team | On Track
QM-003 | Rework Percentage | Percentage of rework effort compared to total effort | (Rework hours / Total hours) * 100 | < 10% | 12% | Monthly | Project Manager | Needs Attention
QM-004 | On-Time Delivery | Percentage of deliverables completed on schedule | (On-time deliverables / Total deliverables) * 100 | 100% | 95% | Monthly | Project Manager | Minor Delay
QM-005 | Customer Satisfaction | Average satisfaction score from stakeholders | Survey score (1-5 scale) | > 4.0 | 4.5 | Quarterly | Customer Relations | Exceeds Expectations
QM-006 | Defect Resolution Time | Average time taken to resolve reported defects | (Sum of resolution time / Number of defects) | < 5 days | 4 days | Monthly | Development Team | On Track
QM-007 | Number of Critical Defects | Total number of critical defects identified during testing | Count of critical defects | 0 | 1 | Monthly | QA Team | Immediate Action
QM-008 | Requirement Stability Index | Percentage of requirements that remain unchanged during the project | (Stable requirements / Total requirements) * 100 | > 95% | 90% | Monthly | Project Manager | Needs Attention
QM-009 | Code Review Coverage | Percentage of code reviewed by peers | (Reviewed code / Total code) * 100 | 100% | 98% | Monthly | Development Team | Minor Improvement
QM-010 | Defect Leakage | Percentage of defects identified after release | (Defects post-release / Total defects) * 100 | < 5% | 2% | Monthly | QA Team | On Track
QM-011 | Training Effectiveness | Percentage of trainees who demonstrate competency post-training | (Competent trainees / Total trainees) * 100 | > 80% | 85% | Quarterly | HR Team | On Track
QM-012 | Process Compliance | Percentage of processes followed as per defined guidelines | (Compliant processes / Total processes) * 100 | 100% | 98% | Monthly | Project Manager | Minor Improvement
QM-013 | UAT Defect Rate | Number of defects found during User Acceptance Testing (UAT) | Count of UAT defects | < 10 defects | 8 | End of UAT | QA Team | On Track
QM-014 | Documentation Quality Index | Percentage of project documents meeting quality standards | (Compliant documents / Total documents) * 100 | 100% | 95% | Monthly | Documentation Team | Needs Attention
QM-015 | Code Complexity | Average cyclomatic complexity of code modules | Complexity score | < 10 | 12 | Monthly | Development Team | Needs Simplification