## Sheet1
Defect ID | Defect Description | Severity | Priority | Module | Reported By | Date Reported | Status | Assigned To | Resolution Date | Resolution Description | Comments
DEF-001 | Login page crashes with invalid input | Critical | High | User Authentication | QA Tester | 2024-03-05 | Open | Back-End Dev Team | 2024-03-07 | Input validation added | Needs regression testing
DEF-002 | Order history shows incorrect data | Major | High | Parent Dashboard | QA Tester | 2024-03-06 | Resolved | Front-End Dev Team | 2024-03-08 | Corrected data mapping
DEF-003 | Payment gateway timeout on slow network | Critical | High | Secure Payment | QA Tester | 2024-03-07 | Open | Back-End Dev Team |  | Optimization required for slow networks
DEF-004 | UI misalignment in the product comparison | Minor | Medium | Product Comparison | UI/UX Designer | 2024-03-07 | Open | UI/UX Team | 2024-03-10 | UI alignment fixed
DEF-005 | Notification not triggered for low stock | Major | High | Inventory Management | Admin User | 2024-03-08 | Open | Back-End Dev Team |  | Notification logic implemented
DEF-006 | Supplier ratings not displayed correctly | Major | Medium | Supplier Management | QA Tester | 2024-03-09 | Open | Front-End Dev Team |  | Corrected rating calculation logic
DEF-007 | Data not saved correctly on multi-location | Critical | High | Multi-Location Dashboard | QA Tester | 2024-03-10 | Open | Back-End Dev Team |  | Corrected data handling for locations
DEF-008 | Mobile app crashes on voice search | Critical | High | Voice Search | QA Tester | 2024-03-11 | Open | Mobile Dev Team |  | Optimization needed for voice commands
DEF-009 | Product images not loading on product page | Minor | Low | Product Details Page | User | 2024-03-11 | Open | Front-End Dev Team |  | Image URL paths corrected
DEF-010 | Incorrect date format in reports | Minor | Low | Reports Dashboard | QA Tester | 2024-03-12 | Open | Back-End Dev Team |  | Date format standardized
DEF-011 | Discount codes not applied at checkout | Major | High | Shopping Cart & Checkout | User | 2024-03-13 | Open | Back-End Dev Team |  | Discount logic corrected
DEF-012 | System timeout during bulk order submission | Critical | High | Bulk Ordering System | QA Tester | 2024-03-13 | Open | Back-End Dev Team |  | Optimization of order submission logic
DEF-013 | Multi-language support not working for French | Major | Medium | Multi-Language Support | QA Tester | 2024-03-14 | Open | Front-End Dev Team |  | Corrected translation issues
DEF-014 | Forgot password email not sent | Critical | High | User Authentication | User | 2024-03-14 | Open | Back-End Dev Team |  | Email trigger logic fixed
DEF-015 | ADA compliance issues in UI contrast | Minor | Medium | Accessibility | QA Tester | 2024-03-15 | Open | UI/UX Team |  | UI contrast corrected for ADA
DEF-016 | Search results not filtering by category | Major | Medium | Product Search & Filter | User | 2024-03-15 | Open | Back-End Dev Team |  | Filtering logic corrected
DEF-017 | Push notifications not working on Android | Major | High | Mobile App Notifications | QA Tester | 2024-03-16 | Open | Mobile Dev Team |  | Push notification issue resolved
DEF-018 | UI layout issue on tablet devices | Minor | Low | Mobile App Responsiveness | UI/UX Designer | 2024-03-16 | Open | UI/UX Team |  | Responsive layout fixed
DEF-019 | Group purchasing not calculating discounts | Major | High | Group Purchasing | QA Tester | 2024-03-17 | Open | Back-End Dev Team |  | Discount calculation corrected
DEF-020 | Payment page crashes with invalid input | Critical | High | Secure Payment | QA Tester | 2024-03-17 | Open | Back-End Dev Team |  | Input validation added for payment fields