## Sheet1
Change ID | Date Submitted | Change Request Title | Description | Change Type | Impact on Project | Status | Decision Date | Approved By | Comments
CR-001 | 2024-02-15 | Supplier API Integration | Add API integration with additional suppliers for real-time stock updates. | Scope, Schedule | Extended schedule by 2 weeks; no budget impact. | Approved | 2024-02-20 | Exec Sponsor | Critical for launch.
CR-002 | 2024-03-10 | Additional Languages | Add support for French and Spanish languages for wider adoption. | Scope, Budget | $25,000 increase; no schedule impact. | Approved | 2024-03-15 | CCB | Enhances user base.
CR-003 | 2024-04-05 | UI/UX Enhancement | Modify user interface based on beta feedback to improve usability. | Scope, Schedule | 1-week delay; no budget impact. | Pending | - | CCB | To be evaluated.
CR-004 | 2024-04-18 | Vendor Contract Extension | Extend the contract with Vendor A for additional testing services. | Budget | $10,000 increase; no schedule impact. | Rejected | 2024-04-22 | Exec Sponsor | Cost exceeds budget limit.
CR-005 | 2024-05-02 | Data Backup Feature | Add automated data backup functionality for school supply orders. | Scope, Resources | 2 extra developers needed; 1-month delay. | Approved | 2024-05-10 | CCB | Backup system essential.