## Sheet1
Review ID | Module Name | Code Reviewer | Date of Review | Code Author | Review Summary | Issues Identified | Severity | Action Items | Status | Resolution Date | Comments
CR-001 | User Authentication | John Doe | 2024-03-10 | Jane Smith | Initial Review | 1. Password validation logic is missing 2. Lack of input sanitization on login form 3. Code is not following the DRY principle | High | 1. Add password validation 2. Implement input sanitization 3. Refactor repetitive code | In Progress
CR-002 | Payment Gateway Integration | Sarah Lee | 2024-03-12 | Robert Johnson | Follow-up Review | 1. Error handling for failed transactions is not comprehensive 2. Logging of sensitive data in error logs | Critical | 1. Improve error handling 2. Remove sensitive data from logs | Open |  | Needs immediate attention
CR-003 | Order Management | Michael Brown | 2024-03-14 | Emily White | Initial Review | 1. Order status update is missing for partial shipments 2. Hardcoded values for shipping costs found in the code | Medium | 1. Add partial shipment status 2. Use configuration files for dynamic shipping costs | Open
CR-004 | Inventory Management | David Clark | 2024-03-16 | John Doe | Initial Review | 1. Low stock alert logic is inefficient, leading to performance issues 2. No unit tests for critical inventory functions | High | 1. Optimize low stock alert logic 2. Add unit tests for inventory functions | In Progress
CR-005 | Multi-Language Support | Maria Rodriguez | 2024-03-17 | Jane Smith | Initial Review | 1. Translations are missing for certain UI elements 2. Language change does not reflect dynamically | Medium | 1. Complete missing translations 2. Implement dynamic language switch | Open
CR-006 | Product Comparison Tool | John Doe | 2024-03-18 | Robert Johnson | Follow-up Review | 1. Comparison logic does not handle null values properly 2. Sorting by rating does not function as expected | High | 1. Improve handling of null values 2. Correct sorting logic | Open
CR-007 | Bulk Ordering System | Sarah Lee | 2024-03-19 | Emily White | Initial Review | 1. Performance bottleneck identified in bulk order processing 2. Lack of validation for order quantities exceeding stock availability | Critical | 1. Optimize bulk order processing 2. Implement validation for stock availability | In Progress
CR-008 | User Role Management | Michael Brown | 2024-03-20 | Jane Smith | Initial Review | 1. Insufficient role-based access controls for admin functions 2. User role data is stored in plain text in the database | Critical | 1. Strengthen access controls 2. Encrypt role data in the database | Open
CR-009 | Secure API Integration | David Clark | 2024-03-21 | Robert Johnson | Follow-up Review | 1. Inconsistent use of API keys across different services 2. Lack of security headers in API responses | Critical | 1. Standardize API key usage 2. Add security headers to all API responses | Open
CR-010 | Notification System | Maria Rodriguez | 2024-03-22 | Emily White | Initial Review | 1. Push notification service does not retry failed deliveries 2. No support for custom notification channels | Medium | 1. Implement retry logic for notifications 2. Add support for custom channels | Open
CR-011 | Reports Dashboard | John Doe | 2024-03-23 | Jane Smith | Initial Review | 1. Slow query performance on large data sets 2. Incorrect data aggregation in supplier performance report | High | 1. Optimize query performance 2. Correct data aggregation logic | Open
CR-012 | ADA Compliance | Sarah Lee | 2024-03-24 | Robert Johnson | Initial Review | 1. Some UI elements are not keyboard accessible 2. Lack of alternative text for images | High | 1. Implement keyboard navigation 2. Add alternative text for images | Open |  | Needs accessibility review
CR-013 | Secure Payment System | Michael Brown | 2024-03-25 | Emily White | Follow-up Review | 1. Insecure storage of payment tokens 2. Payment form does not validate CVV properly | Critical | 1. Use secure storage for tokens 2. Implement CVV validation | Open
CR-014 | Product Search and Filter | David Clark | 2024-03-26 | John Doe | Initial Review | 1. Search results do not reflect new product entries 2. Filter options are not working for price range | Medium | 1. Update search index dynamically 2. Correct filter logic | Open
CR-015 | Shopping Cart & Checkout | Maria Rodriguez | 2024-03-27 | Jane Smith | Initial Review | 1. Cart does not save session data properly 2. Incorrect tax calculation for certain regions | Critical | 1. Correct session handling 2. Fix tax calculation logic | Open
CR-016 | Voice Search | John Doe | 2024-03-28 | Robert Johnson | Follow-up Review | 1. Voice commands are not recognized in noisy environments 2. Lack of support for multiple languages in voice input | Medium | 1. Improve voice recognition accuracy 2. Add support for multiple languages | Open
CR-017 | Data Backup and Recovery | Sarah Lee | 2024-03-29 | Emily White | Initial Review | 1. Inconsistent backup schedules across different databases 2. Lack of automated recovery testing | High | 1. Standardize backup schedules 2. Implement automated recovery testing | Open
CR-018 | Loyalty Program System | Michael Brown | 2024-03-30 | Jane Smith | Initial Review | 1. Incorrect calculation of loyalty points 2. Points expiry logic not implemented | Medium | 1. Correct loyalty point calculation 2. Implement expiry logic | Open
CR-019 | Reports Customization | David Clark | 2024-03-31 | Robert Johnson | Initial Review | 1. Custom reports do not save user preferences 2. Incorrect date formatting in custom reports | Medium | 1. Save user preferences for reports 2. Correct date formatting | Open
CR-020 | Mobile App Responsiveness | Maria Rodriguez | 2024-04-01 | Emily White | Initial Review | 1. UI elements are not scaling properly on tablets 2. Performance lag on older mobile devices | High | 1. Optimize UI scaling 2. Improve performance on older devices | Open