## Sheet1
Requirement ID | Requirement Description | Initial Version | Current Version | Number of Changes | RSI (%) | Change Type | Date of Change | Reason for Change | Status | Comments
BR-001 | Centralized platform for school supply procurement | 1 | 1.3 | 3 | 90 | Scope Adjustment | 2024-02-15 | Expanded features for suppliers | Approved | Additional features requested by client
BR-002 | Real-time integration with suppliers | 1 | 1.2 | 2 | 95 | Technical Change | 2024-03-01 | API structure update | In Progress | API format updated
FR-003 | Order Tracking System | 1 | 1.1 | 1 | 98 | Minor Functional Change | 2024-03-10 | Added support for partial orders | Approved | Small adjustment for partial shipments
FR-008 | Shopping Cart Functionality | 1 | 1.2 | 2 | 95 | Usability Improvement | 2024-03-15 | Improved UI flow | Approved | User feedback led to UI improvement
NFR-002 | Scalability for increased user traffic | 1 | 1 | 0 | 100 | No Change | - | - | Approved | Stable requirement
TR-005 | Data Storage | 1 | 1.3 | 3 | 90 | Compliance Requirement | 2024-04-01 | GDPR compliance update | Approved | Compliance updates required
UR-007 | Parent Order Notifications | 1 | 1.2 | 2 | 95 | Functional Enhancement | 2024-03-18 | Enhanced notification preferences | In Progress | Parent request for additional settings
FR-012 | Custom Reporting Tool | 1 | 1.1 | 1 | 98 | Additional Feature Request | 2024-03-20 | Added export options | Approved | Export feature requested by admin users
FR-021 | Product Comparison Tool | 1 | 1.3 | 3 | 90 | Feature Expansion | 2024-03-25 | Added additional comparison metrics | Approved | Expanded metrics for better comparison
UR-015 | Voice-Assisted Search | 1 | 1.4 | 4 | 85 | Major Functional Change | 2024-03-30 | Added multi-language support | Approved | Major update for voice commands
BR-003 | Reduction in procurement time by 25% | 1 | 1 | 0 | 100 | No Change | - | - | Approved | Stable requirement
NFR-007 | Backup and Recovery | 1 | 1.2 | 2 | 95 | Technical Adjustment | 2024-04-05 | Improved recovery time | Approved | Technical optimization
FR-016 | Bulk and individual ordering options | 1 | 1.3 | 3 | 90 | Scope Adjustment | 2024-04-10 | Added functionality for admin bulk orders | Approved | Client requested additional flexibility
UR-018 | Group purchasing options for bulk discounts | 1 | 1.1 | 1 | 98 | Feature Addition | 2024-04-15 | Added user collaboration feature | In Progress | User feedback for collaboration
NFR-012 | ADA compliance with accessibility standards | 1 | 1 | 0 | 100 | No Change | - | - | Approved | Stable requirement