## Sheet1
Document ID | Document Name | Initial Version | Current Version | Number of Revisions | DQI (%) | Review Date | Reviewer Name | Quality Issues Identified | Severity | Action Items | Status | Comments
DOC-001 | Project Charter | 1 | 1.2 | 2 | 95 | 2024-03-01 | John Doe | Incomplete scope section, unclear project objectives | Medium | Clarify scope, update objectives | Approved | Final review needed
DOC-002 | Requirements Specifications Document | 1 | 1.4 | 4 | 90 | 2024-03-05 | Sarah Lee | Inconsistent formatting, missing acceptance criteria | High | Standardize format, add missing criteria | In Progress | Format review in process
DOC-003 | Project Plan | 1 | 1.1 | 1 | 98 | 2024-03-10 | Robert Johnson | Minor grammar errors, unclear risk management section | Low | Correct grammar, rephrase risk management | Approved | Minor revisions made
DOC-004 | Risk Management Plan | 1 | 1.3 | 3 | 93 | 2024-03-15 | Emily White | Ambiguity in risk response strategies, missing risk owner information | High | Clarify strategies, add risk owner details | Approved | High priority for next revision
DOC-005 | Stakeholder Management Plan | 1 | 1.2 | 2 | 95 | 2024-03-20 | Michael Brown | Incomplete stakeholder list, unclear communication plan | Medium | Update stakeholder list, clarify communication strategies | In Progress | Pending additional stakeholder input
DOC-006 | Communication Plan | 1 | 1.3 | 3 | 93 | 2024-03-25 | David Clark | Missing escalation paths, inconsistent contact information | High | Add escalation paths, verify contact info | Approved | Completed and verified
DOC-007 | Project Schedule | 1 | 1.2 | 2 | 95 | 2024-03-30 | Maria Rodriguez | Inconsistent dates, unclear task dependencies | Medium | Correct dates, clarify dependencies | Approved | Final review needed
DOC-008 | Budget Management Plan | 1 | 1.1 | 1 | 98 | 2024-04-01 | John Doe | Minor errors in cost estimates, unclear funding sources | Low | Correct cost estimates, clarify funding | Approved | Minor updates applied
DOC-009 | Change Control Process | 1 | 1.3 | 3 | 93 | 2024-04-05 | Sarah Lee | Ambiguous change request criteria, inconsistent approval process | High | Clarify criteria, standardize approval process | In Progress | Major revision in progress
DOC-010 | Procurement Management Plan | 1 | 1.2 | 2 | 95 | 2024-04-10 | Robert Johnson | Incomplete supplier evaluation criteria, unclear procurement timelines | Medium | Update evaluation criteria, clarify timelines | Approved | Final review completed
DOC-011 | Quality Management Plan | 1 | 1.3 | 3 | 93 | 2024-04-15 | Emily White | Incomplete quality metrics, missing defect management procedures | High | Add quality metrics, document defect management | In Progress | Pending defect management update
DOC-012 | Human Resource Management Plan | 1 | 1.1 | 1 | 98 | 2024-04-20 | Michael Brown | Minor errors in role descriptions, missing training plan | Low | Correct roles, add training plan | Approved | Minor revisions made
DOC-013 | Resource Management Plan | 1 | 1.2 | 2 | 95 | 2024-04-25 | David Clark | Incomplete resource allocation details, unclear resource monitoring | Medium | Complete allocation details, clarify monitoring process | Approved | Final review needed
DOC-014 | Cost Management Plan | 1 | 1.2 | 2 | 95 | 2024-04-30 | Maria Rodriguez | Inconsistent cost baselines, unclear cost control measures | Medium | Correct baselines, clarify control measures | Approved | Completed and verified
DOC-015 | Risk Register | 1 | 1.3 | 3 | 93 | 2024-05-05 | John Doe | Incomplete risk categories, missing risk impact descriptions | High | Add categories, complete impact descriptions | In Progress | Major revision in progress
DOC-016 | Lessons Learned Document | 1 | 1.1 | 1 | 98 | 2024-05-10 | Sarah Lee | Minor formatting errors, incomplete lessons learned from last phase | Low | Correct formatting, complete lessons learned | Approved | Final review completed
DOC-017 | Meeting Management Plan | 1 | 1.2 | 2 | 95 | 2024-05-15 | Robert Johnson | Incomplete meeting schedules, unclear meeting roles and responsibilities | Medium | Update schedules, clarify roles | Approved | Pending final approval
DOC-018 | Issue Log | 1 | 1.1 | 1 | 98 | 2024-05-20 | Emily White | Minor inconsistencies in issue descriptions, unclear resolutions | Low | Correct descriptions, clarify resolutions | Approved | Minor revisions made
DOC-019 | Earned Value Management (EVM) Report | 1 | 1.2 | 2 | 95 | 2024-05-25 | Michael Brown | Incorrect CPI and SPI calculations, unclear variance analysis | Medium | Correct calculations, improve variance analysis | Approved | Final review needed
DOC-020 | Monte Carlo Simulation Report | 1 | 1.1 | 1 | 98 | 2024-05-30 | David Clark | Minor errors in simulation parameters, unclear probability interpretation | Low | Correct parameters, clarify interpretation | Approved | Final review needed