## Sheet1
UAT ID | Test Scenario | Test Case Description | Expected Outcome | Actual Outcome | Tested By | Date Tested | Status | Comments/Notes
UAT-001 | User Registration | Verify that a new user can register using valid details | User is successfully registered and redirected to the dashboard | User successfully registered | [Tester Name] | 2024-01-10 | Pass | -
UAT-002 | User Authentication | Verify that a user can log in with valid credentials | User is logged in and redirected to the homepage | User logged in successfully | [Tester Name] | 2024-01-11 | Pass | -
UAT-003 | Password Reset | Verify that a user can reset their password | Password reset link sent to registered email | Password reset link received and password updated | [Tester Name] | 2024-01-12 | Pass | -
UAT-004 | Inventory Management | Verify that the admin can add, update, and delete items | Inventory items updated as expected | Items added, updated, and deleted successfully | [Tester Name] | 2024-01-13 | Pass | -
UAT-005 | Order Placement | Verify that a parent can place an order for school supplies | Order is successfully placed and confirmation is received | Order placed successfully | [Tester Name] | 2024-01-14 | Pass | -
UAT-006 | Payment Gateway | Verify that users can complete payment using a credit card | Payment is processed and a confirmation receipt is generated | Payment processed successfully | [Tester Name] | 2024-01-15 | Pass | -
UAT-007 | Order Tracking | Verify that parents can track their order status | Order status updates are displayed correctly | Order status tracked successfully | [Tester Name] | 2024-01-16 | Pass | -
UAT-008 | User Interface Consistency | Verify that the UI elements are consistent across all screens | All screens have a uniform and consistent layout | UI elements are consistent across all screens | [Tester Name] | 2024-01-17 | Pass | Minor adjustments made to button colors
UAT-009 | Report Generation | Verify that the admin can generate reports | Reports are generated with correct data | Reports generated successfully with accurate data | [Tester Name] | 2024-01-18 | Pass | -
UAT-010 | Supplier Performance Evaluation | Verify that the supplier performance dashboard works correctly | Dashboard displays accurate performance metrics | Performance metrics displayed correctly | [Tester Name] | 2024-01-19 | Pass | -
UAT-011 | Bulk Order Placement | Verify that admins can place bulk orders | Bulk orders are placed and confirmed | Bulk order placement successful | [Tester Name] | 2024-01-20 | Pass | -
UAT-012 | Notification and Alerts | Verify that users receive notifications and alerts | Notifications and alerts are received as expected | Notifications received correctly | [Tester Name] | 2024-01-21 | Pass | -
UAT-013 | Multi-User Collaboration | Verify that multiple users can collaborate on the same order | Multiple users can add or edit items in the same order | Collaboration features work as expected | [Tester Name] | 2024-01-22 | Pass | -
UAT-014 | User Role-Based Access | Verify that different user roles have appropriate access | Admins, parents, and suppliers have correct access levels | Access controls verified successfully | [Tester Name] | 2024-01-23 | Pass | -
UAT-015 | Voice-Assisted Search | Verify that users can search using voice commands | Search results are displayed based on voice input | Voice search functionality works as expected | [Tester Name] | 2024-01-24 | Pass | -
UAT-016 | Real-Time Data Synchronization | Verify that data is synchronized across all platforms | Data updates are reflected in real-time | Real-time data synchronization verified | [Tester Name] | 2024-01-25 | Pass | -
UAT-017 | AI-Powered Supply Prediction | Verify that the AI model predicts supply needs accurately | Predicted supply needs match historical data trends | AI predictions are accurate based on historical data | [Tester Name] | 2024-01-26 | Pass | -
UAT-018 | User Feedback Collection | Verify that users can submit feedback through the app | Feedback is submitted and stored in the system | Feedback submitted successfully | [Tester Name] | 2024-01-27 | Pass | -
UAT-019 | Order Splitting Across Suppliers | Verify that orders can be split across multiple suppliers | Orders are split based on availability and pricing | Order splitting feature works as expected | [Tester Name] | 2024-01-28 | Pass | -
UAT-020 | Mobile Responsiveness | Verify that the app is fully functional on mobile devices | All features are accessible and functional on mobile | Mobile responsiveness tested successfully | [Tester Name] | 2024-01-29 | Pass | -
UAT-021 | ADA Compliance | Verify that the app meets ADA accessibility standards | App is accessible to users with disabilities | ADA compliance verified | [Tester Name] | 2024-01-30 | Pass | -
UAT-022 | Secure API Integration | Verify that all APIs are secure and accessible | API security and access tested successfully | API integration verified | [Tester Name] | 2024-01-31 | Pass | -
UAT-023 | Custom Report Generation | Verify that admins can generate custom reports | Custom reports are generated as per selected criteria | Custom reports generated successfully | [Tester Name] | 2024-02-01 | Pass | -
UAT-024 | Supplier Product Management | Verify that suppliers can manage their product listings | Products can be added, updated, and deleted | Supplier product management tested successfully | [Tester Name] | 2024-02-02 | Pass | -
UAT-025 | Group Purchasing for Bulk Orders | Verify that group purchasing works for bulk orders | Group purchasing processed successfully | Group purchasing feature verified | [Tester Name] | 2024-02-03 | Pass | -
UAT-026 | Order Confirmation and Invoice Generation | Verify that users receive order confirmation and invoice | Order confirmation and invoice generated successfully | Confirmation and invoice features verified | [Tester Name] | 2024-02-04 | Pass | -
UAT-027 | Data Backup and Recovery | Verify that the data backup and recovery system works | Data is backed up and can be recovered as needed | Backup and recovery system tested successfully | [Tester Name] | 2024-02-05 | Pass | -
UAT-028 | Multi-Language Support | Verify that the app supports multiple languages | Language selection and translation features work | Multi-language support verified | [Tester Name] | 2024-02-06 | Pass | -
UAT-029 | Discount and Promotion Feature | Verify that discounts and promotions are applied correctly | Discounts and promotions are applied as configured | Discounts and promotion features tested successfully | [Tester Name] | 2024-02-07 | Pass | -
UAT-030 | Recurring Orders Setup | Verify that parents can set up recurring orders | Recurring orders are created and scheduled as expected | Recurring orders feature tested successfully | [Tester Name] | 2024-02-08 | Pass | -