This Impact Assessment Report provides a detailed evaluation of the potential effects of the requested changes on the School Supplies App Project. Each change request (CR) is analyzed to determine its impact on scope, schedule, budget, and resources, as well as any associated risks.

### Change Request ID: CR-001

- Date Submitted: 02/15/2024

- Title: Supplier API Integration

- Description: Add API integration with additional suppliers for real-time stock updates.

- Change Type: Scope, Schedule

- Impact on Scope: Expands the project to include integration with 3 additional suppliers.

- Impact on Schedule: Extends the schedule by 2 weeks to accommodate new integration requirements.

- Impact on Budget: No budget impact.

- Impact on Resources: Requires additional developer support for 2 weeks.

- Risks: Potential delays in testing due to extended integration timelines.

- Mitigation Plan: Allocate additional developer hours and schedule overlap between integration and testing phases to minimize delays.

- Decision: Approved on 02/20/2024 by the Executive Sponsor.

### Change Request ID: CR-002

- Date Submitted: 03/10/2024

- Title: Additional Languages

- Description: Add support for French and Spanish languages for wider adoption.

- Change Type: Scope, Budget

- Impact on Scope: Expands the user base to include non-English-speaking markets.

- Impact on Schedule: No impact on the project schedule.

- Impact on Budget: Increases the budget by $25,000 for language translation services and localization testing.

- Impact on Resources: Additional testing team for language support required.

- Risks: Delayed user testing in non-English languages due to late translations.

- Mitigation Plan: Parallel translation and development process to ensure timely delivery.

- Decision: Approved on 03/15/2024 by the Change Control Board (CCB).

### Change Request ID: CR-003

- Date Submitted: 04/05/2024

- Title: UI/UX Enhancement

- Description: Modify user interface based on beta feedback to improve usability.

- Change Type: Scope, Schedule

- Impact on Scope: Minor adjustments to the user interface design to improve navigation and accessibility.

- Impact on Schedule: Causes a 1-week delay due to additional design work and user testing.

- Impact on Budget: No budget impact.

- Impact on Resources: Requires 1 additional UI/UX designer for 1 week.

- Risks: User acceptance testing might require further iterations, causing additional delays.

- Mitigation Plan: Prioritize UI changes with the most significant user impact to minimize time spent on redesigns.

- Decision: Pending further review.

### Change Request ID: CR-004

- Date Submitted: 04/18/2024

- Title: Vendor Contract Extension

- Description: Extend the contract with Vendor A for additional testing services.

- Change Type: Budget

- Impact on Scope: No impact on scope.

- Impact on Schedule: No impact on schedule.

- Impact on Budget: Increases the project budget by $10,000 for extended vendor services.

- Impact on Resources: No additional resource requirements.

- Risks: None identified.

- Mitigation Plan: N/A

- Decision: Rejected on 04/22/2024 by the Executive Sponsor due to exceeding the available budget.

### Change Request ID: CR-005

- Date Submitted: 05/02/2024

- Title: Data Backup Feature

- Description: Add automated data backup functionality for school supply orders.

- Change Type: Scope, Resources

- Impact on Scope: Adds new functionality to ensure data security and compliance.

- Impact on Schedule: Extends the project timeline by 1 month due to additional development and testing requirements.

- Impact on Budget: No budget impact.

- Impact on Resources: Requires 2 additional developers for 1 month to build and test the backup system.

- Risks: Delays in deployment if the backup feature is not thoroughly tested.

- Mitigation Plan: Allocate extra testing time to validate backup functionality before launch.

- Decision: Approved on 05/10/2024 by the CCB due to the critical importance of data security.

### Summary of Impacts

| Change Request ID | Scope Impact | Schedule Impact | Budget Impact | Resource Impact | Risk Level | Decision |
| --- | --- | --- | --- | --- | --- | --- |
| CR-001 | Expanded supplier integration | +2 weeks | None | Additional dev support | Medium | Approved |
| CR-002 | Additional languages | None | +$25,000 | Extra testing resources | Low | Approved |
| CR-003 | UI adjustments | +1 week | None | Additional designer | Medium | Pending |
| CR-004 | None | None | +$10,000 | None | Low | Rejected |
| CR-005 | Added data backup | +1 month | None | 2 extra developers | High | Approved |

This Impact Assessment Report provides a detailed evaluation of each change request, ensuring that all changes are thoroughly analyzed before a decision is made to approve or reject them.