## Sheet1
Issue ID | Issue Description | Priority | Date Identified | Reported By | Assigned To | Status | Resolution | Date Resolved | Comments
ISS-001 | Delay in integrating payment gateway | High | 2024-01-05 | Project Manager | Payment Integration Team | In Progress | Adjust timeline and reassign resources | - | Coordination with supplier required
ISS-002 | Login issues for new users | Medium | 2024-01-07 | QA Team | Development Team | Resolved | Fixed validation error in code | 2024-01-08 | Retested successfully
ISS-003 | Incorrect data display in reports | High | 2024-01-12 | QA Team | Reporting Team | In Progress | Recheck data mapping and update code | - | Scheduled for review on 01/15/2024
ISS-004 | UI inconsistencies in the dashboard | Low | 2024-01-15 | UI/UX Designer | UI Development Team | Open | Redesign UI elements | - | Planned for UI sprint
ISS-005 | Performance lag in inventory module | High | 2024-01-18 | QA Team | Performance Team | In Progress | Optimize database queries | - | Additional performance testing required
ISS-006 | Security vulnerability in API endpoints | Critical | 2024-01-20 | Security Team | API Development Team | Resolved | Implemented additional security measures | 2024-01-22 | Security audit passed
ISS-007 | Vendor feedback not being saved | Medium | 2024-01-22 | QA Team | Development Team | In Progress | Fix database write issue | - | Impacting only specific conditions
ISS-008 | Notification system delay | Low | 2024-01-25 | QA Team | Notification Team | Open | Adjust server scheduling | - | Requires load testing
ISS-009 | Errors in order confirmation emails | Medium | 2024-01-27 | Customer Support | Email Team | Resolved | Corrected template code | 2024-01-28 | Emails tested successfully
ISS-010 | Misalignment in UI on mobile devices | Low | 2024-01-28 | QA Team | Mobile UI Team | Open | Adjust CSS for responsiveness | - | Scheduled for next mobile update
ISS-011 | Database backup failures | Critical | 2024-02-01 | IT Team | Database Team | In Progress | Check backup scripts and permissions | - | High priority due to data risk
ISS-012 | Inaccurate order tracking information | Medium | 2024-02-05 | Customer Support | Development Team | Open | Verify data integration with suppliers | - | Affects customer experience
ISS-013 | Lack of documentation for new features | Low | 2024-02-10 | Project Manager | Documentation Team | In Progress | Create comprehensive user guides | - | Documentation in progress
ISS-014 | High CPU usage on cloud servers | High | 2024-02-12 | IT Team | Cloud Infrastructure Team | In Progress | Review and optimize server resources | - | Impacting app performance
ISS-015 | Data inconsistency in user reports | High | 2024-02-15 | Reporting Team | Database Team | In Progress | Investigate data source discrepancies | - | Scheduled for immediate review