## Sheet1
Project Name: School Supplies App Development Project
Project Manager: [Project Manager Name]
Project Start Date: January 1, 2024
Project End Date: June 30, 2024
Checklist Item | Description | Responsible | Completion Date | Status | Comments
1. Final Deliverables Completed | Ensure all project deliverables are completed and approved. | Project Manager | [Date] | ☐ Not Started
2. Stakeholder Acceptance | Obtain formal acceptance of all deliverables from stakeholders. | Project Manager, Stakeholders | [Date] | In Progress
3. Final Testing and Quality Assurance | Complete all testing and quality assurance activities. | QA Team | [Date] | Completed
4. Documentation Review | Review and finalize all project documentation (e.g., project plan, requirements, design documents, etc.). | Project Manager | [Date] | ☐ Not Started
5. Lessons Learned Documentation | Document lessons learned during the project lifecycle. | Project Team | [Date] | In Progress
6. Financial Closure | Finalize all financials, including invoices, payments, and budget reconciliation. | Finance Team | [Date] | Completed
7. Resource Release | Release project resources and reassign them as needed. | Resource Manager | [Date] | ☐ Not Started
8. Final Project Report | Prepare and distribute the final project report to stakeholders. | Project Manager | [Date] | In Progress
9. Stakeholder Satisfaction Survey | Conduct a satisfaction survey to gather stakeholder feedback. | Project Manager | [Date] | Completed
10. Archiving Project Documents | Archive all project documents in a central repository. | Project Coordinator | [Date] | ☐ Not Started
11. Formal Project Closure Meeting | Conduct a final review meeting to formally close the project. | Project Manager | [Date] | In Progress
12. Transition and Handover | Transition and hand over ongoing support, maintenance, or operational activities. | Project Manager, Operations Team | [Date] | Completed
13. Post-Implementation Review | Schedule a post-implementation review to assess project outcomes and benefits realization. | Project Manager | [Date] | ☐ Not Started
14. Risk and Issue Closure | Review and close all remaining risks and issues. | Risk Manager | [Date] | In Progress
15. Celebrate Project Success | Acknowledge the team’s efforts and celebrate project completion. | Project Sponsor | [Date] | Completed