Hello, my name is Dr. Christy Bozic and I am a faculty member in Engineering Management at the University of Colorado Boulder College of Engineering and Applied Science. Welcome to the second course in the project management specialization, project planning and execution. This course will serve as an introduction to how a project manager executes a project. You will learn the tools and techniques used by project managers to develop and control the project schedule. We'll also discuss the methods used to determine the budget for individual project activities, as well as for the overall project itself. Including how to use both the budget and the schedule to determine if a project is on track. You will learn about how to obtain the resources needed for a successful project. We'll discuss methods on how to analyze any potential risks to the overall project. Finally, we'll learn about the ways that a project manager controls and assures a quality product is delivered to the customer. Again, welcome and I hope you enjoy this course.

In this video, we will discuss two project management methodologies. The first is the predictive model. This is also called waterfall in software development. The predictive model follows a more linear path for project scheduling. We'll compare that with Agile project management, which uses more of an iterative process to place value on providing the customer deliverables more frequently. There are different lifecycles in project management. First, let's take a look at the predictive project management or traditional project management style. You will use this project methodology where your milestones are more defined and more sequenced. This methodology also doesn't really respond well to changes. It isn't as Agile, if you will. It follows the stages of initiating, planning, executing, controlling, and monitoring, and closing. In each of these stages have well-defined processes and tools. When it comes to managing the project schedule, it may follow a stage gate process more on this later. Then we have a project management called Agile. An Agile project management is one that prioritizes creating value through quicker releases. While traditional project management doesn't respond well to change, Agile welcomes changes to the project and to the project schedule.

Play video starting at :1:55 and follow transcript

1:55

In this slide, we have a graphical example of a predictive methodology in terms of the project timeline. In the traditional schedule, the approach is linear. All phases of the project will occur in a predicted sequence. The project team must first complete planning before moving on to execution and then verification and then delivery to the customer. The project manager plans the schedule upfront. They try to reduce the risk of any schedule changes or scope changes because the predictive model doesn't really allow many changes in the model. Since all the planning is done in the beginning, there isn't any changes due to the scope or the budget. If there are those changes, they'll really throw off your schedule. Now let's compare this to the Agile methodology. The Agile method invite changes. It works on an editor iterative process. The Agile approach encourages more frequent delivery. It really focuses on creating value early and often. This means that teams work more collaboratively to plan smaller iterations of the project, execute on those iterations, on each smaller segment, verify them, and then deliver them to the customer again to create value. Now, this isn't to say that Agile is better than predictive in every situation or for every project. Many projects lend themselves to a traditional project methodology very well. Especially when the scope is well-defined or if the project is similar to a previous successful project. In this class, I will discuss project scheduling from the perspective of a traditional project or a waterfall project. But I did at least want to introduce you to some of the basic terminology of project's schedules in terms of Agile project management. The Agile project manager uses short cycles of planning and then jumps right into execution. This is all done in something called sprints. The project manager in Agile is called the scrum master. Project scheduling and monitoring is often done using a system called Kanban. What Kanban is it's essentially a work in progress for the Agile team. As parts of the project progress, they move across the Kanban board from left to right until they are tested, validated, and delivered to the end-user or to the customer or to the client. Now, don't worry if this all seems foreign to you, especially if you've just completed my first course. I do have another course called Agile project management, where I will explain the entire process in more detail. I just wanted to introduce the concept of the sprint sense project scheduling is vastly different between the methodologies. Now let's move on to predictive models.

In the traditional or predictive model of project management, there is a knowledge area called project schedule management. There are a number of formal processes a project manager can follow to accurately plan and control their project schedule. In this video, we will review the six project management processes for schedule project management. The purpose of a project schedule management plan is to define the process for delivering the project to the clients on time. We also need to have a plan for how we will estimate each individual process or step within the project, what milestones will be met, as well as a way to determine the quickest and most efficient way to meet the project needs.

Play video starting at :1:4 and follow transcript

1:04

Let's begin first by looking at our project management process groups and knowledge areas. If you've taken a previous class with me you'll recognize this slide where we discuss each of the knowledge areas and process groups. We can see that project schedule management contains six processes across the planning and the monitoring and controlling process groups. The first process is plan schedule management. Just like all other knowledge areas in project management, we must first start with a plan. In this process, the project manager will create a document called the schedule management plan. This document details the process that will be followed to determine the project schedule. This includes a formal report on how the project group will define and estimate project activities along with any assumptions and any risks to the schedule. The planning document provides a guidebook for the project manager to follow throughout the project.

Play video starting at :2:18 and follow transcript

2:18

Also, part of the planning process includes defining the specific activities that need to take place during your project. Project activities are well-defined and itemized. This is where the project manager takes a deep look into the work breakdown structure and work packages developed in the scope management process, and they use the WBS. It's really just a guide. The project manager develops the activities list based on the WBS and they make sure that it is aligned with the scope of the project. Also, while defining activities, the project manager identifies any major project milestones that need to be met.

Play video starting at :3:7 and follow transcript

3:07

Next, the project manager will sequence the project activities. This means that we define the order of those activities. This is where things start to become tricky. Some activities need to be completed before others begin, and this is called a dependency. For example, we cannot begin assembling a product until we purchase all of the raw materials or components in that project that we need to build it. We are depending on the components for that assembly. Many companies use software to help us with activity sequencing.

Play video starting at :3:48 and follow transcript

3:48

During the planning process, the project team will also estimate how long each activity will take. They can do this by a number of ways. Perhaps they have done a similar project in the past and they've got historical information to reference or they can consult an expert or the person who will actually be doing the activities for an estimate of the time necessary. They could also use a variety of estimation techniques based on industry standards. We'll dive deeper on the ways to estimate activity duration later in this class.

Play video starting at :4:29 and follow transcript

4:29

Next, the project manager develops a schedule. This is where they take all of the information determined in the sequencing and the estimation steps and then they develop a formal project schedule. We will determine something called a critical path, which simply put is just the shortest time the project takes to be completed; how fast or the minimum amount of time necessary to complete the project. This schedule also is communicated to the appropriate stakeholders.

Play video starting at :5:6 and follow transcript

5:06

Once the schedule is developed and all the milestones and dependencies are determined, the project manager monitors and controls the schedule. This means that if some of the dates of the project begin to slip or it looks like some deadlines won't be met, the project manager finds ways to get the project back on schedule. There are a number of corrective actions or tools the project manager has to perform, schedule compression or getting the project back on schedule just to make sure that the dates don't slip further. The main output or main product of the knowledge area of project schedule management is the document called the schedule management plan. Like other plans in project management, it will serve as your playbook throughout the project. What's included in this document? Well, first you should explain your overall methodology for how you will manage the schedule. This includes details on how you will define your activities, how you will estimate your activity resources and durations of those activities. It should also include how you plan to report the schedule to stakeholders, as well as any assumptions you have taken during the development of the plan. You should also include any potential risks to the schedule that you are aware of at the time. There are a number of ways project managers can manage and report the project schedule, but it is really important to have a solid plan. I have included links in the next module to a variety of sample templates that you can use to develop your schedule management plan. Additionally, a quick Google search of project scheduled management is sure to provide many more links and examples as well.

Leads and Lags

When sequencing project activities, there are times when we need to wait.  We wait for materials to be delivered or we wait to start a dependent activity.

These are called leads and lags.

Lead Time

A lead time is something we are waiting for, but can be accounted for in a schedule overlap.  For example, We need to purchase an engine for the assembly of a cruise ship.  The supplier advises us procurement will take 365 days from the start of the order until delivery of the engine.  We know to order the engine exactly one year before we need it installed.

Lag Time

A lag time is a delay before the beginning of the next activity.  An example would be if we were pouring a concrete driveway.  We need the driveway to be poured before we can make a delivery into the house. We need to make sure that the concrete has completely cured or hardened before we can drive on it. Let’s say this takes two days.  This would represent a two day lag time for the delivery schedule.

In order for us to deliver a successful project, there are a lot of activities that need to get accomplished by you as the project manager, by the team, by suppliers, and other stakeholders. Defining project activities is the second process in schedule management and it's where we break down each project component or work package into specific activities. Let's discuss the way project managers identify and define project activities. Before developing a project schedule, we need to figure out the project activities that need to be done. We can do this by the process of defining activities and detailing the actions necessary within those activities to produce the deliverables defined by the project's scope.

Play video starting at :1:2 and follow transcript

1:02

Let's talk about how to define activities. You'll need a few pieces of information. First is the project scope. If you took the first course in the sequence, you understand scope, but for those who didn't or those who may need a reminder, project scope means the work required to successfully meet the project's deliverables. As part of the project scope, you developed a work breakdown structure or WBS. You'll also need the WBS since it provides detail on all the parts and components that have to be delivered to meet the scope of your project. When you develop the work breakdown structure, you break these components further into something called work packages. I like to think of work packages as many projects within your larger project, we'll break down the work packages into individual activities. It is those activities where we'll estimate time durations and develop the project schedule. All of these inputs are needed to define the activities. From these inputs, we will develop three main outputs. These are the activity list; the activity attributes, and project milestones. More on these later.

Play video starting at :2:30 and follow transcript

2:30

First, let's take a look at an example of a work breakdown structure to explain the activities estimation or defining activities. This one is a work breakdown structure detailing the building of a cruise ship. On level 1, we have the project name, which is cruise ship project. Level 2 are some of the sub-components such as manufacturing and assembly and safety.

Play video starting at :3:5 and follow transcript

3:05

On level 3, these are broken down further into individual components such as the hull, sky decks and etc.

Play video starting at :3:21 and follow transcript

3:21

Now, if we look at the manufacturing and assembly task specifically, we can see the sub-components such as the hull, the sky deck, and the engines. Looking at the engines specifically we can break down engines into three separate work packages. These are the starboard engine, the portside engine, and the center engines.

Play video starting at :3:52 and follow transcript

3:52

Let's assume that we purchase the entire starboard engine from an external vendor. We can break down that work package into specific activities, such as perhaps ordering the engine, installing the engine, and testing the engine. Each of these activities take some time, so it's important to break down the work packages into manageable activities, to be able to assign them to team members or to other stakeholders.

Play video starting at :4:26 and follow transcript

4:26

Once you have defined the project activities, the project manager develops an activity list with activity attributes. Activity attributes include any of the details about the activities such as dependencies. A dependency means that one activity is dependent upon the completion of another, so obviously, we couldn't install a ship's engine without ordering the ship's engines first. So this would be an example of a dependency. Another output are the project milestones, and milestones are significant events in the projects. Using our example, a milestone might be the successful test of the starboard engine. This is the process you would follow to define activities using your scope, WBS, and work packages.

Now that we have defined our project activities we need to determine in what order these activities need to be done. Some activities depend on others to happen before they can even begin these are called dependencies. There is a tool and project management called network diagramming or precedence diagramming that helps us determine the most efficient sequence for our project activities. When sequencing project activities, project managers use precedent diagrams to determine the relationships between activities in order to develop the formal project schedule. Now we have discussed activity dependencies before and it's where one activity is dependent upon another activity. There are four types of dependencies for activities. The first is called a mandatory dependency and this is where one activity must happen before another and there's just no way around it. The second activity is completely dependent upon the first. An example of this is if you are wanting to paint a wall of a new home, that wall must first be built. So in order to paint it, it must be built, it must be there the next is called discretionary dependencies and this is where an activity should happen before another, but it's not absolutely necessary. So an example of that would be if we wanted to paint that same wall before we moved in furniture into the house, we we should paint the wall before we move in furniture but it doesn't have to happen that way. So we would call that the discretionary dependency. Another dependency is called an external dependency and this comes from outside your project. So in order to paint the wall, the paint supplier must deliver the paint to the house. So we're depending on an external supplier, some from from outside the project and then the last is called an internal dependency and this comes from within your project. So an example might be that we're using our own painters to paint the house and those painters must finish painting the kitchen before they start painting the bedroom. So in order to complete the bedroom painting job, we need the labor or the resources from the kitchen to complete in order to start painting the bedroom. Now let's take a look at something called precedence diagramming and this is used to help the project manager further examine dependencies and make a determination of the project's critical path. The critical path is determined by building a diagram to determine the earliest possible completion date for the project. So again, the critical path is the earliest possible completion date. In order to do this, we need to understand diagramming. So let's start first with a precedents diagram. Here's a square and this square is it's it's called a node and this node represents an activity that needs to happen for our project and let's call that activity A and here's another node and let's call that one activity B. Now let's say that we need to complete activity A in order to start activity B. So activity B is completely dependent upon activities A's completion. The arrow represents the dependency, we call this finish to start dependency. Now let's look at a simplified example, so assume we're planting a garden and we want to plant tomatoes, peppers, herbs, etcetera. You get it, let's say activity A. Is preparing the dirt for planting, then ACTIVITY B. Is digging the hole to plant the tomato. Now we would have to make sure that ACTIVITY A. Is completed before ACTIVITY B. Can start. Of course we need dirt in the garden before we can begin to plant anything. Now let's take a look at finish to finish and this is a different type of dependency but it's where both activities should be finished at the same time. An example would be if we were to pick tomatoes from our garden to make a fresh salad. The tomatoes need to be harvested or finished growing before we can serve and assemble the salad. We call that finish to finish next. Let's look at start to start and this is where activities A must start before activity B, but these are usually done simultaneously. An example would be, let's say your instead of a gardener, you're a farmer and in order to plant your seeds for crops. You need to plow the land and we know that we can do the plowing and the planting at the same time, but first the plowing starts, then the seeds are dropped into the ground and then planted. So these must be done in order but you can do them at the same time. That's an example of a start to start and then we have start to finish and that's where ACTIVITY A must start before ACTIVITY B can finish. It's very rare that we use a start to finish, but I just at least want to introduce that dependency to you. Now, here's an example of a simplified precedents diagram on the left, we have the project start, we start with activity A. And in order to move on to Activities B and C, we must first complete Activity A. Activities B and C can be done in parallel and simultaneously, but ACTIVITY B must be complete in order to start ACTIVITY D, activity C and D. Can both finish at the same time, which would be the end of the project. So that's a of an overall simple example of what a precedence diagram looks like, as you can see many activities in our project can depend upon one another. The precedents diagram allows us to visually see these dependencies. It is an important step when it comes to developing the actual project schedule

We now know what activities we need to do and what order we need to do them in. Now let's talk about how long each activity will take. In order to build a project schedule, we need to complete an estimate of activity durations. There are many techniques a project manager can use to estimate each activity, along with an arsenal of common tools that we can apply. Let's look at the process. Estimating the duration of activities is the process of determining how long each individual activity will take to complete given all the resources assigned to that activity. Those activity estimates will be used to develop the overall project schedule. Now, I will introduce the estimation techniques, but first I wanted to discuss some of the other factors that can have an impact on your estimates. One factor to consider when assigning resources or estimating activities is something called the law of diminishing returns. This means that when we add an additional resource to the activity to try to increase the efficiency, or reduce the amount of time it takes to accomplish it, you will eventually reach a point where if we keep adding resources to it, we will not save any time and we may even have the opposite effect. Let's say you assign someone to work on an activity for 40 hours a week, and they produce 1,000 units during those 40 hours. You decide you need to increase their output, so you require them to work 10 percent more hours in a week or 44 hours. Now, you may expect an increase in their output of 10 percent or 1,100 units. But what you actually may get is an output of only 1,050 units which is only a five percent increase. You have reached the peak of diminishing returns. This could be due to a number of reasons including worker fatigue or some other negative worker impact.

Play video starting at :2:24 and follow transcript

2:24

Similar to the law of diminishing returns is the addition of the number of resources. We need to be careful adding more resources. Let's say we double the number of resources in an activity, you may expect to reduce the amount of time it is accomplished by half and this isn't usually the case. There's usually a learning curve with new people on a new activity and as you increase the number of people on an activity, you also increase the level of risk of error due to those new resources added to the project. Sometimes there's a learning curve and sometimes there's just too many people on an activity. Additionally, we need to consider technology. As our capacity for technology increases, a lot of times so does productivity. Just keep in mind technology increases as well.

Play video starting at :3:26 and follow transcript

3:26

We also need to be aware of different motivational factors in staff resources. There's something called the student syndrome and this is just basically procrastination. It's when people start to apply themselves at the last possible minute to accomplish a task. There's also something called Parkinson's law, which means that the work will expand to fill the available time. This is when you know you've got a due date like a week from today, and it should only take about a day to complete it but you use the full week to work on it. You use the entire time.

Play video starting at :4:7 and follow transcript

4:07

Now that we know what we need to keep in mind or consider during our estimating process, let's introduce four common estimating techniques. I'll go into greater detail on each of these later in the module. I just wanted to introduce the concepts here. First is analogous estimating. This is where we use historic data from a similar activity or a project. It is the least time-consuming as the other estimation techniques, but it can be less accurate. Next, we have parametric estimating. This is where we use an algorithm to calculate cost or duration based on both historical data and our specific project parameters. It provides for a bit more accuracy. Then we have three-point estimating. This method incorporates levels of risk to determine a range for an activity's duration. Finally, we have bottom-up estimating. This is a method that aggregates the estimates of the lower-level components of the WBS. It uses the work breakdown structure sub-components to estimate cost, and it's also used for estimating time and this usually takes longer than the other approaches.

Play video starting at :5:39 and follow transcript

5:39

One last consideration. We have these tools for estimating the duration of our activities, but sometimes people have differing opinions. It's really important that you work with your project team to determine these duration estimates. But sometimes we can't always reach a consensus. We hold meetings, we seek their input since they are really the experts at accomplishing those tasks, but at the end of the day, who decides on the estimate? There is a decision-making technique used in project management and often in agile project management and it's called the fist of five. This is where each member of the project team votes on their confidence level of the estimates. A closed fist means they don't support the estimate at all. If a team member is holding up five fingers, that means there is full support. If a team member is holding up fewer than three fingers, they get to voice their concerns about that estimate and this is done repeatedly until everyone is holding up three or more fingers to show that they support that estimate.

Play video starting at :6:52 and follow transcript

6:52

​Analogous estimating compares your current activity to a previous, similar activity to get an estimated activity duration.

Parametric Estimating typically uses a unit time then multiplies that time by the number of units.  If it takes me 4 months to develop a course, it would take me 8 months to develop 2 courses.

Both analogous and parametric estimating are used to estimate cost in addition to estimating time.

Three-Point & PERT Estimating

There are two additional techniques for estimating activity duration.  These are the three-point estimate and the Program Evaluation and Review Technique (PERT).

These techniques allow the project team to incorporate risk scenarios into the estimate.

Three-Point Estimating

The three-point estimating technique allows for a range:

- Optimistic Estimate - amount of time the activity will take if we assume no problems. (Best Case)

- Most Likely Estimate - amount of time the activity will take with a realistic view.         (Most Likely)

- Pessimistic Estimate - amount of time the activity will take if there are many problems. (Worst Case)

The Three-point estimate takes the average of these scenarios:

Estimate = (Optimistic + Most Likely + Pessimistic)     -or-  Estimate = (O + ML +P)/3

3

Example:

Optimistic = 15 hours

Most Likely = 24 hours

Pessimistic = 30 hours

Estimate = (O + ML +P)/3

= (15 + 24 + 30) /3 = 23 hours

PERT Estimating

PERT Estimating gives more weight to the most likely scenario.

The formula for PERT is:

PERT Estimate = (Optimistic + (4 Most Likely) + Pessimistic)

6

Estimate = (O + (4ML) +P)/6

So using our example times for Optimistic, Most Likely, and Pessimistic from above we have:

Estimate = (O + (4ML) +P)/6

= (15 +(4*24) +30)/6

=(15+96+30)/6

= 141/6

= 23.5 hours

Now you have the precedence diagrams. You've estimated the duration of each of the project activities, and you have assigned resources to those activities. Now it's time to develop the project schedule. The first thing we need to consider when developing the overall project schedule are any constraints we might have. We also need to consider any of the potential risks to the project schedule. In this video we will talk about constraints and risks. Every project will have some scheduled constraints, it's just the nature of project management. The most restrictive constraints are the must start on and the must finish by dates, and these are usually customer-driven or client driven. For an example, let's take a look at, let's say you're running a project to update software for a company and they run a continuous operation except for a small three-week period where they shut down, employees take vacation, and they're just wanting to get it done in that time frame. They may have a start on date of day one of that shut down and a must finish by date of a day or two before resuming operations, so those are those types of restrictions. Then we have the start no earlier and starting to later. These are usually representing beginning a project when some other project or event finishes, you may then begin yours. Similarly, starting no later can mean that you must start some portion of your project by a certain no later date than in order to have it complete for something that's dependent upon that portion of your project. So it's to meet some predetermined deadline. Then we have finish no earlier and finish no later. You're sensing a pattern here, these usually have dependencies for other events or other projects as well.

Play video starting at :2:16 and follow transcript

2:16

We also need to take into account other constraints. Do we have the access to the resources when we need them? Let's say we need a particular programmer or a training resource, but they're committed for a particular period time. We just need to be aware and work around their prior schedule commitments and be prepared to work around those. Can we still make a profit? Maybe we need to be the first to market, or maybe we want to do a product release at a certain time. If you're launching a new video game unit, you want to make sure to launch it before that large holiday where people buy lots of presence for kids or something, so you can maximize your profit. Then, are there any regulatory compliances we need to meet. How much time do we need for testing? How much time do the regulatory rules require us to do testing or labs or whatever it may be. Just keep in mind those regulatory compliances as well. We also need to consider any potential risks to our projects. Are there other competing projects? Something that might take our resources, or something that might take our funding. We need to consider those as risks. Catastrophic events. Well, we can't predict catastrophic events like earthquakes, or wildfires, or hurricanes, we can definitely plan certain activities at certain times of the year to reduce those potential risks. Labor. This one's a tough one, will we be able to find adequate labor to complete specific activities of the project. If you took my first course, we learned that labor is hard to attract and retain, so we just need to make sure that we consider that as a risk as well. More and more increasingly, supply chains has become an issue, there are global shortages on goods coming from all over the globe. Have we built in appropriately lee times, these are all just risks to consider when developing your schedule.

We're now ready to put together the project schedule, and we do this by developing a network diagram. A network diagram is a visual or a graphical representation of the sequence of activities of a project. The purpose of this diagram is to find the earliest possible completion date for the project and the latest completion date for the project. It allows us to view opportunities for efficiencies in our schedule by shifting things around or delaying specific activities in the project. Many project managers use software programs to develop their network diagrams, but I wanted to show you how to develop one so that you have a better understanding of the concept.

Play video starting at ::59 and follow transcript

0:59

First, let's talk about the critical path. A project's critical path is the longest total duration of the activities. The activities on the critical path cannot be delayed or the entire project will be delayed. It's the total amount of time on the critical path represents the quickest project schedule and I know that sounds contradictory but it will become clear with an example.

Play video starting at :1:31 and follow transcript

1:31

This is an example of a network diagram, and this is from our PM4DEV report. You should recognize this from this week's reading assignment. On the left we have the start of the project then we move to the right, to the first node which is called Activity 1. Activity 1 has a duration of 20 days. Activity 1 must be completed before Activities 2 or 3 begin, so Activity 1 is a predecessor to those activities. Activities 4, 5, and 6 follow then Activities 7 and 8. If we follow the path with the longest duration, that is the critical path. Activity 1 equals 20 days, Activity 2 is 30 while Activity 3 is only 10, so we'll follow the top path. Activity 4 leads to Activity 7 which lasts 10 days, then the project will end. Our critical path is Activity 1 at 20 days, Activity 2 at 30, Activity 4 at 30 days, and Activity 7 at 10 days, so a total of 90 days. This means that 90 days is the fastest time frame we can complete all project activities plus it is the longest path that we can follow in terms of the progress of each of the activities. You may also see a table used to identify these dependencies, and in this table you can easily see that Activities 2 and 3 have a predecessor which is Activity 1. This means you can't start Activity 2 or 3 until Activity 1 is finished.

Play video starting at :3:41 and follow transcript

3:41

Now that we know how to find the critical path, let's look at network diagrams as a tool for identifying potential delays or opportunities within the project schedule. First, let's talk about float and sometimes you'll hear it called slack. Float is the amount of time an activity can be delayed without delaying the entire project's finish date. To determine the amount of float a project has we use network diagrams, and you can do this by something called a forward and a backward pass. Let's look at the same example, but do a forward pass. In order to do this forward pass, we need to give our nodes a bit more detail. This is an example of a node we will use for our forward and backward pass. In the center is the activity number. On the upper left corner is the early start, and on the upper right corner is the early finish. Early start means it's the earliest day you can start an activity. It's usually the predecessor plus 1. Early finish is calculated by adding the duration of the activity to its early start day. It represents the earliest possible day that an activity can be finished. It's pretty straightforward, but it's easier to take a look at an example. First we have our start and Activity 1. The first step in finding the project float is doing a forward pass. First, we have our Start and our Activity 1. We know Activity 1 takes 20 days, so the number 20 goes in the upper middle square. We can start Activity 1 on Day 1 which is its early start. The early finish day would be the early start plus the duration of the activity minus 1. Here's the reason for that. You can start Activity 1 on Day 1. You have all of Day 1 through all of Day 20 to complete this activity. Since it only takes 20 days, its early finish is at the end of Day 20. Now we have Activity 2 which has a dependency on Activity 1. Activity 2 takes 30 days and has an early start of 21 which is Activity 1s early finish day plus 1. Since Activity 1 finished at the end of Day 20, the earliest we can start Activity 2 is on Day 21. Activity 2s early finish is 50. You figure early finish by the early start plus duration minus 1, so that's 21 plus 30 minus 1 equals 50. Activity 3 has a duration of 10 days with an early start of 21. It has an early finish of 21 plus 10 minus 1 or 30. Activities 4 and 5, both have an early start of 51. Activity 4 takes 30 days with an early finish of 80. Activity 5 last 20 days with an early finish of 70. Activity 6 has a dependency on activity 3 and can be started on day 31 with an early finish of day 60. Activity 7 depends on both activities 4 and 5, it can not start until activity 4 is finished, and that's at day 80. So it's early start is day 81 with a 10 day duration it's early finish is 90. Activity 8 starts at 61 and ends at 70. We then have the project end. Remember, the critical path is the longest duration. The critical path would be activity 1, 2, 4, and 7, and a total project duration of 90 days.

Play video starting at :8:16 and follow transcript

8:16

The critical path is outlined here. Activity use 1, 2, 4, and 7.

Play video starting at :8:26 and follow transcript

8:26

Now, let's take a look at a backward pass. In the lower right of the node is the late finish. This is the latest that a specific activity must finish. In the lower left is the late start. This is obviously the latest start date for that activity. What we do is we start at the end of the critical path and we know the quickest the project can be done is 90 days. We put that in the late finish for both activity 7 and activity 8, since it's the latest each of those activities can finish. Let's work backward on the critical path first. For activity 4, we have a late finish of 80, which is activity 7's, late start date minus one. To figure out activity 4s late start date, we must take its late finish minus the duration of the activity plus one. So 80 minus 30 plus 1 equals 51. We'll do the same thing for activity 2. We have a late finish of 50 and a late start of 21, which is its late finish minus 30 days plus 1. The same for activity 1, late finish of 20 and a late start of one. Now, let's move on to activity 5 with a late finish of 80, and 80 minus 20 plus 1 gives us 61 for the late start. You'll notice that activity 5 is dependent on activity 2 to finish. We know that activity 2 has a late finish date of 50, but that activity 5 it doesn't have to start until day 61. It can have an early start on day 51, but it really doesn't have to start past day 61. Activity 6 has a late finish of 80 and a late start of 51. That leaves activity 3 with a late finish of 50 and a late start of 50 minus 10 plus 1 or 41.

Play video starting at :11:6 and follow transcript

11:06

Now that I've figured our forward pass and backward pass, we have enough information to figure out our float. Float means that an activity can be delayed without impacting the overall schedule. Float goes into the lower middle boxes of the nodes. Now to determine the value, it's either the late finish minus early finish or the late start minus early start for that particular activity, either one will give you the same value. So starting on the critical path in activity 1, we can see that looking at the early finish minus the early start we have 20 minus 20 or 0 days float. This makes sense since it's on the critical path. This goes for activities 2 and activity 4, and activity 7 since they're all on the critical path. That's what the critical path means. It's the earliest possible finish date, so there's no question for delays. You'll have zero float on your critical path. Let's take a look at activity 6, a bit closer. We can see that it has an early start date of 31. This is because it depends on activity 3 to finish at day 30. But activity 6 also has a late start of 51. This means that activity 6 has a float of 20. Meaning the activity 6 can be delayed up to 20 days without impacting the overall project schedule. That's how we figure float. Float is the number of days that can be delayed for that particular activity without impacting the overall schedule.

Schedule Baseline and Gannt Chart

Now that we have determined the project’s critical path, durations, and slack, it is time to develop the project schedule baseline. According to PMI, the schedule baseline is, “the approved version of a schedule model that can be changed only through formal change control procedures and is used as a basis for comparison to actual results.  It is accepted and approved by the appropriate stakeholders as the schedule baseline with baseline start dates and baseline finish dates.”

This schedule that is shared with stakeholders is usually communicated through a tool called a Gantt chart.  A Gantt chart is a graphical representation that clearly communicates the activities of the project including their start and finish dates, duration, and any project milestones.

Gantt charts are usually developed through project management software programs or through spreadsheet applications.

You may be wondering where to even start in building your own Gantt chart. I wanted to record this quick video to show you how to access Gantt chart using Google Sheets. As you can see, I've got a Google page open here, and all you will do is go to Google Sheets and open up a new sheet. Actually it'll take you to Google Sheets. On the upper right-hand side you'll see template gallery, so hit that. Go to your general templates. If you scroll all the way down, you'll see there are four different project management templates on Google Sheets for you. First one is Gantt chart project timeline, project tracking, and event marketing timeline. Any of those will work for setting up a Gantt chart. I'm going to just open up a project timeline sheet here. Once you see that it's open, all of these cells, everything is customizable. Edit a bowl so you can put your project name here, like I'm building a deck. Then all of these specific cells here are also edit a bowl, you can change them. If we cut and paste that, we know that we're going to start our charter early and move things around. All of these are available to you to edit and update and use for either your project for any courses or project timeline for any courses, or for your personal use or professional use as well, so those are available on Google Sheets templates.

Controlling the Schedule

Now that we have our project schedule detailed and developed our schedule baseline, we move into the Monitoring & Controlling process groups with the Control Schedule process.  This is the process where the project manager makes sure the project is progressing to plan. This process happens throughout the life of the project.

Compressing the Project Schedule

While monitoring the project schedule, you may find that your project is not meeting the schedule goals.  Many projects will run behind schedule.  The project manager has a few tools to “compress the schedule” or make up some time.  Two common methods are fast-tracking and crashing.

Now that we have developed the project schedule, it's time to estimate the cost of the project. The cost of the overall project is the sum of all of its activities. All project managers know the importance of estimating and controlling costs in a project. When we think of project management, we always think of delivering the project to scope, on schedule and on budget. So it's really important that we manage project costs. In this video, we'll examine the overall process for managing the project's cost.

Play video starting at ::44 and follow transcript

0:44

Project cost management is the knowledge area that contains all of the processes that allow the project manager to plan the budget to estimate the costs of activities and to manage and control the project budget. As we usually do, let's begin by looking at our project management process groups and our knowledge areas. We already know that project cost management is a knowledge area. And we can see that it contains four processes across the planning and the monitoring and controlling process groups. The first process is plan cost management and just like all other knowledge areas and project management, we must always first start with a plan. In this process, the project manager will create a document called the cost management plan. This document details the framework for how project costs will be planned and estimated and how we'll control them throughout the project.

Play video starting at :1:51 and follow transcript

1:51

Just like during the schedule planning process, the team will need to estimate project costs. They can do this by a number of ways. Perhaps they have done a similar project in the past and can use historical information to project costs. They could consult with suppliers. They could also use a number of estimation techniques based on industry standards and will dive deeper on the ways that project managers and the team can estimate costs later in this module.

Play video starting at :2:28 and follow transcript

2:28

Now the project manager develops the project budget and this is where they take all of the information determined in the cost estimating process. And then we establish a cost baseline and this baseline will serve as the initial measurement from which all future project costs will be compared to. So the project budget should also include all of the necessary funds that are needed to execute the project successfully through its life. Once the project budget is approved and the project is progressing, the project manager needs to continuously monitor and control the budget. So they do this by comparing actuals to the baseline budget. It's also during this process that the project manager uses tools known as earned value management to track the budget and to communicate directly with stakeholders. We'll learn more about earned value management further along this module.

Play video starting at :3:33 and follow transcript

3:33

The project management process for managing cost is obviously everything related to the project's budget and its costs, controlling the budget is critical to a project success. We will now look at the ways a project manager can develop and estimate costs, develop the budget and report project status through budget-based formulas and budget-based tools.

Estimating Project Cost

How much will it cost?  That is the key question.  You could provide a rough order of magnitude estimate and be -25% to 75% accurate, you could develop a budget estimate and narrow that range to -10% to 25%.  Or you could dive deeper and provide a definitive estimate which would yield about -5% to 10% accuracy.

The project team has much to consider when developing the project budget. How will we estimate the cost of the project?  Will we base our estimates on previous work?  Or should we break down each part of the WBS to determine costs?

The project team can use some of the same methods to determine costs as they did to determine the schedule.  Remember Analogous estimating? Parametric estimating?  Button-Up, Three-Point, and PERT formulas?  These are also used in estimating the cost of activities to determine the project budget.

Just like when we estimated the duration of project activities, we need to estimate the cost of each of the components of the activities so we can add them up to get a total project cost. We use many of the same tools and techniques in estimating costs as we did in estimating the project schedule. In this video, we will discuss the different categories of costs as well as review the types of estimates and later on some techniques that a project manager uses to estimate costs.

Play video starting at ::42 and follow transcript

0:42

There are many considerations when determining the cost of the project and its individual activities. First, we need to distinguish between the different types of costs. Then we can estimate the activity costs, then aggregate those estimates into a total project cost. There are different ways of doing this at different times of the project and for different purposes.

Play video starting at :1:7 and follow transcript

1:07

First we need to define the different types of costs. There are many costs associated with a project. There is the cost of materials to make things, there is the cost of labor to do the work of the project. There is overhead costs that needs to be paid to have a place to conduct the the project activities, right? So let's look at the different types of costs and try to categorize them. In the first category of costs, we have both direct costs and indirect costs. First, the direct costs, these are usually something that can be easily assigned to the project or build to the project. So, examples of direct cost is the project team wages if they are working on the project 100% of the time. Other examples include any of the materials that are needed to build the deliverable. So it's really anything that can be easily attributed directly to the cost of the project.

Play video starting at :2:9 and follow transcript

2:09

Next we have indirect costs, and these are costs that cannot be easily associated with the project. You would think of indirect costs as resources that are shared or working across multiple projects such as quality control or the cost of the PMO office or the cost of corporate tech support. Those costs are indirectly associated with your project.

Play video starting at :2:37 and follow transcript

2:37

In the second category of costs we have fixed costs and variable costs. So fixed costs are ones that don't usually change over time or change with the number of units produced. This includes lease payments for the building you're in or monthly subscriptions for software licenses. If you produce more output, those costs are fixed, they don't change. And then last we have variable costs. So these will change proportionally to the amount of output that you produce. So the more you make, the higher the variable costs. This could mean that if you produce one unit of output you have a specific material cost, right? And if you produce 50 units, of course the material cost will increase. So it varies with the units of output.

Play video starting at :3:33 and follow transcript

3:33

It's also important to note that costs can be either direct or indirect but not both, and they can be either fixed or variable but not both, but a cost can be both direct and variable. For example, if you have team members working directly for your project in an assembly line and they're fully dedicated 100% of the time they are considered direct. Let's say you need to produce more deliverables, you could hire more assembly workers and they're still direct. But since we need to produce more output, the addition of those additional resources, they're considered a variable cost because it varies with the units of output.

Play video starting at :4:19 and follow transcript

4:19

So while determining costs we can provide different levels of estimate based on an accuracy. So we may be asked for a cost range, and there are different estimates that you can offer and each have a different accuracy and are useful at different times in the project.

Play video starting at :4:41 and follow transcript

4:41

So first we have a rough order of magnitude estimate and this is a very rough estimate. It's usually used at the beginning of the project to give an educated guess of a cost. It's not very precise and it's given when we don't have a lot of detail about the project. It should be replaced with a more accurate estimate as the project progresses and the rough order of magnitude estimate falls within a range of plus 75 to negative 25%. So it's a larger guess or guesstimate. Next we have something called the budget estimate, and these estimates are much more refined when compared to the rough order of magnitude. Budget estimates are useful when we're planning the project and they are often used when making the decision to approve the project. So budget estimate will have a tighter range and it falls within a range of plus 25 to negative 10%.

Play video starting at :5:44 and follow transcript

5:44

And then we have the definitive estimate and this estimate is much more accurate. A definitive estimate is developed when the project is planned in detail and when the project team has done a detailed analysis for all of the activities and those associated costs. The definitive estimate is a much narrower range and it falls within the range of plus 10% to minus 5%. Now that we have a high level of understanding of the different categories of costs and the options for the ranges of estimates during the project life cycle. Let's take a deeper dive into the different cost estimating tools and techniques our project manager can use to develop the project budget.

The project manager is a few tools to estimate the cost of activities and materials to determine the overall project budget. You will recognize many of these same techniques as they were the same techniques we use to estimate activity duration. Let's review, compare, and contrast some of these estimating tools. Some of these same techniques for estimating costs we used in estimating project duration as well. The analogous estimating, parametric, bottom-up, three-point, and PERT estimating are used in both duration and cost estimation and project management.

Play video starting at ::53 and follow transcript

0:53

First, let's take a look at the analogous estimation tool. Again, analogous estimation is when we use historical information to determine cost of a component of the project. It's sometimes referred to as top-down estimating. Perhaps we did a similar activity on a different project. We would use that cost as a basis for our current project. It takes less time to complete, but it can also be less accurate.

Play video starting at :1:26 and follow transcript

1:26

An example of this is let's say you successfully completed an assembly line changeover project last year that converted 1,000 square feet of manufacturing space for a new model production this year. The cost of that project was $500,000 in total. Let's say now you've been assigned the project for next year's model manufacturing changeover as well. Next year they're doubling the production space to 2,000 square feet. Using an analogous estimation, you would estimate a cost of one million dollars. Again, this is just a broad estimation that would need to be narrowed later.

Play video starting at :2:8 and follow transcript

2:08

Now, when we talk about parametric estimating, we're using a mathematical modeling based estimation technique based on a specific parameter and using some historical information. It could be based on a unit like a cubic yard or a gallon or an hour of labor and you would adjust based on the different size or scope of your particular project. You might scale up or scale down based on a particular size. An example would be you know the cost of a meter of extruded aluminum and you know you need to defined amount of that material. You could estimate total meters needed times price per meter.

Play video starting at :2:52 and follow transcript

2:52

As an example or a brief overall example of that is let's say you're a project manager and you need to outsource some specific programming resource or labor since you don't have that resource in-house. The company you're working with your supplier says that the programmer will cost you $800 per day and that they will need six total days of work. You could estimate the cost of programming as $4,800 or $800 times six days.

Play video starting at :3:26 and follow transcript

3:26

Next we have bottom up estimating. This is where we use the WBS and we estimate every single activity. We need to make sure to include all of the costs, whether they be direct or indirect or variable or fixed and then we add up all the individual activity cost to develop the estimate for the project. It does take much more time, but it is much more precise than the other two.

Play video starting at :3:58 and follow transcript

3:58

Next, we have three-point estimating. Just like using three-point estimates to divine activity durations, we use subject matter experts to help us define and average an optimistic most likely and pessimistic scenarios to develop cost. Similarly to the three-point, we've got part estimating, which uses optimistic most likely and pessimistic scenarios as well but it puts more weight on the most likely scenario.

Play video starting at :4:36 and follow transcript

4:36

Since three-point estimates and PERTs are so similar, let's look at an example of how the PERT will put greater weight on the most likely. Let's say we have optimistic at $4,000 cost most likely around $8,000 and pessimistic around $15,000. The three-point estimate will take the average of the optimistic, most likely and pessimistic. The PERT puts more weight on the most likely. What it does is it takes the optimistic plus the most likely value times four plus the pessimistic, and then it divides it by six. In reality, what we're looking at is on the three-point, we take the optimistic of $4,000, the most likely of $8,000, and the pessimistic at $15,000, add those together at 27,000 divide that by three to get an average and we get a cost estimate of $9,000. It's a little bit higher than most likely. But with the PERT we take the optimistic at $4,000. We take the most likely value at $8,000 and multiply that times four, so it puts a greater weight on it. Then we take the pessimistic at $15,000, we add all those together at $51,000 and take the average. But now we divide it by six, since we've weighted the most likely. It's $51,000 divided by six or 8,500. You'll see that using the PERT, the 8,500 estimate is a little bit closer to the most likely than if we were to use the three-point estimates. There's just a really high level difference of how the PERT is weighted more heavily on the most likely when compared to the three-point estimating technique.

Now that we've estimated cost for each of the project components, including labor, materials, and any overhead, we can use those estimates to develop the project budget. This is the part we need to get the necessary funding for our project. In this video, we'll discuss the steps to follow to determine the project budget. First, let's define a few important terms. Number 1, the project budget is the total projected costs needed to complete the project scope within the project schedule. This is the entire project budget from start to finish. When all is said and done and the project is complete, it's all of the authorized funds used to execute the project. Number 2, the cost performance baseline or cost baseline, is the approved version of the budget that includes some contingency reserves. I have more on the reserves later. The cost baseline is really important because it serves as the baseline for measuring project performance throughout the project. The baseline should include key dates and milestones and this allows the project manager to compare actual project expenditures at different points in time to the baseline and it allows them to gauge project performance. What I mean by project performance is, are we behind on budget? Are we meeting our predicted milestones? Those types of questions.

Play video starting at :1:43 and follow transcript

1:43

Let's talk about cost performance baseline or cost baseline. Let's talk about how we determine the budget using the cost baseline. First, we estimate the total amount needed for each of the individual project activities. You remember we did this by using our methods such as analogous or parametric, developing specific cost estimates for each activity.

Play video starting at :2:12 and follow transcript

2:12

Then we may include something called contingency reserves. Contingency reserves are an additional amount added to the cost of the activity to cover any known risks associated with that activity. An example of a contingency reserve is let's say you were ordering an industrial washer for your project and you received a prize from your supplier. Yet they indicated that they might need you to pay an expedited fee to get it delivered from an oversea supplier. You've ordered it in enough time, so hopefully you don't need it, but it's a known risk. We may include a contingency reserve of maybe 2-5 percent for that particular work package to account for this known risk of an anticipated supply chain issue. Contingency reserves are also appropriate for project schedules as well. You may add a contingency to the schedule for the delay in the delivery as well.

Play video starting at :3:16 and follow transcript

3:16

We total the estimated cost of each of the activities along with the activity contingencies to get the estimates for the work packages, which is the total of the expenses anticipated for the project. We then may add another general contingency reserve for the total. This may be an overall five or 10 percent. An additional note on contingency reserves, they're really important to include in your project budget. If you don't include one, it's like saying, hey, no problem, every delivery will be made on time. Every task will be complete within its predicted timeframe, and we don't anticipate any problems on this project at all, and that's not very realistic, so we need to account for the known risks. A bit later in this course, we'll cover risk analysis and dive deeper on how to quantify those risks. But for now, just know it's important to plan for these known risks.

Play video starting at :4:21 and follow transcript

4:21

After we add contingency reserves to the work package estimates we have a total number, and this is our cost performance baseline. Again, this is the approved version of the budget that we will measure actual project performance against. The cost baseline is the sum of all of the cost of the project activities along with any contingency reserves, which account for known project risks. This cost performance baseline is also known as the BAC or the budget at completion.

Play video starting at :5: and follow transcript

5:00

But things don't always go as planned. We have slips in the schedule, we have cost overruns, we have to be able to pay for those as well. In order to plan for risks that are unknown, we have something called; management reserve. The management reserve is some amount of money that is held outside of the cost performance baseline or cost baseline for any uncertainty. It's important to know that the management reserve is not controlled by us, the project manager, it's controlled by management, or the sponsor, or the PMO. In order to access it, it requires going through a change process to access those funds.

Play video starting at :5:44 and follow transcript

5:44

Then we have the total project budget. This is in the cost baseline plus the management reserve. Again, the cost of every activity plus the contingency reserves equals the cost performance baseline. The cost baseline plus the management reserves, equals the total project budget.

Play video starting at :6:10 and follow transcript

6:10

You remember, earlier that I said the cost baseline should include a time component. This graph shows the relationship between the cost baseline, time, and the total budget. On the x-axis, we have the project over time. On the y-axis is the cumulative value of the project expenditure, so how much money we've spent over time. Let's take a look at this first line. It's called the cost performance baseline. Again, it's our cost baseline. It's also known as the BAC or the budget at completion. Next, we have a dotted line that represents the amount of funding we need throughout the project at different points of time. This is to fund different project activities. So this is how much we need a commitment to fund for the project over time. We need money committed at these points in time to fund our project. Funding may not come all at once, so it may be distributed as needed, and this is where a graph like this comes into play or is important. It's driven by the cost baseline and the actual expenses.

Play video starting at :7:28 and follow transcript

7:28

Next, below the cost baseline, you'll see that we have a smaller dotted line, and that represents the actual project expenditures. You can see we are staying within budget, along the project until we progress to the point where the expenditures have exceeded the cost baseline. This means we are over the BAC or the cost baseline. The funding requirements, that dotted step stair line must meet the additional need for these expenditures and that's where our management reserve comes in. It's the amount needed over the cost baseline to meet the actual project spend.

Play video starting at :8:16 and follow transcript

8:16

The cost baseline is really important since it is used to forecast our project funding requirements. It's also used to measure our project performance in terms of expenditures as well as level of completion. In order to use and measure performance, we use the baseline in something called; earned value management. Later in this module, we'll learn to use earned value management to monitor the progress of our project in terms of schedule and cost.

Now we know when we need resources, we know how much they cost, and we have an approved budget. Now it's time to procure what we need. Procurement means buying the things we need for the project that we don't either make ourselves or outsourcing for people that we don't already have within our company. Many companies have procurement offices or purchasing groups that the project manager will work with to source the items and services that they need. We will now learn about project procurement management.

Play video starting at ::41 and follow transcript

0:41

Project procurement management is the knowledge area that contains the processes that allow project managers to purchase or acquire products or services from outside the project team. This means we currently don't either employ the resources we need or have the materials on hand to complete our project. As we usually do, let's first begin by looking at our project management process groups and knowledge areas. Now, we already know that project procurement management is a knowledge area, and we can see that it contains three processes across the planning, the executing, and the monitoring and controlling process groups. The first process is plan procurement management. Just like all the other knowledge areas and project management, again, we always start with the plan. In this process, the project manager will create a document called the Procurement Management Plan. This document contains all of the activities to be done during the procurement or buying process. It should talk about if we will send requests out to bid and to whom we send those requests. It also details any constraints and it details certain stakeholder roles. It also includes the criteria on how we plan to measure competitive bids from our suppliers.

Play video starting at :2:15 and follow transcript

2:15

Conducting procurements is the process of obtaining seller responses, contacting the seller, selecting the seller, and awarding the contract. Many companies have specific procurement or buying processes or offices that they follow. This could include preferred sellers or preferred vendors. This could include formal RFPs or request for proposals from suppliers. This could also include having a separate group review proposals and award the contract to reduce any bias within the teams or preferential selection of suppliers.

Play video starting at :2:56 and follow transcript

2:56

Once the contracts are approved and the orders are placed or the agreements are in place, we have to control those procurements. This means that we manage vendor relationships, making sure lines of communication are open and everyone is performing as expected. We continuously measure contract performance and we make corrective actions where necessary with our vendors. Control procurements is also where we close out the contract, any contracts that have been fulfilled by the vendor, meaning the work is done to completion, or any contracts that have been canceled.

Play video starting at :3:35 and follow transcript

3:35

Project procurement management may seem pretty straightforward, but there are many nuances to finding and qualifying suppliers for your project. Suppliers are an extension of your team. They're very crucial stakeholders. Managing relationships with vendors is necessary to project success. We'll learn some strategies for managing vendor relationships as well as some terminology around obtaining quotes from suppliers and awarding contracts.

Projects are about creating value. Project managers create value by creating deliverables to the customer or to the client, and in order to create the deliverable we need resources. Resources mean people or things. Sometimes we have the necessary items and sometimes we don't. We may need to outsource or buy the materials or services to accomplish our project goals. This is what we call procurement. The buying of what we need. Procurement follows a few steps and these steps may seem obvious and there's some of the same steps that we follow when buying things in our personal life. Things like, what do we need, when do we need it, and where will we get it? But in project management we need to pay attention to the details that are not so intuitive. Things like, can we make this ourselves faster or for less money? Or how do we choose the best supplier in the most fair way? How do we communicate what we need to those suppliers? We've already answered a few of those questions we need for the procurement process such as Number 1, what do we need? Number 2, when do we need it? We answered those in the project scope and schedule management processes. Now let's take a look at the common tools and practices that help us answer the following questions. Number 3, do we make or buy materials or outsource services? Number 4, who will supply it to us? Number 5, how do we enter into an agreement or contract? Number 6, how will we maintain a positive relationship with our vendors and suppliers?

Make or Buy Decisions

Project managers are often involved in the decision to make or manufacture the resources needed for a project or outsource the resource to another company.  We could outsource equipment needed to build a specific part of the deliverable, or we could outsource the people, or expertise needed for a particular part of the project.

Make or buy decisions will weigh the costs of internally producing the resource vs externally sourcing.

Supplier selection is very important to the project's success. During the supplier selection process and after you award them the contract, they become important stakeholders for your project. Companies need to be strategic in their supplier selection and have a well defined process in choosing the best vendor partners.

Play video starting at ::32 and follow transcript

0:32

There are many processes to follow when awarding a contract to an external supplier or to outsource a good or service. In this video, I'll discuss the high level process of supplier selection and supplier management.

Play video starting at ::49 and follow transcript

0:49

Let's take a look at this very high level flow chart that follows outsourcing of goods and supplier selection. This process kicks off when we decide to outsource and gain approval for entering into the procurement process with an external supplier. First we develop a document known as the statement of work, and the statement of work is a document that you'll use to describe the details of the project. It should include all of the relevant items that will be delivered. The timeline involved in delivering, when the supplier should invoice you as the customer and what your payment terms are. It should be comprehensive enough so that any vendors should be able to understand the project's requirements and what they need to provide as part of those requirements. Then we provide a document known as terms of reference. Terms of reference is especially important when the project is technical in nature, the terms of reference is a description of all of the technical requirements of the project. It includes any and all of the engineering related work, and it also details the level of expertise expected from suppliers such as any work that must be conducted by someone that is licensed or credentialed as part of the contract. These documents are provided as part of a request for quote or a request for proposal. You'll also hear it as our RQ or FP. And this is the formal document that is sent to potential suppliers that acts as an invitation to bid on the contract for the project. So after these potential suppliers received the request for quote or the request for bid, they may offer a quote. And you could receive quotes from multiple suppliers. So you need to enter into an evaluation phase and evaluate each of those bids or quotes. We evaluate in a number of ways. There are different criteria we use such as supplier history, have they worked with us before? What is the risk of using a new supplier and how will we rate a new supplier? Do they have references? How's their quality? So after we evaluate those quotes or those bids from the suppliers who supplied them. We will enter into a negotiation with the supplier or potential supplier for things like pricing or payment terms, we may not accept the first proposal that they offer. So sometimes there's some back and forth that goes place that takes place during the negotiation process. After negotiations between the supplier and the buyer, we would enter into the contract phase. And this is where we award the contract to the supplier for the goods or the services. Later on in this module, we'll explore the different types of contracts and how different contracts carry different levels of risk for us as the buyer or for the project. After the contracts awarded, the supplier starts to perform or deliver on the contract. And this is where they do the work or supply the goods. And of course this could be either be like a one time delivery for a piece of capital equipment or it could be ongoing such as outsourcing of a person to do specific work on the project over time, even over the entire project life. Right, either way, we move into the control and monitor phase. And this is where we measure the supplier's performance and the supplier does any corrective actions if there are issues. And this is where we view them as a stakeholder and communication is extremely important between us as the buyer and them as the supplier during this phase.

Procurement Documents

Statement of Work

We have now made our decision to procure resources needed for our project.  In order to develop a request for quote or request for proposal to send out to potential suppliers, we need to develop a formal Statement of Work.  A Statement of Work is a detailed overview of the scope of the project.  It is considered a legally binding document which contains all of the project requirements as well as any contractual terms.

A Statement of Work could contain the following sections (depending on the project):

- Introduction

- Purpose statement (What is the purpose of the project?)

- Scope statement

- Work location

- Schedule duration

- Types of tasks or deliverables

- Milestones

- Testing requirements

- Payment terms or payment schedule

- Other important information

This may look a bit like the information included in the Project Charter, but there are clear differences.

Terms of Reference

Terms of Reference is a description of the technical requirements of the request for proposal or bidding documents. It is especially important in projects that may be governmentally regulated or require a specific technical credential from the supplier.  The Terms of Reference should include the project scope as well as the schedule.  It should also explain any stakeholder interests such as permits, standards or regulations associated with the project.

Sometimes the reason you are outsourcing is because you don’t have the appropriate people who have professional qualifications or certifications.  Those details will also need to be included in the Terms of Reference.

Evaluating Vendors

You have issued the request for proposals and have received a number of bids from vendors.  Now it is time for you and the project team to evaluate the vendors and make a decision.

We've selected a vendor and are ready to purchase our materials. We need a place to order or enter into a contract with the supplier to receive our goods or services. Project managers should understand the contracting process, as well as the different types of contracts commonly used in project-based procurement. In this video, we'll learn about contracts. A contract is a legally binding agreement between parties that creates mutual obligations enforceable by law. Really what this means is that contracts are essentially a promise, I promise to pay you for goods or services rendered. What makes it different than a promise is that it's enforceable by law. If one part of a contract party is in breach or doesn't hold up their end of the promise, the other party can sue them in a court of law.

Play video starting at :1:13 and follow transcript

1:13

In order for a promise to be enforceable by law, it must contain the elements of a contract. Here are some of the elements that make a contract a contract. First, there must be an offer. An offer means one party made a promise to do something specific, such as, I will supply you this piece of equipment that you need for your project. Second, there's something called consideration, which means something of value was promised in exchange for that offer. This could mean that I'll pay you $2,000 for the equipment upon delivery. Really consideration is the value that makes the parties want to enter into the contract in the first place. Then third, there's acceptance. This is where the offer was accepted. It's where the parties agree on the offer and the consideration. Then finally, we have mutuality. It's something called the meeting of the minds. It's much easier to say. That means that the parties understand and agree to the basic terms of the contract and that both of the parties entering into the contract have the authority to do so. I'm allowed to enter into this contract. I'm over 18, I have got whatever the law is in where you live, that you've got the authority to enter into a contract. It's also worth mentioning that in order for a contract to be valid, it must also be legal. A contract to do something or provide something illegal is not enforceable by law.

Play video starting at :2:58 and follow transcript

2:58

Let's look at the different kinds and types of contracts that we have. First is the fixed price contract. Fixed price contracts are used when deliverables are clearly defined. Once scope is provided to the supplier and they can offer a fixed price quotation for the agreed deliverables or the scope of work.

Play video starting at :3:23 and follow transcript

3:23

Once both parties enter into a fixed price contract, the buyer can be sure that that is all that they will pack to pay once the delivery is complete or the work is done by the seller. The price they quote to you is the price you pay. The seller assumes more risk in a fixed price contract than the buyer does. If the seller's cost increased during the life of the contract, they will not be able to pass on that increase of costs to the buyer. The price is fixed. There is something called a fixed price incentive contract as well. It's similar to the firm fixed price, but it allows for the seller to receive more money for some incentive. This could mean that the buyer could incentivize the seller to finish the work early with some type of bonus structure for early delivery or for meeting the contract requirements ahead of schedule. A fixed price with economic price adjustment is a fixed price contract that allows the seller to adjust the price if, for instance, the cost of materials increases or the cost of labor increases. It allows for a price adjustment up or down based on the cost of materials or labor or something like that.

Play video starting at :4:42 and follow transcript

4:42

Time and material contracts are very popular when outsourcing labor and materials. It's used when the intent is to reimburse one party for the costs incurred when completing a job. This may include temporary employees for the project needed for their specific skill set or their specific expertise. This type of contract is used when the buyer doesn't know the exact time needed to accomplish the task. The risk is higher with the buyer than what the supplier in a time and material contract because the cost can quickly get out of hand and the labor can take longer than the buyer expected.

Play video starting at :5:27 and follow transcript

5:27

In a cost plus contract, the buyer agrees to pay the actual cost incurred by the seller plus some predetermined additional fee. This is used when the exact requirements are ambiguous or not really very clear. The risk is with the buyer in cost-plus contracts because you could end up paying more than expected for materials or labor. The supplier is not incentivized to finish early or even incentivize to finish on time since all of the costs are being covered by the buyer for the span of the contract.

Play video starting at :6:7 and follow transcript

6:07

There's something called a retainer. This is where the seller prepays a specific amount for a specific number of employee hours and you would use this when the statement of work isn't that clear. Retainer agreements are becoming more and more popular with freelancers and with the gig economy since you may need to hire individuals for your project, and the risk is really with the buyer since retainers are usually paid in advance of the work that's been completed for your project.

Play video starting at :6:48 and follow transcript

6:48

As you can see, different types of contracts come with different risks. Sometimes it's riskier for us, the buyer, sometimes the risk lies with the supplier. Once the contract is awarded, we need to move into the process of monitoring and controlling the procurement and building relationships with our suppliers.

Supplier Relationship Management

We have selected our suppliers, placed orders, and are receiving the necessary goods and services for our project.  We are moving into the Project Management process of “Control Procurements” which means we monitor supplier performance, manage the supplier relationship and finally, close out the contracts upon completion.

One important part of controlling procurements in managing the relationship with our suppliers. Supplier Relationship Management is becoming increasingly important as supply chains tighten.  A positive customer / supplier relationship has been known to drive new innovation.

What do we mean by risk? Risk sounds bad, right? Well, in project management it just means uncertainty. And as you've learned already, project managers always like to have a plan. And this is especially true for traditional or predictive models of project management, but risk is something that may or may not happen in the future. It could be bad like some weather event or obsolescence of a product or it could be good, it could be a good risk, such as an opportunity emerging or a new market opening up for us. Either way, it is that uncertainty that project managers need to plan for. Well, how do we plan for uncertainty? It sounds tough, right? There's a number of techniques that we project managers use to predict risks. We can quantify risks and we use these to mitigate those risks. So in this module we'll learn about project risk management.

The purpose of project risk management is to identify and manage risks that have the potential to impact our overall projects plan. And there are two types of risk on every project. First is the individual project risk which is an event that could have either a negative or even a positive impact on one or more of the project's objectives. And then we have the overall project risk which is the effect of uncertainty on the entire project as a whole. It's important that we manage both types of risks throughout the project.

Play video starting at ::55 and follow transcript

0:55

When we start discussing a new knowledge area, we always start by looking at our project management process group. And we can see that the knowledge area of project risk management has seven different processes across the planning, the executing and the monitoring and controlling process groups. The first process is plan risk management, and just like all other knowledge areas in project management, we must first start with a plan. In this process, the project manager will create a document called the risk management plan. And this document details how risk management activities will occur. It also defines the key stakeholders and how they will identify and analyze risks as well. How you plan to respond to risks and how you plan to monitor and control the risks to your project is also included. It's important to talk about the differences between the risk tolerance of companies, just like different people have a different tolerance for risk so do companies. So some companies take the approach of high risk equals high reward while others may be much more risk averse or much more conservative in their risk tolerance.

Play video starting at :2:18 and follow transcript

2:18

Also part of the planning process includes identifying project risks. So after we identify the risks, they go into something called the risk register and the risk register contains details of the project risks. The register is used to further analyze each risk to determine the appropriate risk response. And it's important for the entire project team to engage in this activity. Since it's really the team and the other stakeholders who have the experience and they have the knowledge of the specific processes and they're more familiar with the potential risks. Then the project manager is alone. After the risks have been identified, you'll create that again you'll create this risk register. Next, the project manager will analyze the risks. And the first part of analyzing the risks is performing a qualitative analysis and qualitative risk analysis is really what you do is prioritize your project risks based on their probability of occurrence, and then what the impact of that occurrence is on the project as a whole. There are a number of categories project managers used to evaluate each project risk, and we will learn more about those later in this module. But this is a data driven process that helps guide the team to develop the appropriate risk responses. And after we perform the qualitative analysis, we'll go into the quantitative analysis. And this is where the team uses data stimulation techniques to determine the combined effect of all of these risks to the overall project objectives. Quantitative analysis is especially important in large complex projects with many identified risks.

Play video starting at :4:30 and follow transcript

4:30

During the planning process, the project team will also use the data developed from the qualitative and quantitative analysis to develop a strategy to respond to both the individual and the overall project risks. And this includes specific actions for each of the prioritized risks along with a cost estimate of how much the risk response will cost. And this is where our contingencies that we talked about in budget management really come into play and are really important. Now that the project manager, it's time to move into the executing phase of the project where we implement risk responses as events happen throughout the project. And this is where we now have to reduce our risk exposure by implementing the plan we developed as needed.

Play video starting at :5:31 and follow transcript

5:31

So then we'll move into the monitor and control process group where the project manager must continuously evaluate the effectiveness of our responses to the risks. And this is really an ongoing process because new risks and new opportunities arrive throughout the project. And this is the overall plan for how project managers manage risk.

Risk Management Plan

Just like all other plans the project manager develops, the risk management plan will document how the project team will identify, analyze, prioritize and respond to potential risks (or opportunities) to the project.

Risk Management Plans contain many of the following categories/sections:

- Strategy for managing risks

- Methodology for identifying risks

- Stakeholder roles and responsibilities

- Risk categories

- Risk tolerance summary

- Risk probabilities

- Risk impacts

- Resources needed

- How you plan to track and monitor risks

In this video, we will look at the different methods project managers use to identify project risks. It is important to conduct this risk identification process with the entire project team and make sure to include stakeholders as well, as they all have greater understanding of each of the risks. They may also be the ones who need to respond to those risks. Collaboration creates a sense of ownership, and that's important when it comes to project risk management. You have the project team assembled and now it's time to identify any potential risks or opportunities to your project. Remember, a risk can be negative or something bad that happens to your project deliverables or it can be a good risk or an opportunity or something good that can have a positive impact to your project, or its deliverables. There are ways a project manager can gather the necessary information from stakeholders to identify any potential risks. These are documented in an output known as the risk register and the risk report.

Play video starting at :1:21 and follow transcript

1:21

A good place to start is by reviewing all of the project documents. You're looking for any uncertainty or ambiguity in contracts with suppliers, or you are reviewing the assumptions you've made when developing the scope, or the schedule, or the budget. Having another review of the project documents can help the team identify any potential risks associated with the scope or with the deliverables, or with the suppliers. You can also look at the results of similar projects for any potential risks based on their previous results as well.

Play video starting at :2:3 and follow transcript

2:03

You can also conduct a traditional brainstorming session. The idea behind brainstorming is to gather everyone together to generate ideas or identify any potential risks or opportunities. There are no bad ideas, everything is considered. People are encouraged to offer up any and all ideas while someone is capturing all of this information. There's no criticism of any ideas and we're looking for a large number of ideas or potential risks in this case, and we can analyze each of those risks or ideas later. Many times the project manager facilitates the brainstorming session. Here are a few ground rules you should follow when facilitating a brainstorming session. First, clearly state the objectives or the purpose of the session. In this case, it is identifying any potential risks to the project. Second is generating ideas. This could be in the form of a round-robin, where you go around the room and ask each individual to contribute an idea. You can do this multiple times. Or it can be through an anonymous written idea that people just write down on a post-it note and stick it to the wall. Again, we're looking for volume, not quantity. The more ideas, the better. Another rule to follow is that you should make sure people feel safe in offering out-of-the-box ideas. Criticizing ideas of any sort during this brainstorming session should not be allowed.

Play video starting at :3:46 and follow transcript

3:46

Also, the project manager could conduct a SWOT analysis, and this is spelled S-W-O-T. A SWOT analysis identifies any project strengths, weaknesses, opportunities, and threats. This is good to look at at a really high level and not necessarily the activity level or even the project level sometimes. What you're looking for are what are your corporate strengths? What are the weaknesses of the company? Then for opportunities and for threats, you can become a little bit more narrow. What opportunities does my company have as a result of this project? Or what are the threats to the company or to the project itself? Doing a SWOT analysis allows the project team to take a really high level approach to identifying risks associated with the project.

Play video starting at :4:43 and follow transcript

4:43

Next, we have interviews. Projects, risks, and opportunities can be identified by interviewing experienced project managers, interviewing relevant stakeholders, and especially subject matter experts. You can and should ask about similar projects and how those risks were realized and the impact that those had on those previous projects. You can ask general questions such as, what do you think could go wrong with this project? What opportunities do you think might come from this project? Just really open questions to drive conversations from your subject matter experts and stakeholders.

Play video starting at :5:27 and follow transcript

5:27

Another way to get input from subject matter experts and relevant stakeholders is by using the Delphi technique. The Delphi technique is a process where you get anonymous opinions, you get anonymous judgments from experts, and you get them individually instead of collectively. There's this phenomenon known as collective bias, where members of a group can be swayed by one another and their comments and their input. By following the Delphi technique, that bias is avoided. The first step is to identify the group members or subject matter experts. Then you develop a questionnaire asking each member to generate a list of concerns or generate a list of risks or opportunities. You take those results from the first questionnaire and summarize them and develop survey Number 2. In that survey or questionnaire Number 2, you ask the subject matter experts, again, to rank or rate each of the responses from the first survey. In this next round, you can include the rankings and the qualitative feedback, and ask for further clarification. This can go on for a number of rounds until you gain a consensus on the risks and the types of risks, and the priorities of those.

Play video starting at :6:53 and follow transcript

6:53

These are just a few of the techniques that you can use to identify risks of a project. Upon completion of the risk identification phase, the project manager develops the risk register, which provides the details for the identified risks in the risk report, which offers a summary of overall risk exposure.

The Risk Register & Risk Report

After identifying the risks (and opportunities) in a project, the project manager develops the Risk Register and the Risk Report.

Risk Register

The risk register is a document that collects the results from the risk identification. It is a log that tracks and prioritizes potential risks.  You will use this prioritized list in the next step which is risk analysis.

Risk Report

A risk report is also an output of the process of identifying risks.  The risk report is a formal summary of the company’s overall exposure to risk.  It should include opportunities and threats and be succinct enough to communicate risk at a high level to corporate management.

During our identify risk phase, we generated a large number of risks. Some of them may be more risky than others and not all risks have to go through a formal quantitative analysis. We use qualitative analysis to make a quicker decision on which risks need further quantitative analysis. In this video, we'll look at the process of conducting a qualitative risk analysis. Now is the time to analyze each of the identified project risks. First, we should perform a qualitative analysis. The purpose of a qualitative analysis is just to make a quick and subjective decision on whether the risk that's posed is great enough for further analysis. Is this risk something that we just need to be aware of and log into our risk register? Or is it critical enough that we should spend some more time analyzing that particular risk and further quantify its impact on our project? How do we perform a qualitative risk analysis? Well, first, we need to prioritize each of the risks based on their probability and their impact on our project.

Play video starting at :1:33 and follow transcript

1:33

In order for the project team to determine probability and impact, they need to be able to evaluate based on a few parameters. Let's take a look at some of the parameters they should consider. The first is urgency. Urgency means how long until this risk happens. The second is proximity, and that's really how long will it take until this risk impacts our project. The third is dormancy, is how long after it happens will it take to make an impact or will it lay dormant for a while and then impact after certain amount of time? Then we have manageability. This is how easily can we manage this risk. If it's something we can manage easily, it shouldn't have too much of an impact. The next is controllability. Is this risk something that we can control? Then detectability, how easily can we detect that this risk is about to happen before it happens? Does it have any warning signs or signals? Next we have connectivity, and is this risk related to another project risk. If this risk happens, will one of our other project risks happen because of it? How are they connected? One of the other ones is strategic impact, and is if this risk is realized, how does it impact our company goals as a whole? Then propinquity, I can't say that word. How is this risk perceived? What is the perception of it from stakeholders? How is it received and taken by other stakeholders if this risk were to really happen? Propinquity, there we go. One way we can do that to analyze it after considering those aspects or characteristics is to perform a probability impact matrix, and that is just a graphical representation or a grid that allows our project team to quickly assess the probability of each of the identified risks in terms of their occurrence and the impact to our project. On the left column, we have the specific risks, and we will rate each one based on their probability of them happening, the impact to the project. Then from there, we'll determine what we feel as a project team is our risk level of that particular risk happening. Is that low, moderate, or high? Let's take an example from some of the common project risks we learned about from our reading assignment. First, we have data security. Let's say we view data security or some data breach, the probability of that happening is pretty moderate, not low, not high, but in the middle. But it would have significant impact to our project, high impact. We as a team have rated the risk level of data security as high. The next is around communication. Let's say one of the project risks we identified was our email server goes down, and we view the probability of that as low and really it might have low impact to our project because we have other ways of communicating. We determined that the risk level to the overall project for this is low. Next we look at a supply chain delay, so a supplier is late on delivering something we need. Probability is high. It happens quite often that somebody misses a deadline. The impact of the project, we would consider that to be low. Perhaps there are redundancies or something built in. We would assign this a risk level of moderate. Then one other one that was identified in our reading was material theft, so things from the project being stolen. We view that probability is low with a moderate impact to the project depending on what it is. We have rated the risk level of material theft as low. Putting a chart like this together will help you determine which risks we should analyze further with quantitative analysis, and those risks which have a low probability and low impact may not need that analysis or a strategy to mitigate them. We may just want to log those into the risk register and monitor them throughout the project. The greater probability of a risk or the greater the impact to the project if that risk is realized, the more necessary it becomes to do further analysis on that particular risk. Qualitative risk analysis is the tool that teams use to make relatively quick decisions on whether a potential risk will be impactful enough to warrant further analysis. Once you've determined those risks that have a higher probability of impacting your project, you want to conduct a more detailed quantitative analysis and develop strategies to prevent or react to those risks.

Quantitative Risk Analysis

Now that we have qualified our risks through the qualitative analysis process, you have decided to conduct a quantitative analysis to further predict the potential impact of risks to your overall project. Knowing the effects of risks on your project, and your company, will allow you to make better decisions about how and when to mitigate or avoid those risks. It also gives us an estimate of how much we need for Contingency Reserves. Please review Project Cost Management if you need a refresher on contingency reserves.

Project managers have a variety of tools they can use in quantitative risk analysis.  We will explore three common methods:

- Expected Monetary Value

- Decision Trees

- Monte Carlo Simulation

Decision Tree Analysis

Decision Trees are an excellent way to visualize different risks and probabilities for decision making.

Monte Carlo Simulations

Monte Carlo Analysis is a tool used in risk management as well as project schedule management to provide a range of risk outcomes to better quantify the risk to our projects. It is commonly used in large projects with many identified risks.

After we've analyzed our individual risks for the impact on both the individual components of our project, as well as our project as a whole, project managers need to develop a plan for responding to the risks should they occur. The entire project team should assist in developing the strategies for responding to risks. In this video, we will discuss strategies that project managers use in responding to risks. Having a strategy for responding to identified risks will minimize any negative impacts to the project and maximize project opportunities. Again, the types of negative impacts we're talking about are threats or bad risks. But remember, we also have good risks or opportunities. These can arise any time during the project life, and we want to maximize any positive risks and minimize any negative.

Play video starting at :1:11 and follow transcript

1:11

There are a number of strategies for responding to both negative risks and positive risks. First is to escalate, and it's appropriate to escalate the risk of a negative threat to the project sponsor when you are not able to respond to the threat yourself as the project manager or within the project team, or if it has significant implications to the company as a whole. It's also appropriate to escalate any opportunities that arise as well, and this could be technology breakthroughs or market information you discovered throughout the progression of the project. Next is negative risk of avoidance. Of course, you want to avoid any risk to the project but what we mean here is when the project team can perform some action to eliminate the threat or protect the project from any impact. On the positive side, we have exploiting the opportunity. This is where the project team has the ability to capture the benefit of the opportunity by somehow making it happen or initiating it.

Play video starting at :2:24 and follow transcript

2:24

Then we have transference of risk. Transference means we transfer the risk to someone else, and this could be a third party. An example of this would be if you identified a risk having to do with theft of materials. In order to transfer risk, you could purchase an insurance policy to cover any theft, therefore, transferring that risk to another party, which is the insurance company. On the positive risk side, we have sharing. Sharing means transferring the benefit if the opportunity occurs. This could mean entering into partnerships, maybe with a partner organization or a subsidiary of your organization who could benefit from this opportunity should it arise.

Play video starting at :3:16 and follow transcript

3:16

Next, we have mitigation of negative risks, and mitigation means that we take some action to reduce the probability of the occurrence of this risk. This means it's always better to try to prevent it from happening than to have to pay for it later. On the positive side, we have enhancing, and this is where we take some action to try to make the positive risk happen. We can do whatever we can to make sure to promote the conditions to make that risk or opportunity happen. Then we have acceptance. This is for both negative and positive risks. This means that we know the risk of either negative or the opportunity is there, but we don't actively do anything about it. You would choose acceptance if the risk doesn't have that much of a negative impact or that much of a positive financial impact on your project, or if the probability of it happening might be very low.

Play video starting at :4:21 and follow transcript

4:21

Having a risk response strategy that is well documented and accepted by the project team allows you the ability to quickly react if those events were to happen. Now let's take a look at how we implement risk responses and monitor our risks throughout the project.

Now that we have our strategy for responding to the risks that we identified, once our project is in the execution phase, we need to continuously monitor and see if these risks have occurred or have been triggered and measure our responses. Are they working? Are they appropriate responses? In this video, I'll discuss the four main steps in monitoring risks in your project. So the first step is pretty intuitive. It's to monitor for identified risks. Did the project team miss a milestone? Did a supplier miss a deadline? Number two, implement risk responses. If a risk is occurring, we need to implement the documented risk response. Is the risk owner or the person who's responsible to respond to the risk, are they actively implementing that response? Number three, evaluate the response. Is the response working as predicted? Has the risk response created new problems or new risks? And finally, number four, continuously analyze for new risks. New risk can arise at any point during the project. And we need to continually look for new risks and new opportunities, and perform risk analysis for any of these new threats.

Quality management is about meeting stakeholder expectations. It's not a one time event, but it's an ongoing process throughout your project and it focuses on preventing or correcting errors or poor performance. Project quality management is the knowledge area that contains the processes that allow project managers to determine the quality policy and determine and control the quality measures for the entire project.

Play video starting at ::46 and follow transcript

0:46

As we usually do, let's begin by looking at our project management, process groups and knowledge areas. Again, we already know that project quality management is a knowledge area and we can see that it contains three processes. It's across the planning, the executing and monitoring and the controlling process groups. The first process is plan quality management and again, just like all of the other areas and project management, we start with the plan. In this process, the project manager will create a document called the quality management plan. And to accomplish this, we need to identify the quality requirements for the project and each of the project deliverables. And this is a really important step because it'll tell us the requirements that we have to comply to or the level of quality that's necessary to deliver a successful project to our customer.

Play video starting at :1:45 and follow transcript

1:45

The next process is managing quality and sometimes we refer to this process of managing quality as quality assurance. And this is all about the process, right? The process of making sure quality is built into the project through the use of different quality management tools. And we'll review these tools later in the module, but this is really all about answering the question. How will we be assured that we're producing a product that meets the quality standards that were defined in the quality management plan?

Play video starting at :2:25 and follow transcript

2:25

Now, let's talk about controlling quality and it's about measuring, monitoring and controlling all of the quality activities throughout the project. And we want to make sure that we deliver a complete and correct product to our customer. So this is a data driven process that is performed throughout the project to demonstrate that we're meeting the customer's expectations of quality as determined in the other two steps. So it's about measuring, collecting data and reporting the data.

Play video starting at :3:1 and follow transcript

3:01

It's important for the project manager to understand the quality requirements of their own company, the clients, as well as industry specific standards. Quality management is a continuous process from the beginning through project completion and we want to meet the client's expectations for deliverables. And project quality management gives us the tools and the methodology to achieve this goal.

Project Quality Management

According to the PMBOK, Project Quality Management is the process for “incorporating the organization’s quality policy regarding planning, managing, and controlling project and product quality requirements in order to meet stakeholders’ objectives.”

Managing quality is an ongoing process throughout the project.  It isn’t just inspecting the project deliverables to see if they meet the required specifications.  The goal is to prevent defects through the use of standards and tools to ensure the project team understands what is meant by quality for the project.

Global Knowledge developed a white paper that reads similar to a chapter in a book.  It succinctly describes the project quality management process and introduces the tools and techniques project managers often use to plan and control quality. It serves as an excellent foundation for applying the tools we will learn in this module.

How do we know that we are meeting quality standards and what are the types of things we measure to make sure that we are adhering to our quality policy? In this video we will look at a few quality characteristics that are used to define both product and process quality. Quality characteristics are the attributes, the measures and the process methods that are specific to a project and its deliverables. We know not every project is the same. All projects are different, so the characteristics or measurements of quality will be different for each project, but let's take a look at some of the common characteristics of quality that we can examine and measure to validate that we are meeting the required project deliverables.

Play video starting at ::59 and follow transcript

0:59

We can view quality characteristics through the lens of either the product itself or our process. First, let's take a look at the characteristics of product quality. First is reliability. What we mean by reliability is, does it perform as needed? Does the product perform as needed? We can also look at reliability through a process, is our process for making multiple products the same and producing the same product each time. Suitability. Does it work for the application that it's intended? Functionality. Doesn't meet the requirements that the customer or the client specified in the project scope process? Technological. Are the dimensions correct? Is it the right size? Is it the right color? Is it the right weight? All of the physical attributes with regard to measuring quality. Next are the characteristics of the process, so is it complete, have we completed the project? Have we completed the deliverables per the scope? Contractual. Did we meet any safety requirements? Did we meet our warranty requirements? Anything that was specified within the contract. Is it on time, and we can measure our process based on time, and did we follow the process with integrity, and being ethical in our manufacturing as well? Not all of these are specific to every project. It all depends on what your company or corporate quality policy is, so in the next module we'll take a look at some specific quality policies.

Quality Policy

Quality policies can also be known as a Quality Management System. Simply put, a company’s quality policy is a statement or framework that aligns with the organization's mission and strategic vision. A company’s quality policy can also be guided by the industry they serve such as those for the automotive industry or prescription drug manufacturing.

product and process quality have associated costs. What does it cost? If we have an error in quality, we have to correct it and that also has a cost. But there are costs associated with preventing errors as well. In this video we'll discuss the cost of quality.

Play video starting at ::30 and follow transcript

0:30

Quality isn't free, it has a cost. And in project management, when we talk about the cost of quality, we mean the cumulative cost of conforming to the quality standards that we've set for our project. And this includes the cost of meeting the requirements or the cost of doing everything right. And it also includes the cost of non conformance. So if something goes wrong and we have to correct it, it's the cost of those corrective actions as well. So it's a total cost of meeting our quality standards, plus the cost of any corrections.

Play video starting at :1:6 and follow transcript

1:06

We can look at the cost of quality in three different categories. The first is prevention. And when we think of prevention, we think of everything that all of the cost associated with preventing an error from happening. And we can often think of this as quality assurance. The second is appraisal and these are costs associated with, you know, monitoring, controlling and testing. So we view these more as quality control and the third is the cost of failure. And those are really just the costs incurred if we have an a an event or a quality error.

Play video starting at :1:45 and follow transcript

1:45

So, first, let's look at the cost of prevention and preventing an error before it happens is ideal. And what can we do to prevent these errors. And this is often done through our quality assurance processes and procedures. It could be any costs associated with the project before we actually make it or produce deliverables. Examples could include any of the costs that we've incurred due to selecting a higher quality material or supplier or any costs in the design that make it more streamlined or easier to manufacture, thus reducing any potential for quality errors.

Play video starting at :2:24 and follow transcript

2:24

The second, we have appraisal costs and appraisal costs are associated with monitoring or controlling quality activities. And this could be any of the inspection costs of incoming materials. It could be the cost of testing our outgoing materials or finished products or verification of any of our machines. These are costs associated with any activity that we must do to check to see if any errors have occurred.

Play video starting at :2:56 and follow transcript

2:56

And then we've got the cost of failure and this is when we want to avoid and it's the cost that we, that we have occurred due to an error that has happened. And this means we have a non conformance to scope a non conformance to requirements and we have to perform a corrective action. So there are two types of failure costs. There's an internal failure cost and an external and the internal any waste. So if we have to rework an item, we may have to scrap the original item. If it had an error and that has a cost, then there's the external errors and this is if the customer or stakeholder has actually received the product or deliverable and there's a failure with it, so we may have to bring it back in and rework it, or we may have to go out into the field and service it. Both of these are external errors and are really quite costly.

Quality Assurance

Quality assurance is the portion of quality management that ensures all quality-related activities are being performed effectively.  Quality assurance is about preventing errors.

Quality Assurance Terms:

- TQM - Total Quality Management. A management system that involves all employees in quality improvement.  The belief is that everyone is in charge of quality.

- Continuous Improvement - Continues improvement assumes no system is perfect and we need to make small, constant improvements to improve quality.

- PDCA - Plan, Do, Check, Act. A cycle of continuous improvement.

- Kaizen - A literal translation of Kaizen from Japanese means “change for the better”. It is a continuous improvement methodology that focuses on culture and the team.

PDCA

Plan, Do, Check, Act.  PDCA is a quality framework for continuous improvement. It is based on a repeating cycle that allows the team to improve quality and productivity as well as spur innovation.

Quality Control in Project Management

While quality assurance is about the prevention of errors, quality control is about the detection and correction of errors.

Quality Control Tools, Techniques, and Charts

- Histograms- a bar chart that graphically displays the frequency of measurements or other specific measurement.

- Statistical Sampling - Selecting a portion of the population (or grouping) for testing. The sample should be representative of the entire population.

- Control Chart - graphical representation used in projects with repetitive activities to analyze data to identify potential errors.

- Scatter Diagrams- a chart that shows the association between two specific variables. Used when you have related variables.

- Run Chart - a line graph that looks at quality data over time to look for trends or patterns.

- Cause and Effect Diagram or Ishikawa Diagram - Shows the relationships between the different variables within a process. Used to identify possible causes of quality error.

- Pareto Chart - Used to analyze data to visualize the frequency of an error.  It is based on the principle that 80% of errors come from only 20% of inputs or causes.

Now let's discuss change. No matter how much we plan or prepare, or even if we execute the project plan flawlessly, there will always be changes. The customer may request changes to the scope of the project. We may have to change something due to a quality issue. We could have a supplier who cannot fulfill their obligation to the contract. It could be a number of different reasons. In Project Management, we have a process called Integrated Change Control, and this is all about evaluating the impact of changes on our project. In this video, we will discuss how we control change. Integrated Change Control is the process of reviewing and evaluating proposed project changes for impacts on risk, on the budget, on your schedule, on quality, and really any area of the project. Changes to the project can happen for a number of reasons. The clients or stakeholders could request changes to the deliverables such as the change in dimensions or some other physical attribute. We could also have an internal data breach that requires us to make a change to the way that we protect our data, or we may have a technological change that impacts some portion of our project. No matter what the reason for change, it's important to know that the process in traditional project management for controlling change. Now I do want to note that what I'm going to discuss is only for predictive models of Project Management, where change has greater impact on our project plan. In Agile Project Management, change is good, changes welcomed. If you're interested in learning more about change in Agile environments, you can check out my other class in Agile Project Management. The first step is talking about the process. The process kicks off with a project manager initiating the change. You'll want to make sure to include all relevant documentation, and this would include analysis of any impacts on the project scope, on the budget, on the timeline, really any impacts to any components of the project. Next is an approval process. Many times change will have to be reviewed by a Change Control Board or a CCB. Change Control Board is made up of a group of people who are familiar with the project, who will determine if the change should be made.

Play video starting at :2:47 and follow transcript

2:47

The Change Control Board will either approve or reject the change. If they reject it, it's the process is over. If the CCB approves the change, the Project Manager will have to take the analyses and update the project's baselines, like the budget baseline, and the schedule baseline, and scope baseline, all of the baselines if there's any impact. Then they'll also want to update the overall project plan, as well, to reflect the changes. Next, the Project Manager will implement the change along with the project team. Finally, we will communicate. The Project Manager communicates the changes to any of the stakeholders that need to know. The Project Manager will also make sure to document the change in any of the project documents including, the project management plan, any of the issue logs, anything that the change affects. To successfully manage change, the Project Manager needs to identify, evaluate, and communicate the potential impacts it will have on the overall project. The integrated change control process is what you would follow. No matter what the change, it's critical to communicate the effects of the change to any impacted stakeholders. Remember Project Management is all about communication.

Issue Log

All projects have issues.  An issue is anything related to the project that was unexpected. It could be anything from staff shortages to storage problems.

Not all issues turn into changes.  Some issues just need to be documented and recorded. The project issue log is the place to document every project issue that arises.  The issue log also serves as a document for other project managers to review to better predict potential issues or risks in future similar projects.

I wanted to talk about an important phase in project management that doesn't get discussed enough, but it's super important, and this is closing the project. You have met your milestones and the customer's happy, and now you're ready to move on. Hold on a second, not so fast. There's a process for closing the project. In this video, we'll discuss this process and why it's so important to the success of your future projects. Let's talk about the steps of closing the project and there's the process for it. First is confirmed that the project deliverables are complete. Have the requirements been met? Have we completed the project as defined by the scope? If we have, then we can hand off and gain acceptance. This is where we deliver the project and gain formal acceptance from the customer. This could be through a written document or even just an email, but something that states that the project is complete and that they accepted as delivered. Then we'll close procurement, and this is where we close the contracts by completing any outstanding payments and communicating with our suppliers that the work is complete.

Play video starting at :1:36 and follow transcript

1:36

Then we finish up any final performance reports. The project manager needs to measure and update the final performance reports. This includes any updates to the final budget, where we over, where we under budget or any variances to the schedule, did we complete the work on time? It also includes any quality metrics or charts that we've completed as well. Then we need to document any lessons learned. This is accomplished through something called a project postmortem meeting. This is where we get the project team together and discuss what went right, what went wrong, what would we have like to have done differently? All of those insights are documented so that we can share the knowledge, so that any future projects can use those lessons learned and adjust their project plans. Finally, we release our resources and celebrate. This means that we release any of the people who were working on the projects, so they can begin other projects. It's important to celebrate. Don't forget that part. Many projects can go on for months or even years, so we want to celebrate as a project team and celebrate the successes that we've had and shared together. The closing process is so necessary for the project team to end on a good note, the knowledge shared and the knowledge that's documented through the closing process could have positive impacts on your future projects and those that your team is working on. It's really the last step in closing the loop on successful project completion.

Project Post-Mortem & Knowledge Management

A Post Mortem meeting happens at the end of a project where the project team discusses and evaluates their performance in the overall project.

Knowledge Management

Knowledge Management is an area within Project Management that collects, archives, and shares knowledge between the project team, stakeholders, and others within the organization to learn from previous projects.

While planning our project, we reviewed any documents of similar projects to gain insight into the challenges and successes they experienced.  After your project Post Mortem, you will use knowledge gained to inform future projects.